## Work List
Exported on: 2026-10-05 15:12:51
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KHAMARIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA / GHUGHRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1735007031/DP/22012034562403 — PLANTATION CONTUR TRENCH KUKRATOLA KHAMARIYA | Ongoing | 408000 | 0 | 2022-09-15
MANDLA / GHUGHRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1735007031/DP/22012034562421 — PLANTATION GHUGHRA KE PASS KHAMARIYA | Ongoing | 408000 | 0 | 2022-09-30
MANDLA / GHUGHRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Raising of Nursery for Individuals / Raising of Nursery for Individuals | Nursery Development | 1735007031/IF/22012034582134 — FLODHYAN HARDYAL/HIRASING KHAMARIYA | Closed | 111599 | 0 | 2020-07-29
MANDLA / GHUGHRI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1735007031/IF/22012034649501 — बोल्डर मेडबंधन कार्य धरमाबाई/ सुमरित खम्हरिया | Closed | 57969 | 0 | 2021-04-25
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735007031/IF/22012035280088 — Khet Tala Nirman Karya Chamra/Narji Khamariya | Ongoing | 490197.1 | 0 | 2025-02-15
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735007031/IF/22012035285110 — बोल्डर मेड़ बन्धान कार्य रम्मु लाल /धनुआ सिह खम्हरिया | Approved | 0 | 0 | 2024-10-02
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735007031/IF/22012035289082 — Khet Talab Nirman Karya Rammu Lal/Dhanua Khamriya | Ongoing | 490197.1 | 0 | 2025-02-15
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735007031/IF/22012035316876 — Khet Talab Nirman Premvati/Sahdev Khamariya | Approved | 0 | 0 | 2025-03-08
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1735007031/IF/22012035356467 — Khet talab nirman kary Angad singh /Jagat singh Kaknu Khamriya | Approved | 492341.67 | 0 | 2025-04-01
MANDLA / GHUGHRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/3655321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166440 | Ongoing | 28500 | 0 | 2022-09-20
MANDLA / GHUGHRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/3657969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146250924 | Ongoing | 28500 | 0 | 2022-09-20
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4596680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123173847 | Ongoing | 28500 | 0 | 2024-11-12
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4611682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125548625 | Ongoing | 28500 | 0 | 2024-11-12
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4616865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126329877 | Ongoing | 28500 | 0 | 2024-11-12
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4621536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127124984 | Ongoing | 28500 | 0 | 2024-11-12
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4643830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141125741 | Ongoing | 28500 | 0 | 2025-02-11
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4648873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166360 | Ongoing | 28500 | 0 | 2024-11-12
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4648878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166756 | Ongoing | 28500 | 0 | 2025-04-08
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4651917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144799158 | Ongoing | 28500 | 0 | 2024-10-17
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4652039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146251005 | Ongoing | 28500 | 0 | 2025-04-05
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4668458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150262883 | Ongoing | 28500 | 0 | 2026-05-21
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4855231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126935708 | Ongoing | 28500 | 0 | 2025-04-03
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4855526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125077559 | Ongoing | 28500 | 0 | 2025-11-04
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4857850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150264466 | Ongoing | 28500 | 0 | 2025-10-10
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/4872930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145872188 | Ongoing | 28500 | 0 | 2026-04-22
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5181403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126931655 | Ongoing | 28500 | 0 | 2026-02-18
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5555726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123165449 | Ongoing | 28500 | 0 | 2026-02-20
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5560647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125719329 | Physically Completed | 28500 | 0 | 2025-11-04 | 2026-09-06
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5560882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144799583 | Ongoing | 28500 | 0 | 2026-02-20
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5561164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126926616 | Ongoing | 28500 | 0 | 2025-05-13
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5561957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126924196 | Ongoing | 28500 | 0 | 2026-03-13
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5564550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125550085 | Approved | 28500 | 0 | 2025-03-27
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5564601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150262288 | Ongoing | 28500 | 4800 | 2026-08-22
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5564602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150262502 | Ongoing | 28500 | 0 | 2025-05-13
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5564698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150262951 | Approved | 28500 | 0 | 2025-02-27
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5564787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126950382 | Approved | 28500 | 0 | 2025-02-27
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5565731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125048980 | Physically Completed | 28500 | 0 | 2025-11-04 | 2026-09-27
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5565968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146250468 | Ongoing | 28500 | 0 | 2025-11-19
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5618676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148699037 | Approved | 28500 | 0 | 2025-04-04
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5646447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144799368 | Approved | 28500 | 0 | 2025-02-27
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5666904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145872347 | Ongoing | 28500 | 0 | 2025-09-07
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5674680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145872729 | Physically Completed | 28500 | 4500 | 2025-10-29 | 2026-08-30
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150264317 | Approved | 28500 | 0 | 2025-03-27
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150264370 | Ongoing | 28500 | 4500 | 2025-12-07
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150264621 | Ongoing | 28500 | 0 | 2026-04-28
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144800425 | Ongoing | 28500 | 0 | 2026-05-01
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123054840 | Ongoing | 28500 | 0 | 2026-02-28
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148698918 | Ongoing | 28500 | 4800 | 2026-03-26
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141125670 | Approved | 28500 | 0 | 2025-05-30
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144798991 | Ongoing | 28500 | 0 | 2025-09-07
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144799220 | Ongoing | 28500 | 0 | 2025-09-07
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144799414 | Ongoing | 28500 | 0 | 2025-09-07
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144799774 | Ongoing | 28500 | 0 | 2026-04-20
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144799837 | Ongoing | 28500 | 0 | 2026-02-18
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166217 | Ongoing | 28500 | 0 | 2026-02-25
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166249 | Ongoing | 28500 | 0 | 2026-01-08
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166410 | Ongoing | 28500 | 0 | 2026-04-22
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166455 | Ongoing | 28500 | 0 | 2026-02-17
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166589 | Ongoing | 28500 | 9600 | 2026-04-22
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166657 | Approved | 28500 | 0 | 2025-02-27
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150262005 | Ongoing | 28500 | 0 | 2025-11-19
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150262099 | Approved | 28500 | 0 | 2025-02-27
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126080020 | Physically Completed | 28500 | 0 | 2025-11-19 | 2026-09-06
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145872292 | Approved | 28500 | 0 | 2025-04-22
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145872532 | Approved | 28500 | 0 | 2025-02-27
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145872748 | Physically Completed | 28500 | 4500 | 2025-10-29 | 2026-09-06
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145872770 | Ongoing | 28500 | 9000 | 2026-02-20
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150263668 | Ongoing | 28500 | 0 | 2026-10-01
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5679799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150263709 | Ongoing | 28500 | 0 | 2026-03-06
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5720446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126082891 | Ongoing | 28500 | 4800 | 2026-03-13
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5720552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125574052 | Approved | 28500 | 0 | 2025-02-27
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5722730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123216687 | Ongoing | 28500 | 0 | 2026-02-20
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5723507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125703370 | Physically Completed | 24795 | 0 | 2026-03-13 | 2026-07-21
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5723510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125713166 | Ongoing | 28500 | 0 | 2026-01-08
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5724984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126328046 | Ongoing | 28500 | 0 | 2026-01-08
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5726713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150262547 | Approved | 28500 | 0 | 2025-02-27
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5726772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126919333 | Ongoing | 28500 | 0 | 2026-02-20
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5727560 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126918779 | Ongoing | 28500 | 0 | 2026-04-22
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5728561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125554027 | Ongoing | 28500 | 0 | 2026-02-20
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5728896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146251099 | Ongoing | 28500 | 0 | 2026-04-20
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5730663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125552997 | Ongoing | 28500 | 0 | 2026-04-28
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5730781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166297 | Ongoing | 28500 | 0 | 2026-04-08
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5730782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166492 | Ongoing | 28500 | 0 | 2026-10-01
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5798276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127112514 | Ongoing | 28500 | 0 | 2026-06-12
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5798354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126081229 | Ongoing | 28500 | 0 | 2025-11-04
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5798615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150264908 | Physically Completed | 28500 | 0 | 2026-03-06 | 2026-09-27
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5798629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150262053 | Ongoing | 28500 | 4800 | 2025-10-30
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5798640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123167565 | Ongoing | 28500 | 0 | 2026-02-20
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5798667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126452307 | Ongoing | 28500 | 0 | 2026-03-13
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5798675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124961080 | Ongoing | 28500 | 0 | 2026-02-20
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5798701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148698946 | Ongoing | 28500 | 4800 | 2026-04-24
MANDLA / GHUGHRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5810198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148699012 | Approved | 28500 | 0 | 2025-03-27
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5951096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146251137 | Ongoing | 28500 | 0 | 2026-04-20
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5952824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123185334 | Ongoing | 28500 | 4800 | 2026-04-28
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5953472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126946804 | Ongoing | 28500 | 0 | 2026-05-21
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5953856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125856205 | Ongoing | 28500 | 0 | 2026-04-20
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5955738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123384453 | Ongoing | 28500 | 0 | 2026-04-20
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5956044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166518 | Ongoing | 28500 | 4500 | 2026-04-22
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5956045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166636 | Approved | 28500 | 0 | 2025-05-09
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5957587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150264750 | Ongoing | 28500 | 0 | 2026-09-01
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5958741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150263871 | Ongoing | 28500 | 0 | 2026-04-29
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5959460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166316 | Ongoing | 28500 | 0 | 2026-04-22
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5959461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142166428 | Ongoing | 28500 | 4500 | 2026-04-29
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5960625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126925773 | Ongoing | 28500 | 0 | 2026-04-22
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5961768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144799706 | Ongoing | 28500 | 4800 | 2026-04-20
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5961769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144799994 | Ongoing | 28500 | 0 | 2026-04-29
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5961920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148698591 | Ongoing | 28500 | 0 | 2026-04-20
MANDLA / GHUGHRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5961921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148698660 | Approved | 28500 | 0 | 2026-02-03
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5961922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148698718 | Ongoing | 28500 | 0 | 2026-04-22
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5965403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150263965 | Ongoing | 28500 | 9000 | 2026-09-01
MANDLA / GHUGHRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1735007031/IF/IAY/5966647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145871976 | Ongoing | 28500 | 0 | 2026-04-20
MANDLA / GHUGHRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1735007031/WH/22012034932556 — JAA STOP DAM MARAMMAT KARYA BAKAL NALA 1 KAKNU KHAMARIYA | Ongoing | 318771.06 | 0 | 2022-05-11
MANDLA / GHUGHRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1735007031/WH/22012034932759 — JAA STOP DAM MARAMMAT KARYA GAURIDABRA 02 KHAMARIYA | Ongoing | 347617.53 | 0 | 2022-05-11