## Work List
Exported on: 2026-09-07 06:47:09
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SURAJPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDLA / MAWAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1735009037/DP/22012034561715 — Maa ki bagiya anganbadi semartola | Ongoing | 34200 | 0 | 2022-08-05
MANDLA / MAWAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1735009037/DP/22012034561902 — Maa ki bagiya gram panchyat bhaban surajpura | Ongoing | 34200 | 0 | 2022-08-05
MANDLA / MAWAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1735009037/IF/22012035510565 — JGAY 2025 Recharge Structur Kapildhara Koop Samaru/ Amrit (1735009037/IF/22012034323612) Surajpura | Approved | 0 | 0 | 2025-04-14
MANDLA / MAWAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1735009037/IF/22012035510621 — JGAY 2025 Recharge Structur Kapildhara Koop Samaru/ Mansing ((1735009037/IF/2201203432066) Bilaikhar | Approved | 0 | 0 | 2025-04-14
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735009037/IF/22012035616991 — Ek bagiya maa ke nam hit nankusiya bai gram bilaikhar | Ongoing | 158688.74 | 0 | 2025-10-16
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735009037/IF/22012035628652 — EK BAGIYA MAA KE NAAM GEETA TEKAM GP SURAJPURA | Ongoing | 158688.74 | 0 | 2025-10-16
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735009037/IF/22012035628655 — EK BAGIYA MAA KE NAAM KALI AYYAM GP SURAJPURA | New | 0 | 0 | 2025-10-01
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735009037/IF/22012035628661 — EK BAGIYA MAA KE NAAM SAVITA BAI CHHATTROO SINGH GP SURAJPURA | Ongoing | 158688.74 | 0 | 2025-10-16
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1735009037/IF/22012035653069 — Ek bagiya maa ke nam hit Santoshi gram Bilaikhar | Ongoing | 166616.45 | 0 | 2026-01-25
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735009037/IF/22012035659672 — Khet Talab Nirman Kary -Mattu Lal /Sunher Singh Surajpura | New | 0 | 0 | 2025-04-14
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735009037/IF/22012035660999 — Khet talab Nirman karya Heera Singh/Lakhni Singh | New | 0 | 0 | 2026-01-26
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735009037/IF/22012035661147 — Khet Talab Nirman Kary -Heera Singh /Lakhanu Singh | Ongoing | 450884.72 | 0 | 2026-02-24
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735009037/IF/22012035661149 — Khet Talab Nirman Kary -Sattu Singh /Sunher Singh | New | 0 | 0 | 2026-01-26
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735009037/IF/22012035661691 — Khet Talab Nirman Kary Son Singh /Jugta Singh | Ongoing | 450884.72 | 0 | 2026-02-24
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735009037/IF/22012035662385 — Khet Talab Nirman Kary Baisakhu Singh /Tapsuram | Approved | 0 | 0 | 2026-02-07
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1735009037/IF/22012035662387 — Khet Talab Nirman Kary Mattu Dhan Singh /Fagu Singh | Approved | 0 | 0 | 2026-02-07
MANDLA / MAWAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/2723596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5237068 | Ongoing | 28500 | 0 | 2023-08-19
MANDLA / MAWAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/2723644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5244551 | Ongoing | 28500 | 0 | 2023-08-19
MANDLA / MAWAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/2992654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5218359 | Ongoing | 28500 | 0 | 2021-06-26
MANDLA / MAWAI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/426938 — Construction of IAY House -IAY REG. NO. MP1373609 | Approved | 28500 | 0 | 2017-01-04
MANDLA / MAWAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/4478797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151941234 | Ongoing | 28500 | 0 | 2024-04-25
MANDLA / MAWAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/4478800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151941268 | Ongoing | 28500 | 2100 | 2024-04-25
MANDLA / MAWAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/4480501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152009582 | Ongoing | 28500 | 0 | 2024-06-25
MANDLA / MAWAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/4480509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152009712 | Ongoing | 28500 | 0 | 2024-05-08
MANDLA / MAWAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/4498810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152009470 | Ongoing | 28500 | 0 | 2024-07-26
MANDLA / MAWAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/4813579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152062727 | Physically Completed | 24795 | 1500 | 2024-11-14 | 2026-08-09
MANDLA / MAWAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/4813583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152062734 | Ongoing | 28500 | 1500 | 2024-11-14
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/5643390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143889430 | Ongoing | 28500 | 8400 | 2025-06-10
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/5653051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121542843 | Ongoing | 28500 | 16800 | 2025-07-27
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/5653944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121388200 | Ongoing | 28500 | 12600 | 2025-07-27
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/5654427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124265335 | Ongoing | 28500 | 0 | 2025-07-27
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/5655319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143889756 | Ongoing | 28500 | 0 | 2025-08-22
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/5655667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124269983 | Ongoing | 28500 | 16800 | 2025-07-27
MANDLA / MAWAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/5717220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124270494 | Ongoing | 28500 | 0 | 2025-08-22
MANDLA / MAWAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1735009037/IF/IAY/5827218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150970364 | Approved | 28500 | 0 | 2025-02-28
MANDLA / MAWAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1735009/DP/22012034548506 — उन्नत प्रजाति का शहतूत पौधरोपण कार्य (ट्री टाईप 06 एकड़) बिलाईखार | Ongoing | 648114 | 0 | 2022-04-26
MANDLA / MAWAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1735/WC/22012035306721 — Amrit Sarover Talab Nirman Karya Surajpura | Ongoing | 3988000 | 0 | 2025-06-14