## Work List
Exported on: 2026-10-10 14:09:47
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: DHUNSAVANI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / TAMIA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1736001025/DP/22012034443904 — Sarvajanik Koop Nirman Khedodhana Dhusawani | Ongoing | 445000 | 129520 | 2023-10-07
CHHINDWARA / TAMIA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plntation-Biodrainage-Wastelands for comm / Bio-drainage Plantation for Community | Plantation | 1736001025/DP/22012034621845 — Vrikchha ropan karya chandi mai pahadi dhusawani | Ongoing | 813250.34 | 6000 | 2024-07-13
CHHINDWARA / TAMIA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plntation-Biodrainage-Wastelands for comm / Bio-drainage Plantation for Community | Plantation | 1736001025/DP/22012034621851 — Vrikchha ropan karya Umar jhil pahadi dhusawani | Ongoing | 813250.34 | 1800 | 2024-07-13
CHHINDWARA / TAMIA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plntation-Biodrainage-Wastelands for comm / Bio-drainage Plantation for Community | Plantation | 1736001025/DP/22012034621863 — Vrikchha ropan karya murgal jodi pahadi dhusawani | Ongoing | 813250.34 | 5700 | 2024-08-31
CHHINDWARA / TAMIA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plntation-Biodrainage-Wastelands for comm / Bio-drainage Plantation for Community | Plantation | 1736001025/DP/22012034621883 — Vrikchha ropan karya sham shan ghat pahadi dhusawani | Ongoing | 813250.34 | 1500 | 2024-07-13
CHHINDWARA / TAMIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1736001025/IC/22012034889560 — Sarwjanik koop sichai hetu moyapani dhusawani | Approved | 547943.65 | 0 | 2025-01-27
CHHINDWARA / TAMIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736001025/IF/22012035271390 — kapil dhara koop ramvati brijpalsa dhusawani | Physically Completed | 310586.35 | 0 | 2025-04-21 | 2026-09-28
CHHINDWARA / TAMIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736001025/IF/22012035271402 — kapil dhara koop suresh hanuman dhusawani | Ongoing | 310586.35 | 0 | 2025-04-21
CHHINDWARA / TAMIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736001025/IF/22012035276720 — Kapil dhara koop harbansa maniram dhusawani | Ongoing | 312155.12 | 0 | 2025-03-23
CHHINDWARA / TAMIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736001025/IF/22012035299791 — Kapil Dhara Koop Baliram Sukarlal Moyapani Dhusawani | Approved | 310586.35 | 0 | 2025-01-27
CHHINDWARA / TAMIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plntation Horti-TreesIndividual / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736001025/IF/22012035604473 — Ek Bagiya Maa Ke Naam Krashna Bai / Jatanpal Irpachi GP Dhusawani | Ongoing | 283886.03 | 300 | 2025-09-04
CHHINDWARA / TAMIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736001025/IF/22012035604547 — Ek Bagiya Maa Ke Naam Surajbati / Prakash Irpachi Gp Dhusawani | Ongoing | 283886.03 | 0 | 2025-09-06
CHHINDWARA / TAMIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736001025/IF/22012035607241 — Ek Bagiya Maa ke Naam Jayanti Bai Vijaypalshah Irpachi Dhusawani | Ongoing | 283886.03 | 0 | 2025-09-04
CHHINDWARA / TAMIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736001025/IF/22012035607250 — Ek Bagiya Maa ke Naam Shivkumari Yuvraj Irpachi Dhusawani | Ongoing | 283886.03 | 0 | 2025-09-04
CHHINDWARA / TAMIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736001025/IF/22012035607259 — Ek Bagiya Maa ke Naam Sanjna Sarjan Irpachi Dhusawani | Ongoing | 283886.03 | 0 | 2025-11-04
CHHINDWARA / TAMIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736001025/IF/22012035607268 — Ek Bagiya Maa ke Naam Rajkumari Ashok Irpachi Dhusawani | Ongoing | 283886.03 | 0 | 2025-09-04
CHHINDWARA / TAMIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736001025/IF/22012035607280 — Ek Bagiya Maa ke Naam Khemanlata Harpal Irpachi Dhusawani | Ongoing | 283886.03 | 0 | 2025-09-04
CHHINDWARA / TAMIA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1736001025/WC/22012035242026 — Nistari Talab Nirman KaryaChital Khobri Nala Dhusawani | Ongoing | 2269989.97 | 352360 | 2025-02-05
CHHINDWARA / TAMIA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1736001025/WC/22012035242374 — parkoliton tenk kusumvali nala dhusawani | Approved | 499083.26 | 0 | 2024-10-03
CHHINDWARA / TAMIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1736001025/WC/22012035274044 — Dug Well Richarge Nirman Karya kaloni Dhusawani | Approved | 23899.46 | 0 | 2025-04-15
CHHINDWARA / TAMIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1736001025/WC/22012035274065 — Dug Well Richarge Nirman Karya Rajdhana Dhusawani | Approved | 23899.46 | 0 | 2025-04-15
CHHINDWARA / TAMIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1736001025/WC/22012035274085 — Dug Well Richarge Nirman Karya bhimsan mohlla Dhusawani | Approved | 23899.46 | 0 | 2025-04-15
CHHINDWARA / TAMIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1736001025/WC/22012035274254 — Dug Well Richarge Nirman Karya khedodhana Dhusawani | Approved | 23899.46 | 0 | 2025-04-15
CHHINDWARA / TAMIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1736001025/WC/22012035274258 — Dug Well Richarge Nirman Karya rajdhana Dhusawani | Approved | 23899.46 | 0 | 2025-04-15
CHHINDWARA / TAMIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1736001025/WC/22012035274265 — Dug Well Richarge Nirman Karya Toldhana Dhusawani | Approved | 23899.46 | 0 | 2025-04-15
CHHINDWARA / TAMIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1736001025/WC/22012035274267 — Dug Well Richarge Nirman Karya umardhana Dhusawani | Approved | 23899.46 | 0 | 2025-04-15
CHHINDWARA / TAMIA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1736/RC/22012034560463 — Sudoor Sadak Main Road Rajdhana To Veer Pathar 1.80 Km Gram Veerpathar | Ongoing | 4970000 | 0 | 2023-10-06