## Work List
Exported on: 2026-10-05 04:11:09
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MARKAWADA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Construction of Biogas Plant for Community | Bio-gas plant | 1736003070/AV/22012034658287 — PLANTATION WORK GROUP A JAGATRAM RAMJI BARMAAN MANESHI PUNOO BALAKRAM DHATURIYA | New | 0 | 0 | 2024-06-08
CHHINDWARA / AMARWARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation-Horticulture - Community / Canal Line Plantation for Community | Plantation | 1736003070/DP/22012034604086 — AMRIT VATIKA- GEETAGANGA MARG TALAB KEY PASS MARKAWARA | Ongoing | 55847.4 | 0 | 2023-09-20
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Groups / Construction of Irrigation Well for Groups | Construction of Well | 1736003070/IC/22012034885145 — PLANTATION WORK GROUP A JAGATRAM RAMJI BARMAAN MANESHI PUNOO BALAKRAM DHATURIYA | New | 0 | 0 | 2024-06-08
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Groups / Construction of Irrigation Well for Groups | Construction of Well | 1736003070/IC/22012034885339 — EAK PEDE MAA KEY NAAM BRECHAROPAN WORK GROUP A DHATURIYA | New | 0 | 0 | 2024-07-22
CHHINDWARA / AMARWARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1736003070/IF/22012035048734 — KAPILDHARA KOOP NIRMAN - BABULAL/UDEYRAM MEHARA | Ongoing | 239422.69 | 0 | 2023-03-14
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252108 — EAK PEDE MAA KEY NAAM BRECHAROPAN WORK JAGATRAM/BHAIYALAL AHARWAR DHATURIYA | Ongoing | 162536.83 | 8100 | 2024-12-15
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252116 — EAK PEDE MAA KEY NAAM BRECHAROPAN WORK RAMJI/CHANDARLAL AHARWARA DHATURIYA | Ongoing | 162536.83 | 13800 | 2024-12-15
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252120 — EAK PEDE MAA KEY NAAM BRECHAROPAN WORK PRAKASH/MEHTAR AHARWARA DHATURIYTA | Ongoing | 162536.83 | 0 | 2024-12-15
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252127 — EAK PEDE MAA KEY NAAM BRECHAROPAN WORK MANESHI/MAHESH UIKEY DHATURIYA | Ongoing | 162536.83 | 24300.12 | 2024-12-15
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252129 — EAK PEDE MAA KEY NAAM BRECHAROPAN WORK PUNU/CHAINSI UIKEY DHATURIYA | Ongoing | 157536.83 | 0 | 2024-12-15
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252136 — EAK PEDE MAA KEY NAAM BRECHAROPAN WORK BALAKERAM/SAKARLAL DHURVE DHATURIYA | Ongoing | 148282.63 | 0 | 2024-12-15
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252139 — EAK PEDE MAA KEY NAAM BRECHAROPAN WORK RATNU/MANGLU BHARTI MARKAWARA | Ongoing | 147536.83 | 8400 | 2024-12-15
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252172 — EAK PADE MAA KE NAAM BRECHAROPAN WORK CHAMRA/JAGE BHARTI MARKAWARA | Ongoing | 147536.83 | 17700 | 2024-12-15
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252174 — EAK PADE MAA KE NAAM BRECHAROPAN WORK MITTHAN/SUKALI INWATI MARKAWARA | Ongoing | 148034.03 | 6300 | 2024-12-15
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252176 — EAK PADE MAA KE NAAM BRECHAROPAN WORK IMARTI/RAMRATAN UIKEY MARKAWARA | Ongoing | 147536.83 | 11700 | 2024-12-15
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252179 — EAK PADE MAA KEY NAAM BRECHAROPAN WORK DAYARAM/PUSOO SAHU MARKAWARA | Ongoing | 147536.83 | 0 | 2024-12-15
CHHINDWARA / AMARWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Wasteland)-Farm Forestry individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736003070/IF/22012035252185 — EAK PADE MAA KEY NAAM BRECHAROPAN WORK KEVALRAM/JAGDESHPRASAD SANODIYA MARKAWARA | Ongoing | 147636.83 | 0 | 2024-12-15
CHHINDWARA / AMARWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736003070/IF/22012035390735 — KAPILDHARA KOOP NIRMAN-MANAKCHAND/RADHELAL MALVI MARKAWARA | Ongoing | 292850.99 | 0 | 2025-05-16
CHHINDWARA / AMARWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736003070/IF/22012035405587 — KAPILDHARA KOOP NIRMAN-CHAMELI/AMARLAL TELI MARKAWARA | Ongoing | 299556.38 | 0 | 2025-05-16
CHHINDWARA / AMARWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736003070/IF/22012035411002 — KAPILDHARA KOOP NIRMAN-SUSHILA/SEHTAR BANJARA MARKAWARA | New | 0 | 0 | 2025-04-25
CHHINDWARA / AMARWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736003070/IF/22012035418901 — KHET TALAB NIRMAN LEKHRAM/NARAYAN GOULEY MARKAWARA | Ongoing | 375876.3 | 0 | 2025-05-11
CHHINDWARA / AMARWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736003070/IF/22012035457807 — KAPILDHARA KOOP NIRMAN-PRAVEEN/BHURA BHARIYA MARKAWARA | Ongoing | 314271.89 | 0 | 2025-06-07
CHHINDWARA / AMARWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736003070/IF/22012035457849 — KAPILDHARA KOOP NIRMAN-DHANARAM/JHEENA BHARIYA MARKAWARA | Ongoing | 316404.61 | 0 | 2025-06-10
CHHINDWARA / AMARWARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736003070/IF/IAY/3769310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126578942 | Completed | 28500 | 0 | 2023-02-16 | 2026-09-16
CHHINDWARA / AMARWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736003070/IF/IAY/5174060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107078710 | Completed | 28500 | 0 | 2025-05-19 | 2026-09-16
CHHINDWARA / AMARWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736003070/IF/IAY/5184278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115388448 | Completed | 28500 | 0 | 2025-05-03 | 2026-09-16
CHHINDWARA / AMARWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736003070/IF/IAY/5938124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126877269 | Physically Completed | 28500 | 6960 | 2026-05-19 | 2026-09-16
CHHINDWARA / AMARWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736003070/IF/IAY/5940149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127972681 | Physically Completed | 28500 | 3915 | 2026-05-19 | 2026-09-16
CHHINDWARA / AMARWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736003070/IF/IAY/5940325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122099592 | Physically Completed | 28500 | 3915 | 2026-05-19 | 2026-09-16
CHHINDWARA / AMARWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736003070/IF/IAY/5941217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117179605 | Physically Completed | 28500 | 3915 | 2026-05-19 | 2026-09-16
CHHINDWARA / AMARWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736003070/IF/IAY/6134862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126862410 | Physically Completed | 28500 | 3915 | 2026-05-19 | 2026-09-16
CHHINDWARA / AMARWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736003070/IF/IAY/6142528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118042070 | Physically Completed | 28500 | 3915 | 2026-05-19 | 2026-09-16
CHHINDWARA / AMARWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736003070/IF/IAY/6157365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127973678 | Physically Completed | 28500 | 3915 | 2026-05-19 | 2026-09-16
CHHINDWARA / AMARWARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736003070/IF/IAY/6175533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118818522 | Physically Completed | 28500 | 3915 | 2026-05-19 | 2026-09-16
CHHINDWARA / AMARWARA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736003070/WC/VB/22012035330000 — COUNTUR TRENCH CCT STAGGERED NIRMAN SAKRUTOLA MARG GHATI MAI DHATURIYA | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / AMARWARA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736003070/WC/VB/22012035330006 — BOLDER CHEK DAM NIRMAN MANGIBUDA NALA KEKDA ROAD PASS MARKAWARA | New | 0 | 0 | 2026-06-05
CHHINDWARA / AMARWARA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736003070/WC/VB/22012035330014 — BOLDER CHEK DAM NIRMAN MANGIBUDA NALA KEKDA ROAD PASS MARKAWARA | Approved | 0 | 0 | 2026-06-05