## Work List
Exported on: 2026-10-11 06:30:38
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: PALADAUN
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1736004035/AV/22012034548052 — Boldar Bal Nirmand Kary PLay Ground Paladoun | Completed | 1040425.21 | 916813.6 | 2021-02-05 | 2024-12-13
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/181 — पालादौन/व्रक्षारोपण कार्य/पालादौन | Completed | 25000 | 9034 | 2011-07-11 | 2013-01-31
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1736004035/DP/194 — पालादौन/ निर्मल वाटिका निर्माण कार्य पालादौन | Completed | 500000 | 50026 | 2011-08-24 | 2011-12-04
CHHINDWARA / CHAURAI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004035/DP/22012034434252 — Paladon Nirmal Neer Nadi ke pass | Completed | 445000 | 455050.63 | 2018-12-27 | 2023-11-24
CHHINDWARA / CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1736004035/DP/22012034596587 — PALADOUN PLANTATION SCHOOL KE PASS | Completed | 55847.4 | 29370 | 2023-09-11 | 2026-04-22
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/322 — पालादौन/ निर्मल वाटिका निर्माण कार्य (सुरेश/ अनखलाल)पालादौन | Completed | 4000 | 2464 | 2011-09-20 | 2011-09-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/323 — पालादौन/ निर्मल वाटिका निर्माण कार्य (हवीव/ गेदलाल )पालादौन | Completed | 4000 | 1714 | 2011-09-20 | 2011-09-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/324 — पालादौन/ निर्मल वाटिका निर्माण कार्य (गुलदास /हजरत )पालादौन | Completed | 4000 | 2464 | 2011-09-20 | 2011-09-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/325 — पालादौन/ निर्मल वाटिका निर्माण कार्य (सुल्‍तान/ हजरत )पालादौन | Completed | 4000 | 982 | 2011-09-20 | 2011-09-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/326 — पालादौन/ निर्मल वाटिका निर्माण कार्य (बनवारी/ सालिकरा )पालादौन | Completed | 4000 | 2464 | 2011-09-20 | 2011-09-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/327 — पालादौन/ निर्मल वाटिका निर्माण कार्य ( लक्ष्‍मण/ खडकसिंग )पालादौन | Completed | 4000 | 4264 | 2011-09-20 | 2011-09-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/328 — पालादौन/ निर्मल वाटिका निर्माण कार्य ( रमेश/ भैयालाल )पालादौन | Completed | 4000 | 4264 | 2011-09-20 | 2011-09-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/329 — पालादौन/ निर्मल वाटिका निर्माण कार्य (ि‍वजय /बालक )पालादौन | Completed | 4000 | 4264 | 2011-09-20 | 2011-09-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/330 — पालादौन/ निर्मल वाटिका निर्माण कार्य (रामदयाल/प्रभुदयाल )पालादौन | Completed | 4000 | 4264 | 2011-09-20 | 2011-09-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/331 — पालादौन/ निर्मल वाटिका निर्माण कार्य (असरफ/ सबदल )पालादौन | Completed | 4000 | 4264 | 2011-09-27 | 2011-10-02
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/332 — पालादौन/ निर्मल वाटिका निर्माण कार्य (सिकन्‍दर/ नाशर)पालादौन | Completed | 4000 | 1714 | 2011-09-27 | 2011-10-02
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/333 — पालादौन/ निर्मल वाटिका निर्माण कार्य (ख्‍यालीराम/ मूरत )पालादौन | Completed | 4000 | 2464 | 2011-09-27 | 2011-10-02
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/334 — पालादौन/ निर्मल वाटिका निर्माण कार्य (श्रीराम /गयाप्रसाद )पालादौन | Completed | 4000 | 1732 | 2011-09-27 | 2011-10-02
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/335 — पालादौन/ निर्मल वाटिका निर्माण कार्य (बलवान/ जनूल )पालादौन | Completed | 4000 | 2464 | 2011-09-27 | 2011-10-02
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/336 — पालादौन/ निर्मल वाटिका निर्माण कार्य (उनद/ कमोदसिंग )पालादौन | Completed | 4000 | 4264 | 2011-09-27 | 2011-10-02
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/337 — पालादौन/ निर्मल वाटिका निर्माण कार्य (केदार/ कल्‍लूनाथ )पालादौन | Completed | 4000 | 4264 | 2011-09-27 | 2011-10-02
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/338 — पालादौन/ निर्मल वाटिका निर्माण कार्य (नेतराम/ मेहनू )पालादौन | Completed | 4000 | 2464 | 2011-09-27 | 2011-10-02
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/339 — पालादौन/ निर्मल वाटिका निर्माण कार्य (कासीराम/शिवराम )पालादौन | Completed | 4000 | 2464 | 2011-09-27 | 2011-12-04
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/35/1 — पालादौन/व्रक्षारोपण कार्य /मोहगांव मार्ग पर | Completed | 100000 | 59657 | 2007-07-23 | 2013-01-31
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/359 — पालादोन/ निर्मल वाटिका निर्माण कार्य (छचना/ झनका)पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/360 — पालादोन/ निर्मल वाटिका निर्माण कार्य (केरा /रामजी )पालादौन | Completed | 4000 | 4864 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/361 — पालादोन/ निर्मल वाटिका निर्माण कार्य (मीता /रामसिंग )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/362 — पालादोन/ निर्मल वाटिका निर्माण कार्य (मेहगू /सूखा )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/363 — पालादोन/ निर्मल वाटिका निर्माण कार्य (मोहनसिंग/बहोरी )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/364 — पालादोन/ निर्मल वाटिका निर्माण कार्य (कोमल/बहोरी )पालादौन | Completed | 4000 | 4864 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/365 — पालादोन/ निर्मल वाटिका निर्माण कार्य (मनीराम/चितांमन )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/366 — पालादोन/ निर्मल वाटिका निर्माण कार्य (जयसिंग/पूरनलाल )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/367 — पालादोन/ निर्मल वाटिका निर्माण कार्य (रामदीन /झाडू )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/368 — पालादोन/ निर्मल वाटिका निर्माण कार्य (महतू/मेहगू )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/369 — पालादोन/ निर्मल वाटिका निर्माण कार्य (मोमीन/न्‍यजामअली )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/370 — पालादोन/ निर्मल वाटिका निर्माण कार्य (संतोष /रामप्रसाद )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/371 — पालादोन/ निर्मल वाटिका निर्माण कार्य (गनपत/ बलीराम )पालादौन | Completed | 4000 | 4864 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/372 — पालादोन/ निर्मल वाटिका निर्माण कार्य (पीतम /परताप )पालादौन | Completed | 4000 | 29176 | 2011-10-13 | 2012-03-18
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/373 — पालादोन/ निर्मल वाटिका निर्माण कार्य (रेखराम/जबर )पालादौन | Completed | 4000 | 4264 | 2011-10-11 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/374 — पालादोन/ निर्मल वाटिका निर्माण कार्य (तुरकसिंग/ बलराम )पालादौन | Completed | 4000 | 4264 | 2011-10-11 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/375 — पालादोन/ निर्मल वाटिका निर्माण कार्य (परसराम/रामप्रसाद )पालादौन | Completed | 4000 | 4264 | 2011-10-11 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/376 — पालादोन/ निर्मल वाटिका निर्माण कार्य (सुमनअली/न्‍याजमअली )पालादौन | Completed | 4000 | 4264 | 2011-10-04 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/377 — पालादोन/ निर्मल वाटिका निर्माण कार्य (सुमल/ पंचकोडी )पालादौन | Completed | 4000 | 4264 | 2011-10-04 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/378 — पालादोन/ निर्मल वाटिका निर्माण कार्य (सोमन /खडकसिंग )पालादौन | Completed | 4000 | 4264 | 2011-10-04 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/399 — पालादौन/ निर्मल वाटिका निर्माण कार्य (अनखनलाल/अंदन )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/400 — पालादौन/ निर्मल वाटिका निर्माण कार्य (सखाराम/दोलडी )पालादौन | Completed | 4000 | 7432 | 2011-10-13 | 2012-03-18
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/401 — पालादौन/ निर्मल वाटिका निर्माण कार्य (झाडू/मेहताप )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/402 — पालादौन/ निर्मल वाटिका निर्माण कार्य (मकबूल/नब्‍बू )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/403 — पालादौन/ निर्मल वाटिका निर्माण कार्य (कशीराम/शिवबगस )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/404 — पालादौन/ निर्मल वाटिका निर्माण कार्य (मलखान/खडकसिंग )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/405 — पालादौन/ निर्मल वाटिका निर्माण कार्य (मौजे /मेहगू )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-04
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/406 — पालादौन/ निर्मल वाटिका निर्माण कार्य (जमनाप्रसाद/दौकडी )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-11
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/407 — पालादौन/ निर्मल वाटिका निर्माण कार्य (कल्‍लूनाथ/कमलनाथ )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-11
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/408 — पालादौन/ निर्मल वाटिका निर्माण कार्य (महेशनाथ/बुध्‍दनाथ )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-11
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/409 — पालादौन/ निर्मल वाटिका निर्माण कार्य (कलीराम/शंकर )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-18
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/410 — पालादौन/ निर्मल वाटिका निर्माण कार्य (गनपत/बलीराम )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-18
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/411 — पालादौन/ निर्मल वाटिका निर्माण कार्य (कौशल /जगदीश )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-18
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/412 — पालादौन/ निर्मल वाटिका निर्माण कार्य (सखिया/रामसिंग )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/413 — पालादौन/ निर्मल वाटिका निर्माण कार्य (देवी/साेमा )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/414 — पालादौन/ निर्मल वाटिका निर्माण कार्य (लेखराम/सोमा )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/415 — पालादौन/ निर्मल वाटिका निर्माण कार्य (तुकाराम/किसनलाल )पालादौन | Completed | 4000 | 2464 | 2011-10-13 | 2011-12-25
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004035/DP/416 — पालादौन/ निर्मल वाटिका निर्माण कार्य (अशोक/द्धारकाप्रसाद )पालादौन | Completed | 4000 | 4264 | 2011-10-13 | 2011-12-25
CHHINDWARA / CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004035/IF/1000026019 — पालादौन मदनमोहन वर्मा | Completed | 72000 | 39040 | 2013-07-25 | 2014-08-12
CHHINDWARA / CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004035/IF/1000038962 — पालादौन भू शिल्‍प पीतम परताप वर्मा पालादौन | Completed | 58000 | 39420 | 2013-12-30 | 2014-02-11
CHHINDWARA / CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004035/IF/1000046059 — पालादौन बकरी सेड मदन पिता झडु | Completed | 50000 | 48132 | 2013-12-12 | 2014-09-28
CHHINDWARA / CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004035/IF/1000046063 — पालादौन मेडबंधान कालूराम पिता इंद्ररलाल | Completed | 75000 | 45360 | 2014-02-06 | 2014-08-10
CHHINDWARA / CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004035/IF/1000046069 — पालादौन मेड बधान सुभानअली मंसूरी | Completed | 43000 | 32120 | 2013-12-12 | 2013-12-17
CHHINDWARA / CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004035/IF/1000055333 — Paladaun sok pit nirman kary subhan ali paladaun | Completed | 4500 | 2920 | 2013-12-12 | 2014-08-10
CHHINDWARA / CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Poultry Shelter / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1736004035/IF/1000062708 — paladoun poulty shed subhanali mansuri s/o nyajam | Completed | 54000 | 50008 | 2014-03-03 | 2014-09-12
CHHINDWARA / CHAURAI | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1736004035/IF/1000062734 — paladoun Goet shed shyamlal / shammudayal | Completed | 50000 | 46320 | 2014-04-23 | 2014-09-12
CHHINDWARA / CHAURAI | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1736004035/IF/1000063987 — paladoun goet shed neelsing /nanhelal | Completed | 50000 | 49670 | 2014-09-22 | 2014-09-28
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736004035/IF/22012034355029 — Plantation play ground paladaun | Completed | 335000 | 49164 | 2017-06-28 | 2022-11-02
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004035/IF/22012034580931 — Nab Naino arched Vipat/ Tularam paladoni | Completed | 60000 | 39853 | 2021-01-11 | 2024-07-14
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004035/IF/22012034580934 — NAb naino arched Shekh jameel Nabbu | Completed | 60000 | 22476 | 2021-01-11 | 2024-08-27
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004035/IF/22012034589544 — NAB Subhan ali /Nayajm ali Mansoori paladon | Completed | 60000 | 24980 | 2021-01-11 | 2025-01-14
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004035/IF/22012034589547 — NAb Jafarali/Eidkhaa paladon | Completed | 60000 | 31190 | 2021-01-11 | 2026-01-27
CHHINDWARA / CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1736004035/IF/22012034589549 — NAB Guldas /Hajrat Mansoori PAladon | Completed | 60000 | 26560 | 2021-01-11 | 2026-01-27
CHHINDWARA / CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004035/IF/22012035095378 — khet talab girija /Laxman | Completed | 490000.87 | 403796.5 | 2023-05-20 | 2024-05-17
CHHINDWARA / CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004035/IF/22012035103721 — khet talab kasiram Soman lodhi | Completed | 377055.91 | 316895 | 2023-06-27 | 2024-06-25
CHHINDWARA / CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004035/IF/22012035103729 — Rajgir Soman lodhi paladon | Completed | 377055.91 | 308160 | 2023-06-27 | 2024-06-25
CHHINDWARA / CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1736004035/IF/22012035110299 — khet talab nirman Ankumar paladon | Completed | 377055.91 | 318500 | 2023-06-21 | 2024-06-22
CHHINDWARA / CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004035/IF/22012035189657 — कपिलधारा कूप संतोष पिता खडगसिंग पालादोन | Completed | 273400.02 | 264925.85 | 2024-03-11 | 2026-01-21
CHHINDWARA / CHAURAI | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1736004035/IF/9926742741 — Paladon/ Goet Shed Kuber/ | Completed | 50000 | 39144 | 2014-07-16 | 2014-08-12
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1011308 — Construction of IAY House -IAY REG. NO. MP1609085 | Completed | 16340 | 16356 | 2018-10-20 | 2019-06-30
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1037307 — Construction of IAY House -IAY REG. NO. MP2789994 | Completed | 16340 | 16344 | 2017-05-24 | 2019-06-26
CHHINDWARA / CHAURAI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/107500 — Construction of IAY House -IAY REG. NO. MP-36-004-035-001/111 | Completed | 15105 | 15030 | 2016-02-23 | 2017-03-03
CHHINDWARA / CHAURAI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/107501 — Construction of IAY House -IAY REG. NO. MP-36-004-035-001/17 | Completed | 15105 | 13694 | 2016-02-23 | 2018-11-23
CHHINDWARA / CHAURAI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/107502 — Construction of IAY House -IAY REG. NO. MP-36-004-035-001/97 | Completed | 15105 | 8076 | 2016-02-23 | 2018-11-23
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1154118 — Construction of IAY House -IAY REG. NO. MP2736601 | Completed | 16340 | 16530 | 2018-06-09 | 2019-02-15
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1207293 — Construction of IAY House -IAY REG. NO. MP3595300 | Completed | 16340 | 16182 | 2018-06-23 | 2019-06-25
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1230943 — Construction of IAY House -IAY REG. NO. MP2764394 | Completed | 16340 | 16530 | 2018-11-19 | 2019-06-08
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1381884 — Construction of IAY House -IAY REG. NO. MP1248249 | Completed | 18050 | 17490 | 2018-11-19 | 2023-03-28
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1522606 — Construction of IAY House -IAY REG. NO. MP3851371 | Completed | 16340 | 15660 | 2018-05-26 | 2019-03-30
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1657580 — Construction of IAY House -IAY REG. NO. MP3808157 | Completed | 16530 | 16722 | 2018-11-19 | 2020-08-05
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1659597 — Construction of IAY House -IAY REG. NO. MP3877280 | Completed | 16530 | 16182 | 2018-05-26 | 2019-08-04
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1702294 — Construction of IAY House -IAY REG. NO. MP1387549 | Completed | 18050 | 17334 | 2018-11-19 | 2021-12-12
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1723803 — Construction of IAY House -IAY REG. NO. MP3853009 | Completed | 16530 | 16530 | 2018-06-23 | 2019-05-24
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/1937196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2033257 | Completed | 16530 | 16530 | 2018-11-19 | 2019-06-08
CHHINDWARA / CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2119281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4528305 | Completed | 18050 | 17132 | 2019-08-02 | 2023-02-07
CHHINDWARA / CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2121453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4556168 | Completed | 18050 | 17066 | 2019-08-02 | 2023-02-07
CHHINDWARA / CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2124425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4650876 | Completed | 18050 | 17336 | 2019-08-02 | 2023-02-07
CHHINDWARA / CHAURAI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2150396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5278278 | Completed | 16720 | 16182 | 2019-08-02 | 2020-06-05
CHHINDWARA / CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2524088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4658365 | Completed | 18050 | 17493 | 2020-06-09 | 2021-12-11
CHHINDWARA / CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2729863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4444573 | Completed | 18050 | 17952 | 2022-07-19 | 2022-11-30
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2738755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5251529 | Completed | 18050 | 17678 | 2021-06-06 | 2023-02-07
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2739029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5000808 | Completed | 18050 | 18874 | 2021-05-08 | 2022-07-11
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2747763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4675133 | Completed | 18050 | 17924 | 2021-05-22 | 2023-06-10
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2750593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4253615 | Completed | 18050 | 17569 | 2021-05-01 | 2023-06-10
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2751895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5125285 | Completed | 18050 | 18009 | 2021-05-18 | 2022-09-30
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2753086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5173062 | Completed | 18050 | 18709 | 2021-06-06 | 2022-06-10
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2756711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5181175 | Completed | 18050 | 17671 | 2021-07-18 | 2023-06-10
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2857691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2792489 | Completed | 18050 | 16625 | 2021-10-23 | 2024-05-14
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2871971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5251525 | Completed | 18050 | 5404 | 2021-10-23 | 2024-08-23
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2872183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5267612 | Completed | 18050 | 17871 | 2021-06-06 | 2024-05-14
CHHINDWARA / CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2875636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5555585 | Completed | 18050 | 17833 | 2022-10-01 | 2023-07-08
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2876254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5267640 | Completed | 18050 | 18025 | 2021-05-08 | 2022-09-13
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2927416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4439813 | Completed | 18050 | 17578 | 2021-06-06 | 2024-05-14
CHHINDWARA / CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2929212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5521936 | Completed | 18050 | 17884 | 2022-08-26 | 2023-07-08
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2932942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4264791 | Completed | 18050 | 17136 | 2021-05-22 | 2023-03-28
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2985326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3497894 | Completed | 18050 | 17901 | 2021-05-22 | 2023-06-10
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2988775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4529390 | Completed | 18050 | 17926 | 2021-05-22 | 2024-05-14
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/2992332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5101908 | Completed | 18050 | 14938 | 2021-06-07 | 2024-12-25
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/3110775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2789862 | Completed | 18335 | 17413 | 2021-11-24 | 2023-07-08
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/3111199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5522830 | Completed | 18335 | 18301 | 2021-09-23 | 2022-11-22
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/3117188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4241588 | Completed | 18335 | 17563 | 2021-06-06 | 2021-12-12
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/3117645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2721763 | Completed | 18335 | 18309 | 2021-06-06 | 2023-06-07
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/3217504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1263279 | Completed | 18335 | 18329 | 2021-09-16 | 2022-09-30
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/3219509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5250197 | Completed | 18335 | 18160 | 2021-09-16 | 2023-07-08
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/3219812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1474411 | Completed | 18335 | 18127 | 2021-11-11 | 2023-06-10
CHHINDWARA / CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/3220116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5260257 | Completed | 18335 | 17901 | 2022-10-01 | 2024-05-14
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/3220132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3860322 | Completed | 18335 | 18335 | 2021-09-16 | 2022-09-30
CHHINDWARA / CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/3317243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5243974 | Completed | 18335 | 15470 | 2023-05-13 | 2024-05-14
CHHINDWARA / CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/4376665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145218418 | Completed | 19380 | 17901 | 2023-08-24 | 2023-11-14
CHHINDWARA / CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/4381713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118846827 | Completed | 19380 | 17017 | 2023-04-13 | 2024-05-14
CHHINDWARA / CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/4399281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118846938 | Completed | 20995 | 17017 | 2023-07-29 | 2024-05-14
CHHINDWARA / CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/4400506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118823940 | Completed | 20995 | 12376 | 2023-07-29 | 2024-05-14
CHHINDWARA / CHAURAI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/453234 — Construction of IAY House -IAY REG. NO. MP1609062 | Completed | 15865 | 16458 | 2017-03-25 | 2019-03-30
CHHINDWARA / CHAURAI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/52003 — Construction of IAY House -IAY REG. NO. MP-36-004-035-001/98 | Completed | 15105 | 16026 | 2016-02-23 | 2019-06-25
CHHINDWARA / CHAURAI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/564008 — Construction of IAY House -IAY REG. NO. MP3808177 | Completed | 15865 | 16188 | 2017-03-04 | 2019-06-26
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/882640 — Construction of IAY House -IAY REG. NO. MP1898446 | Completed | 16340 | 16422 | 2017-05-24 | 2019-02-15
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/884353 — Construction of IAY House -IAY REG. NO. MP1922043 | Completed | 16340 | 16284 | 2017-05-24 | 2019-02-15
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/885094 — Construction of IAY House -IAY REG. NO. MP1932969 | Completed | 16340 | 16158 | 2018-03-08 | 2019-06-08
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/886817 — Construction of IAY House -IAY REG. NO. MP1956813 | Completed | 16340 | 17466 | 2017-05-24 | 2018-11-23
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/886901 — Construction of IAY House -IAY REG. NO. MP1958185 | Completed | 16340 | 16260 | 2017-05-24 | 2019-02-15
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/888909 — Construction of IAY House -IAY REG. NO. MP1984456 | Completed | 16340 | 16362 | 2017-05-24 | 2018-06-22
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/890104 — Construction of IAY House -IAY REG. NO. MP2001279 | Completed | 16340 | 16308 | 2017-05-24 | 2019-06-08
CHHINDWARA / CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/891545 — Construction of IAY House -IAY REG. NO. MP2019611 | Completed | 18050 | 17944 | 2020-08-28 | 2022-11-22
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/934700 — Construction of IAY House -IAY REG. NO. MP2710824 | Completed | 16340 | 16200 | 2017-05-24 | 2018-07-15
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/935474 — Construction of IAY House -IAY REG. NO. MP2730533 | Completed | 16340 | 16386 | 2017-05-24 | 2019-06-08
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/936204 — Construction of IAY House -IAY REG. NO. MP2747390 | Completed | 16340 | 16308 | 2017-05-24 | 2019-06-30
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/936209 — Construction of IAY House -IAY REG. NO. MP2747544 | Completed | 16340 | 16506 | 2017-12-04 | 2019-07-20
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/936728 — Construction of IAY House -IAY REG. NO. MP2758847 | Completed | 16340 | 16260 | 2017-05-24 | 2019-02-15
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/936996 — Construction of IAY House -IAY REG. NO. MP2763455 | Completed | 16340 | 15996 | 2017-05-24 | 2019-06-08
CHHINDWARA / CHAURAI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/937213 — Construction of IAY House -IAY REG. NO. MP2768073 | Completed | 18050 | 16980 | 2018-06-23 | 2023-03-28
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/968577 — Construction of IAY House -IAY REG. NO. MP3513910 | Completed | 16340 | 15426 | 2017-05-24 | 2019-06-24
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/971654 — Construction of IAY House -IAY REG. NO. MP3595290 | Completed | 16340 | 15660 | 2017-05-24 | 2019-02-15
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/974299 — Construction of IAY House -IAY REG. NO. MP3657406 | Completed | 16340 | 16146 | 2017-05-24 | 2019-06-08
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/978607 — Construction of IAY House -IAY REG. NO. MP3825141 | Completed | 16340 | 16506 | 2017-05-24 | 2019-02-15
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/980166 — Construction of IAY House -IAY REG. NO. MP3887452 | Completed | 16340 | 15516 | 2017-05-24 | 2019-02-15
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/988961 — Construction of IAY House -IAY REG. NO. MP1611886 | Completed | 16340 | 16446 | 2017-05-24 | 2018-12-28
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/990067 — Construction of IAY House -IAY REG. NO. MP1958048 | Completed | 16340 | 16008 | 2017-05-24 | 2019-03-30
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/996977 — Construction of IAY House -IAY REG. NO. MP3513880 | Completed | 16340 | 16398 | 2017-05-24 | 2019-06-08
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/996999 — Construction of IAY House -IAY REG. NO. MP3521582 | Completed | 16340 | 15564 | 2017-05-24 | 2019-03-30
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004035/IF/IAY/997001 — Construction of IAY House -IAY REG. NO. MP3521750 | Completed | 16340 | 15960 | 2017-05-24 | 2019-08-04
CHHINDWARA / CHAURAI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004035/LD/298 — पालादौन /मेढ बंधान कार्य/ राजकुमार/श्रीचन्‍द/पालादौन | Completed | 17000 | 7735 | 2009-04-01 | 2010-03-25
CHHINDWARA / CHAURAI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004035/LD/306 — पालादौन मेंड बंधान कार्य नरायण/अंतराम | Completed | 17000 | 14496 | 2009-04-15 | 2009-11-20
CHHINDWARA / CHAURAI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004035/LD/308 — पालादोन मेंड बंधान कार्य श्रीदेवी/सोमा | Completed | 17000 | 15300 | 2009-05-14 | 2009-11-20
CHHINDWARA / CHAURAI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004035/LD/309 — पालादौन मेंड बंधान कार्य रामकली/इंदरलाल | Completed | 17000 | 13050 | 2009-03-18 | 2010-03-25
CHHINDWARA / CHAURAI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004035/LD/3799408083 — पालादौन खेल मैदान निर्माण कार्य टावर के पास पालादौ | Completed | 369000 | 346822.8 | 2013-09-28 | 2017-05-30
CHHINDWARA / CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1736004035/LD/3799408086 — पालादौन शांतिधाम स‍ह चबुतरा निर्माण कार्य पालादौन | Completed | 270000 | 221994.9 | 2013-09-28 | 2017-08-27
CHHINDWARA / CHAURAI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004035/LD/385 — पालादौन/मेढबंधान कार्य/मीता/रामसिंग | Completed | 17000 | 10920 | 2009-06-16 | 2010-03-25
CHHINDWARA / CHAURAI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004035/LD/447 — पालादौन /मेढ बंधान कार्य/ कुन्‍दन/कपूरचंद/पालादौन | Completed | 17000 | 11466 | 2009-11-20 | 2010-03-25
CHHINDWARA / CHAURAI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736004035/RC/22012034218203 — पालादौन जी.एस.बी.मार्ग सह पुलिया निर्माण नारायण के | Completed | 1497000 | 679607 | 2014-05-17 | 2017-10-25
CHHINDWARA / CHAURAI | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004035/RC/22012034298887 — Paladon panchparmeswar C.C. road 110 m Hakim ke ghar se alava tak | Completed | 82000 | 53232 | 2016-02-23 | 2016-06-09
CHHINDWARA / CHAURAI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004035/RC/22012034515033 — सी सी सडक निर्माण कार्य पालादौन मोहन सोनी के घ्रर से शिवमंदिर तक 160 मीटर | Completed | 61200 | 60720 | 2020-02-15 | 2020-03-20
CHHINDWARA / CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004035/RC/22012034537686 — फर्सीकरण कार्य बाजार चौक पालादौन | Completed | 52500 | 47880 | 2020-10-03 | 2020-12-11
CHHINDWARA / CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1736004035/RC/22012034549376 — रोड रिनोवेशन कार्य माता मन्दिर से सरूप वर्मा के धर तक 800 मिटर | Completed | 55000 | 13788 | 2021-02-06 | 2024-12-16
CHHINDWARA / CHAURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004035/RC/22012034657907 — cc road preetam verma keghar se sarkaree koop tak 50mtr | Completed | 24000 | 23130 | 2023-10-07 | 2024-01-03
CHHINDWARA / CHAURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004035/RC/22012034657912 — cc road ganpat verma ke ghar se sundarlal ke ghar tak 100 Mtr paladon | Completed | 48000 | 47085 | 2023-10-07 | 2024-01-03
CHHINDWARA / CHAURAI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004035/RC/340 — पालादौन/ द्धितीय श्रैणी मार्ग पालादौन से झिरिया के | Completed | 498000 | 439172 | 2010-05-10 | 2016-05-31
CHHINDWARA / CHAURAI | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004035/RC/35/1 — पालादौन/दितीय श्रेणी मार्ग/पालादौन से बंधीढाना मार्ग | Completed | 481000 | 754106 | 2007-05-26 | 2007-03-23
CHHINDWARA / CHAURAI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004035/RC/388 — पालादौन/पालादौन से बांधीढाना घनश्‍याम के खेत से नाला तक द्धितीय श्रैणी | Completed | 498000 | 144666 | 2010-12-26 | 2010-05-01
CHHINDWARA / CHAURAI | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736004035/RC/477 — पालादौन/ शम्‍मूदयाल खेत से नाला तक द्धि.श्रै.पालादौन से झिरिया रोड तक भाग 2 | Completed | 498000 | 244306 | 2011-05-30 | 2016-05-31
CHHINDWARA / CHAURAI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004035/RC/609 — पालादौन/सी.सी.सडक र्निमाण कार्य(पंच परमेशवर+MNREGA | Completed | 141000 | 86910 | 2012-07-23 | 2014-03-28
CHHINDWARA / CHAURAI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1736004035/RS/22012034645182 — Paladon Maa Ki Bagiya m s paladon | Completed | 8002.93 | 5380 | 2022-05-27 | 2024-07-14
CHHINDWARA / CHAURAI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1736004035/RS/22012034648789 — Swachhta parisat Paladon | Completed | 44000 | 36188 | 2022-05-27 | 2024-07-14
CHHINDWARA / CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1736004035/RS/22012035133887 — CC Nali Nirman Pitam ke Ghar se Sarkari Koop tak | Completed | 38484 | 36220 | 2024-11-26 | 2025-02-16
CHHINDWARA / CHAURAI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1736004035/RS/22012035133888 — CC Nali Nirman Kamalnath ke Ghar se Garabsing Ke Ghar tak 100 m | Completed | 38484 | 38106 | 2025-12-20 | 2026-02-25
CHHINDWARA / CHAURAI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/22012034427132 — Paladon Bolder Chek Dam Soni k khet k pass nala me | Completed | 192000 | 142974 | 2018-12-27 | 2021-02-04
CHHINDWARA / CHAURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004035/WC/22012034978744 — Box trench nirman Satish verma ke ghar se aage ki or 1 km | Completed | 790844.22 | 689250 | 2022-11-17 | 2026-04-11
CHHINDWARA / CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004035/WC/22012035075455 — box trench nirman kaliram ke ghar ke pass se shankar ke khet tak 2.5 km paladon | Completed | 762553.66 | 621135 | 2023-06-21 | 2024-07-02
CHHINDWARA / CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004035/WC/22012035193484 — Box Trench Sarkari hendpamp se Jagdish Verma ke khet tak | Completed | 789394.31 | 649469 | 2024-03-18 | 2024-07-02
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75037 — पालादौन/कपिल धारा कूप निमार्ण कार्य/कुंदन/कपूरचंद/चमार/पालादौन | Completed | 100000 | 99870 | 2008-01-01 | 2009-11-20
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75038 — पालादौन/कपिल धारा कूप निमार्ण कार्य/रामकुमार/श्रीचंद/पालादौन | Completed | 142000 | 89227 | 2008-01-07 | 2010-03-25
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75039 — पालादौन/कपिल धारा कूप निमार्ण कार्य/तुकाराम/किसनलाल/पालादौन | Completed | 100000 | 93166 | 2008-01-07 | 2010-03-25
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75261 — पालादौन /कपिलधारा कूपनिर्माण कार्य /रामदयाल /प्रभुदयाल /पालादौन | Completed | 100000 | 95394 | 2008-01-07 | 2010-03-25
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75262 — पालादौन /कपिलधारा कूपनिर्माण कार्य /नारायण /अंतराम /पालादौन | Completed | 100000 | 72405 | 2008-01-07 | 2010-03-25
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75263 — पालादौन /कपिलधारा कूपनिर्माण कार्य /मीतीबाई /रामसिंग /पालादौन | Completed | 100000 | 133982 | 2008-01-10 | 2009-11-20
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75264 — पालादौन /कपिलधारा कूपनिर्माण कार्य /रामकली /इन्‍दरलाल /पालादौन | Completed | 142000 | 91453 | 2007-12-14 | 2010-03-25
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75265 — पालादौन /कपिलधारा कूपनिर्माण कार्य /आसाडू /गुमान /पालादौन | Completed | 142000 | 80747 | 2007-12-14 | 2010-03-25
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75266 — पालादौन /कपिलधारा कूपनिर्माण कार्य /रेखन /मेहगू /पालादौन | Completed | 142000 | 820449.5 | 2008-01-07 | 2007-11-30
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75267 — पालादौन /कपिलधारा कूपनिर्माण कार्य /श्रीराम /गयाप्रसाद /पालादौन | Completed | 142000 | 94613 | 2008-01-15 | 2010-03-25
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75350 — पालादौन /कपिल धारा कूप निमार्ण कार्य/ मदन /झाडू/वर्मा/ पालादौन | Completed | 100000 | 63465 | 2008-01-10 | 2010-03-25
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75351 — पालादौन /कपिल धारा कूप निमार्ण कार्य/ देवी /सोमा/कतिया/पालादौन | Completed | 142000 | 215778 | 2008-01-08 | 2010-03-25
CHHINDWARA / CHAURAI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004035/WC/75438 — पालादौन/ कपिलधारा कूप निर्माण कार्य जयसिंग/पूरनलालवर्मा | Completed | 142000 | 127435.6 | 2009-05-20 | 2010-03-25
CHHINDWARA / CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004035/WC/75744 — पालादौन/ कपिल धारा कूप निर्माण कार्य (फग्‍गू/ उमेर | Completed | 148000 | 244284 | 2011-03-12 | 2014-08-15
CHHINDWARA / CHAURAI | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004035/WC/75745 — पालादौन/ कपिल धारा कूप निर्माण कार्य (इदबी /झाडू )पालादौन | Completed | 148000 | 150362 | 2011-03-12 | 2013-11-30
CHHINDWARA / CHAURAI | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004035/WC/75746 — पालादौन/ कपिल धारा कूप निर्माण कार्य (सखाराम/ दोकौडी )पालादौन | Completed | 148000 | 20877 | 2011-03-12 | 2014-03-15
CHHINDWARA / CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004035/WC/75747 — पालादौन/ कपिल धारा कूप निर्माण कार्य (प्रीतम/ प्रर | Completed | 275000 | 242128.7 | 2011-03-16 | 2014-08-12
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004035/WC/75919 — पालादौन/ कपिल धारा कूप निर्माण कार्य (विनोद/ झाडू वर्मा)पालादौन | Completed | 188000 | 111264 | 2012-02-08 | 2013-11-30
CHHINDWARA / CHAURAI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004035/WC/76072 — पालादौन/ कपिल धारा कूप निर्माण कार्य (जमनाप्रसाद/दौकडी )पालादौन | Completed | 498000 | 29550 | 2012-04-01 | 2014-10-10