## Work List
Exported on: 2026-10-11 10:49:21
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SIRAS
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / CHAURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1736004056/AV/22012034643114 — बोल्डर वाल निर्माण कार्य शांति धाम पर सिरस(भाग 2) | Physically Completed | 396919.54 | 0 | 2023-10-07 | 2026-07-23
CHHINDWARA / CHAURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov building Block Plantation-Farm Forestry-Comm / Plantation in Institutions for Community | Plantation | 1736004056/DP/22012034616793 — वृक्षारोपण कार्य शांति धाम पर ग्राम पंचायत सिरस | Ongoing | 440974.24 | 113700 | 2024-06-12
CHHINDWARA / CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736004056/IF/22012035302368 — Hiteshi kapildhara Koop Nirman kary Shekh salim Ke khet Me Siras | Ongoing | 386937.84 | 0 | 2025-03-17
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736004056/IF/22012035583366 — Ek Bagiya Maa Ke Naam Sangya/Ashok Raghuwanshi Panchayat Siras | Ongoing | 284386.03 | 0 | 2025-09-09
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736004056/IF/22012035607763 — Ek Bagiya Maa Ke Naam Suman/Mangal singh Raghuwanshi Gram Panchayat Siras | Ongoing | 284386.03 | 0 | 2025-09-03
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736004056/IF/22012035648654 — Ek Bagiya Maa Ke Naam Rukhmani/Vipat Raghuwanshi Panchayat Siras | Ongoing | 284387.37 | 10800 | 2025-12-20
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736004056/IF/22012035648663 — Ek Bagiya Maa Ke Naam Saroj/Chainsingh Raghuwanshi Panchayat Siras | Ongoing | 284387.37 | 10800 | 2025-12-20
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736004056/IF/22012035648665 — Ek Bagiya Maa Ke Naam Sharmila Raghuwanshi Panchayat Siras | Approved | 0 | 0 | 2025-07-24
CHHINDWARA / CHAURAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736004056/WC/VB/YD/22012035335998 — contour trench mata mandir pahadi siras | Ongoing | 801693.35 | 0 | 2026-10-04