## Work List
Exported on: 2026-10-21 09:34:46
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: NEELKATHI KHURD
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / CHAURAI | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1736004077/AV/22012034567881 — Gp neelkanthi khurd shantidham me shed nirman karya | Completed | 196981.11 | 192564.26 | 2022-11-22 | 2024-07-05
CHHINDWARA / CHAURAI | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1736004077/AV/22012034594758 — Bolder boundri wall nirman karya mata mandir ke pas gp neelkanthi khurd | Completed | 279714.69 | 98235 | 2025-09-20 | 2026-07-10
CHHINDWARA / CHAURAI | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1736004077/AV/22012034624565 — 10 Unit nadep nirman karya gp neelkanthi khurd | Completed | 191983.4 | 188594.87 | 2022-12-01 | 2024-07-05
CHHINDWARA / CHAURAI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004077/DP/125 — नीलकंठी खुर्द - जेडरोपा प्‍लान टेशन(माला मां पहाडी) | Completed | 254000 | 43265 | 2009-05-30 | 2013-01-31
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1736004077/DP/22012034490744 — Samudayik plantation karya panchayat bhavan parisar me gp neelkanthi khurd | Completed | 390851.61 | 303576.58 | 2020-10-20 | 2025-07-28
CHHINDWARA / CHAURAI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1736004077/DP/22012034537441 — 200 unit plantation karya mata mandir pahadi per gp neelkanthi khurd | Completed | 394489.84 | 225562.68 | 2021-10-08 | 2024-07-14
CHHINDWARA / CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1736004077/DP/22012034588077 — Vasudha bandan amrrit vatika shantidham ke pas gp neelkanthi khurd | Completed | 55847.4 | 45158.31 | 2023-09-03 | 2026-01-21
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736004077/DP/90 — व्रक्षारोपण कार्य नीलकंटी खुर्द | Completed | 100000 | 47332 | 2007-07-25 | 2013-01-31
CHHINDWARA / CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004077/IF/1000048125 — नीलकंठीखुर्द पशु शेड निर्माण राधेश्‍याम हरली मेहरा | Completed | 93000 | 75044 | 2013-12-21 | 2016-02-02
CHHINDWARA / CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004077/IF/1000048133 — नीलकंठीखुर्द पशु शेड सोपचंद पिता गरीबा मेहरा | Completed | 48000 | 44410 | 2013-12-21 | 2014-05-27
CHHINDWARA / CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004077/IF/1000048137 — नीलकंठीखुद्र मवेशी आश्रय मनश्‍याम पिता हरली | Completed | 93000 | 86783 | 2013-12-21 | 2015-07-02
CHHINDWARA / CHAURAI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736004077/IF/1000068697 — mavesi shed mansu bisnu neelkanthee khurd | Completed | 47000 | 42730 | 2014-02-08 | 2014-04-27
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736004077/IF/22012034342055 — Hitaisi kapildhara koop sumariya (gopchand) /laxman Neelkanthi khurd | Completed | 200000 | 147000 | 2017-05-22 | 2021-05-31
CHHINDWARA / CHAURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736004077/IF/22012034357924 — neelkanthi khurd plantation work shantidham | Completed | 168000 | 42798 | 2017-06-28 | 2021-12-24
CHHINDWARA / CHAURAI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1736004077/IF/22012034466188 — MED BANDHAN KARYA PRAHLAD/BUDHMAN NEELKANTHI KHURD | Completed | 92000 | 85062 | 2019-05-22 | 2020-07-25
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004077/IF/22012034573181 — NAB Naino orchard Subhash/Natthu gp neelkanthi khurd | Completed | 60000 | 38553 | 2020-06-25 | 2023-07-09
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004077/IF/22012034576935 — NAB Naino orchard plantation Prahlad/buddhman gp neelkanthi khurd | Completed | 60000 | 41415 | 2020-06-25 | 2023-08-18
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1736004077/IF/22012034577058 — NAB Naino orchard plantation sopchand gareeba gp neelkanthi khurd | Completed | 60000 | 41247 | 2020-07-17 | 2023-03-30
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004077/IF/22012034585371 — NAB Naino orchard shreechand/janglu gp neelkanthi khurd | Completed | 60000 | 19095 | 2020-07-27 | 2023-10-07
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004077/IF/22012034585375 — NAB Naino orchard Bhairavsing/Natthu gp neelkanthi khurd | Completed | 60000 | 36561 | 2020-07-27 | 2023-11-06
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004077/IF/22012034590058 — NAB naino orchard shekh babu/shekh kavi gp neelkanthi khurd | Completed | 60000 | 39885 | 2020-09-23 | 2023-07-09
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004077/IF/22012034590065 — NAB naino orchard shekh munna/amjad gp neelkanthi khurd | Completed | 60000 | 41214 | 2020-09-06 | 2023-03-30
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004077/IF/22012034590070 — NAB naino orchard ganaram/manshu gp neelkanthi khurd | Completed | 60000 | 33321 | 2020-10-13 | 2023-11-06
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1736004077/IF/22012034590127 — NAB naino orchard rupsing/ramdayal gp neelkanthi khurd | Completed | 60000 | 40071 | 2020-07-27 | 2023-07-09
CHHINDWARA / CHAURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1736004077/IF/22012034940333 — Med bandhan karya Subhash/natthu | Completed | 101886.94 | 79800 | 2022-06-30 | 2024-08-23
CHHINDWARA / CHAURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1736004077/IF/22012034994698 — Med bandhan karya Ganesh/Mannu gp neelkanthi khurd | Completed | 151756.59 | 106870 | 2022-06-03 | 2024-08-07
CHHINDWARA / CHAURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1736004077/IF/22012034994742 — Med bandhan karya Jagdish/aman gp neelkanthi khurd | Completed | 32277.16 | 26130 | 2023-06-16 | 2024-08-16
CHHINDWARA / CHAURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1736004077/IF/22012034994803 — Med bandhan karya Moharsing/balbansing gp neelkanthi khurd | Completed | 144068.4 | 75246 | 2022-11-26 | 2024-07-17
CHHINDWARA / CHAURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1736004077/IF/22012034994823 — Med bandhan karya Fulver/ramdayal gp neelkanthi khurd | Completed | 10459.27 | 7650 | 2022-12-03 | 2023-07-09
CHHINDWARA / CHAURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004077/IF/22012034994855 — Khet talab Ganesh/mannu gp neelkanthi khurd | Completed | 116607.32 | 87318 | 2023-06-09 | 2024-09-30
CHHINDWARA / CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736004077/IF/22012034994862 — Khet talab Dhaneeram/manshu gp neelkanthi khurd | Completed | 116607.32 | 87561 | 2023-02-15 | 2024-09-30
CHHINDWARA / CHAURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1736004077/IF/22012035038722 — Med bandhan karya bhairavsing/natthu Gp neelkanthi khurd | Completed | 83539.23 | 65934 | 2023-03-02 | 2024-07-17
CHHINDWARA / CHAURAI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/107611 — Construction of IAY House -IAY REG. NO. MP-36-004-077-001/48 | Completed | 15105 | 15030 | 2016-06-11 | 2017-09-07
CHHINDWARA / CHAURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/2430863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5196105 | Completed | 18050 | 18050 | 2020-05-09 | 2021-04-20
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/2754612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5230826 | Completed | 18050 | 18281 | 2021-04-04 | 2022-02-21
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/2756598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5252761 | Completed | 18050 | 17316 | 2021-04-04 | 2022-05-26
CHHINDWARA / CHAURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/2756599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5252789 | Completed | 18050 | 16912 | 2021-04-04 | 2022-01-04
CHHINDWARA / CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/3693037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105330012 | Completed | 19380 | 19380 | 2022-07-15 | 2023-01-30
CHHINDWARA / CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/3693045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105330993 | Completed | 19380 | 19261 | 2022-07-15 | 2023-06-23
CHHINDWARA / CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/3881977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147200147 | Completed | 19380 | 18954 | 2024-10-23 | 2025-02-27
CHHINDWARA / CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/3883453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147232732 | Completed | 19380 | 19380 | 2022-07-15 | 2023-01-30
CHHINDWARA / CHAURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/4238508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147230426 | Completed | 19380 | 19057 | 2022-09-02 | 2023-06-23
CHHINDWARA / CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/4654188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147395976 | Completed | 23085 | 21870 | 2024-10-18 | 2025-02-05
CHHINDWARA / CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/4689625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106417590 | Completed | 23085 | 22356 | 2024-10-18 | 2025-04-14
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/4980843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147228113 | Completed | 24795 | 23337 | 2025-04-02 | 2025-05-30
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/4989094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105331572 | Completed | 24795 | 22779 | 2025-04-02 | 2025-08-23
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/4989436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106417541 | Completed | 24795 | 23337 | 2025-04-02 | 2025-05-30
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/4989437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106417628 | Completed | 24795 | 23337 | 2025-04-02 | 2025-05-30
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/4989438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106417662 | Completed | 24795 | 23337 | 2025-04-02 | 2025-05-30
CHHINDWARA / CHAURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/4989440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106417795 | Completed | 24795 | 24309 | 2025-03-27 | 2025-05-30
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5006685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120228006 | Completed | 24795 | 23094 | 2025-04-02 | 2025-05-30
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5006710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120233696 | Completed | 24795 | 23085 | 2025-04-02 | 2025-05-17
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5007476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120235146 | Completed | 24795 | 22905 | 2025-04-02 | 2025-06-15
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147191103 | Completed | 24795 | 23337 | 2025-04-02 | 2025-06-12
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147203264 | Completed | 24795 | 22077 | 2025-04-09 | 2025-08-22
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147206098 | Completed | 24795 | 22644 | 2025-04-02 | 2025-08-23
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147213324 | Completed | 24795 | 23058 | 2025-04-02 | 2025-08-23
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147220522 | Completed | 24795 | 23094 | 2025-04-01 | 2025-05-30
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147220592 | Completed | 24795 | 22952 | 2025-04-02 | 2025-09-01
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147223908 | Completed | 24795 | 20961 | 2025-04-02 | 2025-08-23
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147232748 | Completed | 24795 | 23337 | 2025-04-02 | 2025-05-30
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147244111 | Completed | 24795 | 22356 | 2025-04-02 | 2026-01-09
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147383407 | Completed | 24795 | 22842 | 2025-04-02 | 2025-06-10
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147383670 | Completed | 24795 | 20178 | 2025-04-02 | 2025-08-22
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147385156 | Completed | 24795 | 22922 | 2025-04-02 | 2025-06-15
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5099958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147385293 | Completed | 24795 | 22527 | 2025-04-02 | 2025-09-10
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5100017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147395918 | Completed | 24795 | 22982 | 2025-04-02 | 2025-06-15
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5100018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147396040 | Completed | 24795 | 23337 | 2025-04-02 | 2025-05-30
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5100258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147618970 | Completed | 24795 | 22599 | 2025-04-02 | 2025-06-10
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5100261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147619665 | Completed | 24795 | 22113 | 2025-04-01 | 2025-05-18
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5100266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147620261 | Completed | 24795 | 23625 | 2025-05-05 | 2025-07-11
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5100271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147620379 | Completed | 24795 | 23337 | 2025-04-02 | 2025-05-30
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5100541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147688393 | Completed | 24795 | 23211 | 2025-04-02 | 2025-05-30
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5100745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147782042 | Completed | 24795 | 23337 | 2025-04-02 | 2025-05-30
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5697299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120231937 | Completed | 24795 | 22902 | 2025-07-30 | 2026-03-06
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5817048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116734952 | Completed | 24795 | 22924 | 2025-09-24 | 2025-12-26
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5817215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106417762 | Completed | 24795 | 22907 | 2025-10-17 | 2026-02-17
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5817569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147235909 | Completed | 24795 | 22938 | 2025-10-18 | 2026-01-09
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5817583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106466126 | Completed | 24795 | 22924 | 2025-09-24 | 2025-12-26
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5817812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147204685 | Completed | 24795 | 22938 | 2025-10-18 | 2026-01-09
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5817854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147620140 | Completed | 24795 | 22924 | 2025-09-24 | 2025-12-26
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5818654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120232940 | Completed | 24795 | 22924 | 2025-09-24 | 2025-12-26
CHHINDWARA / CHAURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736004077/IF/IAY/5818675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147213706 | Completed | 24795 | 22947 | 2025-10-18 | 2025-12-26
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004077/LD/1228 — नीलकंठी खुर्द/ मेढ बंधान कार्य निर्माण (लक्ष्‍मण/फुन्‍दू)नीलकंठी खुर्द | Completed | 28500 | 18480 | 2012-02-21 | 2012-04-25
CHHINDWARA / CHAURAI | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1736004077/LD/22012034233381 — Neelkanthi Khurd Shantidham Nirman Karya | Completed | 410000 | 209434 | 2015-10-24 | 2018-02-15
CHHINDWARA / CHAURAI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004077/LD/3799409140 — नीलकंठीखुर्द खेल मैदान प्राथ शाला नीलकंठीखुर्द | Completed | 381000 | 350935.5 | 2013-10-05 | 2014-08-13
CHHINDWARA / CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004077/LD/689 — नीलकंठी खुर्द /स्‍टाप डेम लघुमुल कार्य निर्माण कार्य (नीलकंठीखुद) | Completed | 162000 | 213989 | 2011-01-24 | 2012-03-31
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004077/LD/792 — नीलकंठी/ मेढ बंधान कार्य निर्माणा ( कौशल्‍या/ शंकर)नीलकंठीखुर्द | Completed | 23400 | 19296 | 2011-06-13 | 2013-06-30
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004077/LD/793 — नीलकंठी/ मेढ बंधान कार्य निर्माणा (गनेश/ मन्‍नू )नीलकंठीखुर्द | Completed | 23400 | 18300 | 2011-06-01 | 2011-06-23
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004077/LD/918 — नीलकंठी खुर्द/ मेढ बंधान कार्य निर्माण (सुमरिया/ लक्ष्‍मण) नीलकंठी खुर्द | Completed | 23300 | 19200 | 2011-06-24 | 2013-03-30
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004077/LD/919 — नीलकंठी खुर्द/ मेढ बंधान कार्य निर्माण (रामदयाल/ झाडू ) नीलकंठी खुर्द | Completed | 23300 | 13740 | 2011-07-16 | 2012-03-31
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004077/LD/920 — नीलकंठी खुर्द/ मेढ बंधान कार्य निर्माण (मंगल/ दुली | Completed | 23300 | 21114 | 2011-07-15 | 2014-08-08
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736004077/LD/921 — नीलकंठी खुर्द/ मेढ बंधान कार्य निर्माण (भैयालाल/ भिक्‍कू ) नीलकंठी खुर्द | Completed | 1170 | 8292 | 2011-07-16 | 2012-03-31
CHHINDWARA / CHAURAI | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004077/RC/141 — नीलकंठीखुर्द /द्वितीय श्रेणी मार्ग /नीलकंठी से सामरबोह खुर्द | Completed | 481000 | 401852 | 2008-01-05 | 2010-09-25
CHHINDWARA / CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004077/RC/22012034185379 — नीलकंठीखुर्द पीसीसी आईएपी मार्ग से मेखराम केघर एंव | Completed | 85000 | 52909 | 2013-10-05 | 2015-04-15
CHHINDWARA / CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004077/RC/22012034189560 — नीलकंठीखुर्द पीसीसी रामप्रकाश के घर से रामपत के घर | Completed | 90000 | 62191 | 2013-10-12 | 2015-04-15
CHHINDWARA / CHAURAI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004077/RC/22012034190331 — नीलकंठीखुर्द पीसीसी प्राथ शाला एंव आंगनवाडी 33 मी | Completed | 32000 | 21024 | 2013-10-19 | 2015-05-24
CHHINDWARA / CHAURAI | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736004077/RC/22012034288955 — Neelkanthikhurd Khet Sadak CC Road se Bajrang Thakur ke khet tak 800 Mtr. | Completed | 1450000 | 923571.99 | 2015-11-14 | 2019-06-30
CHHINDWARA / CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004077/RC/22012034505650 — C.C.ROAD NIRMAN KARYA MEN ROAD SE MOKCHADHAM TAK 50 M | Completed | 19500 | 19380 | 2020-10-04 | 2021-10-20
CHHINDWARA / CHAURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004077/RC/22012034550129 — CC sadak nirman karya men road se shantidham tak 50 meter gp neelkanthi khurd | Completed | 19000 | 11220 | 2020-12-01 | 2021-05-31
CHHINDWARA / CHAURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004077/RC/22012034591086 — C C SADAK NIRMAN KARYA MUNNA CHOURE KE MAKAN SE VIJAY MEHDOLE KE MAKAN TAK 110 M. GP NEELKANTHI KHU | Completed | 84000 | 50160 | 2021-11-13 | 2024-03-02
CHHINDWARA / CHAURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004077/RC/22012034663122 — C C NALI NIRMAN SANTOSH VERMA KE GHAR SE RADHESHYAM KE GHAR TAK NEELKANTHI KHURD | Completed | 35000 | 34405 | 2023-10-07 | 2024-04-20
CHHINDWARA / CHAURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004077/RC/22012034663137 — C C ROAD NIRMAN MANDRU CHOURE KE GHAR SE FAGGU CHOURE KE GHAR TAK NEELKANTHI KHURD | Completed | 48000 | 47886 | 2023-10-08 | 2024-05-02
CHHINDWARA / CHAURAI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004077/RC/428 — नीलकंठी खुर्द/सी.सी.सडक निर्माण कार्य | Completed | 100000 | 43384 | 2011-01-02 | 2011-01-14
CHHINDWARA / CHAURAI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736004077/RC/631 — Panch Parmeshwar Road Sukhram ke ghar se ramprakash ke ghar tak | Completed | 143000 | 134196 | 2012-05-15 | 2012-06-15
CHHINDWARA / CHAURAI | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736004077/RC/77/1 — दितीय श्रेणी मार्ग निमार्ण कार्य निलकठी खुर्द से निशानजानोजी | Completed | 481000 | 281135 | 2007-05-23 | 2010-09-25
CHHINDWARA / CHAURAI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736004077/RS/22012034410457 — Toilet nirman karya nainsing/jhadu chouriya neelkanthi khurd | Completed | 12000 | 11954 | 2018-07-20 | 2020-07-25
CHHINDWARA / CHAURAI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736004077/RS/22012034410459 — Toilet nirman karya durga/bhagela neelkanthi khurd | Completed | 12000 | 12054 | 2018-07-20 | 2019-11-26
CHHINDWARA / CHAURAI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736004077/RS/22012034410461 — Toilet nirman karya bhojelal/kaliram neelkanthi khurd | Completed | 12000 | 11184 | 2018-07-20 | 2018-12-25
CHHINDWARA / CHAURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1736004077/RS/22012035133602 — CC NALI NIRMAN KARYA NARAYAN CHOURE KE GHAR SE TIFNA NADI TAK 100 METER | Completed | 43000 | 41796 | 2024-11-21 | 2025-01-11
CHHINDWARA / CHAURAI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1736004077/WC/22012034446684 — Nala padopchar mangardhara pull ke paas avam nala gp neelkanthi khurd | Completed | 412000 | 382379 | 2019-05-16 | 2021-11-08
CHHINDWARA / CHAURAI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736004077/WC/22012034471883 — Contur trench nirman karya mata mandir pahadi per gp Neelkanthi khurd | Completed | 467235.65 | 404813 | 2019-12-04 | 2020-10-05
CHHINDWARA / CHAURAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1736004077/WC/22012034585779 — Contur trench 2nd part mata mandir pahadi per gp Neelkanthi khurd | Completed | 965195.55 | 623454.02 | 2021-01-02 | 2024-07-14
CHHINDWARA / CHAURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736004077/WC/22012034953400 — Nala padopchar avam check dam tifna nadi me gpp neelkanthi khurd | Completed | 804068.12 | 436598.64 | 2022-11-24 | 2024-08-04
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1736004077/WC/75336 — नीलकंठीखुर्द /शासकीय कूप निमार्ण कार्य/ परसगांव रोड पर/नीलकंठीखुर्द | Completed | 188000 | 294053 | 2008-01-05 | 2010-10-15
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004077/WC/75354 — नीलकंठी खुर्द/ कौशल्‍या बाई/ शंकर किरार ग्राम नीलकंठी खुर्द | Completed | 100000 | 145391 | 2007-11-06 | 2010-02-20
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004077/WC/75373 — नीलकंठी खुर्द /‍कपिल धारा कूप निमार्ण कार्य/ गनेश /मन्‍नू/ नीलकंठीखुर्द | Completed | 100000 | 106216 | 2008-01-06 | 2011-02-20
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004077/WC/75374 — नीलकंठी खुर्द /‍कपिल धारा कूप निमार्ण कार्य/ लक्ष्‍मन /फुन्‍दू/ नीलकंठीखुर्द | Completed | 100000 | 147262 | 2007-11-25 | 2011-03-10
CHHINDWARA / CHAURAI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1736004077/WC/75454 — नीलकंठी -कूप निर्माण कार्य(नदी मोहल्‍ला) | Completed | 234000 | 280849 | 2009-05-16 | 2011-03-10
CHHINDWARA / CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004077/WC/75513 — नीलकंठी खुर्द/ सामुदायिक कूप निर्माण इंदिरा आवाश कलोनी के पास (नीलकंठी खुर्द) | Completed | 230000 | 273736 | 2010-04-02 | 2013-03-12
CHHINDWARA / CHAURAI | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004077/WC/75690 — नीलकंठीखुर्द/ कपिल धारा कूप निर्माण कार्य (पुष्‍पाबाई/ श्रीचंद मेहरा) | Completed | 154000 | 176764.56 | 2011-03-13 | 2012-03-23
CHHINDWARA / CHAURAI | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1736004077/WC/75691 — नीलकंठीखुर्द/ कपिल धारा कूप निर्माण कार्य (रामदयाल/ झाडू मेहरा) | Completed | 154000 | 171731 | 2011-03-13 | 2012-03-20
CHHINDWARA / CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004077/WC/75692 — नीलकंठीखुर्द कपिल धारा कूप निर्माण कार्य मंगल दुल | Completed | 270000 | 302795.9 | 2011-03-13 | 2015-05-24
CHHINDWARA / CHAURAI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004077/WC/75693 — नीलकंठीखुर्द/ कपिल धारा कूप निर्माण कार्य (राधे/ ह | Completed | 154000 | 147039 | 2011-03-12 | 2015-07-02
CHHINDWARA / CHAURAI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004077/WC/75852 — नीलकंठीखुर्द / केकडा जला.की नहर शेष मिटटी का कार्य ( | Completed | 14000 | 38430 | 2011-05-08 | 2013-03-30
CHHINDWARA / CHAURAI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736004077/WC/77/2 — नीलकण्‍ठी खुर्द/कूप निमाण कार्य सेवकराम/चतरू मेहरा | Completed | 100000 | 144797 | 2008-01-15 | 2010-02-20
CHHINDWARA / CHAURAI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736004077/WC/9993634917 — नीलकंठीखुद्र् सामुदायिक कूप गहरीकरण एवं विस्‍तार क | Completed | 60000 | 9102 | 2013-07-05 | 2015-05-24
CHHINDWARA / CHAURAI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boulder Check / Construction of Boulder Check Dam for Community | Boulder Check/Gully Plug | 1736/WC/9993625810 — KEKADA JALASHAY MUKHYA NAHAR MARMMAT KARYA | Completed | 762000 | 313563 | 2012-05-26 | 2017-09-25