## Work List
Exported on: 2026-10-13 11:53:19
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KHUMKAL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1736005080/DP/22012034619299 — वृक्षारोपण निर्माण कार्य तालाब के ऊपर रान में ग्राम प. खुमकाल | Ongoing | 812728.34 | 136197 | 2024-07-07
CHHINDWARA / JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1736005080/DP/22012034621488 — वृक्षारोपण निर्माण कार्य नानटेकडी ग्राम आराडोंगरी ग्रा .प.खुमकाल | Ongoing | 812728.34 | 275616 | 2024-08-25
CHHINDWARA / JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1736005080/DP/22012034623251 — वृक्षारोपण निर्माण कार्य आंगनवाड़ी भवन के बाजु में ग्राम तालखमरा ग्रा.प.खुमकाल | Ongoing | 812728.34 | 51417 | 2024-09-01
CHHINDWARA / JAMAI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Line Plantation of Forestry Trees for Individual | Plantation | 1736005080/IF/22012034582443 — NAB वृक्षारोपण 05 भगन, सुखलाल, मोहन, प्रताप, सुबदी, ग्राम आराडोंगरी | Ongoing | 296350 | 0 | 2020-09-13
CHHINDWARA / JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736005080/IF/22012035311052 — kapildhara koop Nirman Jhadu pita Vattu Lal | Ongoing | 362806.36 | 0 | 2025-05-05
CHHINDWARA / JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736005080/IF/22012035311225 — Kapildhara Koop Nirman Pratap Pita Samarlal | Ongoing | 362770.23 | 0 | 2025-05-05
CHHINDWARA / JAMAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736005080/IF/22012035311229 — Kapildhara Koop Nirman Samku Pita Maliya | Approved | 362847.96 | 0 | 2025-01-27
CHHINDWARA / JAMAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736005080/IF/IAY/4997642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114974835 | Ongoing | 28500 | 0 | 2025-03-23
CHHINDWARA / JAMAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/22012035085999 — बोल्डर चेक डेम निर्माण कार्य टेकापार धँसाराम के खेत के नीचे | Ongoing | 541653.81 | 0 | 2024-03-13
CHHINDWARA / JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1736005080/WC/22012035133541 — परकोलेशन टेंक निर्माण कार्य दल्लू नाला तालखमरा में | Ongoing | 354438.3 | 0 | 2024-06-30
CHHINDWARA / JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1736005080/WC/22012035198091 — निस्तारी तालाब निर्माण कार्य मकई नाला ग्राम मदनी | Physically Completed | 1495687.37 | 0 | 2024-07-03 | 2026-07-06
CHHINDWARA / JAMAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1736005080/WC/22012035248889 — परकोलेशन टेंक निर्माण कार्य शेखलाल के खेत के साइड मे नाला मे टेकापार वनग्राम ग्राम पंचायत खुमकाल | Ongoing | 199900.24 | 44648.1 | 2025-07-27
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330182 — Boulder Check Dam Matal Bhata Nala pe Gram Aaradongri | Approved | 70698.95 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330196 — Boulder Check Dam Hanuman Mandir ke Peeche Nala pe Gram Madni | Approved | 70698.95 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330234 — Boulder Check Dam Barli Nala Pe Gram Khumkal | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330237 — Boulder Chech Dam Renga Dol Nala Pe Gram Khumkal | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330241 — Boulder Check Dam Sumran Ke Khet ke Pas Nala pe Gram Jatasemar | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330243 — Boulder Chech Dam Maruti Ke Khet Ke Pas Nala Pe Gram Khumkal | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330269 — Boulder Chech Dam Singu Nala Pe Gram Talkhamra | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330275 — Boulder Check Dam Sakur Radi Nala Pe Gram Madni | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736005080/WC/VB/22012035330288 — Staggered Contour Trench Pipal Ghondi me Gram Khumkal | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330312 — Boulder Chech Dam Golu Ke Khet Ke Pass Nala Pe Gram Khumkal | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330667 — Boulder Check Dam Nirman Handpump Nala me Gram Aaradongri | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330668 — Boulder Check Dam Nirman Godakholi Nala Pe Gram Aaradongri | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005080/WC/VB/22012035330671 — Boulder Check Dam Nirman Kariya ke khet ke Pass Nala Pe Gram Tekapar | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736005080/WC/VB/YD/22012035336523 — Staggered Contour Trench Pipalghondi Gram Khumkal | Approved | 807069.9 | 0 | 2026-08-15
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736005080/WC/VB/YD/22012035336601 — Staggered Contour Trench Talabtekdi Gram Talkhamra | Approved | 402828.55 | 0 | 2026-08-15
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736005080/WC/VB/YD/22012035336602 — Staggered Contour Trench Raan Me gram Jatasemar | Approved | 402677.34 | 0 | 2026-08-15
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736005080/WC/VB/YD/22012035336603 — Staggered Contour Contour Trench Ran Bhag 2 Gram Jatasemar | Approved | 596026.59 | 0 | 2026-08-15