## Work List
Exported on: 2026-10-24 07:59:15
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BELGAON MAL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Plantation in Institutions for Community | Plantation | 1736005098/DP/22012034623655 — सामुदायिक ब्लाक प्लानटेशन चान्दन डोडा ग्राम बेलगांव माल | New | 0 | 0 | 2024-06-30
CHHINDWARA / JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1736005098/DP/22012034624666 — samudiya block plantions chandhan doho belgaon mal | Ongoing | 812728.34 | 19085.11 | 2024-07-24
CHHINDWARA / JAMAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1736005098/DP/22012034624668 — samudiyak block plntion chandhna doho 1 belagaon mal | Ongoing | 812728.34 | 16840.14 | 2024-07-24
CHHINDWARA / JAMAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1736005098/IF/22012035355936 — DUG WELL RECHARGE PIT RAMMLSING /DHUNDHA KE KHET ME BELGAON RAYAT | Ongoing | 25899.46 | 0 | 2025-04-19
CHHINDWARA / JAMAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736005098/IF/22012035593702 — Ek Bagiya Maa Ke Name Monora Sakharam Belgaon Mal | Ongoing | 269386.03 | 9356 | 2025-09-06
CHHINDWARA / JAMAI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1736005098/RS/22012034526394 — सेग्रेगेशन शेड निर्माण कार्य बेलगांव मा ल | Ongoing | 625963.81 | 0 | 2021-07-03
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736005098/WC/VB/22012035329562 — Contour Trench Neerman Kary Labor Dari Belgaon Raiyt | Ongoing | 201335.8 | 172276.09 | 2026-08-13
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736005098/WC/VB/22012035329569 — Contour Trench Neerman Kary shankar nadi Belgaon Mal | Ongoing | 200086.59 | 173988.56 | 2026-08-13
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005098/WC/VB/22012035329574 — Boulder Check Dam Neerman Kary Doda Dana Belgaon Mal | Ongoing | 70449.74 | 54428.37 | 2026-08-14
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736005098/WC/VB/22012035329583 — Contour Trench Neerman Kary Jangal Ke Kinare Bomalya | Ongoing | 200086.59 | 159721.82 | 2026-08-14
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005098/WC/VB/22012035329585 — Boulder Check Dam Neerman Kary mocha dham Vale nale Par Bomalya | Ongoing | 70449.74 | 49613.64 | 2026-08-14
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1736005098/WC/VB/22012035329587 — Boulder Check Dam Neerman Kary Dobdi ke Pass Belgaon Raiyt | Ongoing | 70449.74 | 53887.92 | 2026-08-14
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736005098/WC/VB/YD/22012035335946 — Construction of Staggered Trench for Goli Khet ke Pass Belgaon Mal | Ongoing | 399902.39 | 80757.05 | 2026-10-02
CHHINDWARA / JAMAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736005098/WC/VB/YD/22012035336562 — CONTOURE TRENACH NIRMAN DHURVA RASTA BELGOAN RYT | Ongoing | 403944.21 | 15900 | 2026-10-13