## Work List
Exported on: 2026-10-21 14:01:32
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: DAMUA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / PARASIA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of distributary Canal for Community / Construction of Major Distributary Canal for Community | Construction of Canal | 1736006008/DP/22012034434749 — निर्मल नीर कूप निर्माण कार्य जूनाढाना दमुआ | Ongoing | 445000 | 0 | 2019-01-08
CHHINDWARA / PARASIA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736006008/DP/22012034532093 — CTR CONTOUR TRENCH NIRMAN KARYA GOGHAL KHATI JUNADHANA DAMUA | Ongoing | 493174.26 | 0 | 2023-02-14
CHHINDWARA / PARASIA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1736006008/DP/22012034623075 — PLANTATION work ghugalkhati contour trench gram damua gp damua | Ongoing | 922603.19 | 43959.89 | 2024-08-03
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1736006008/IC/22012034889888 — निर्मल नीर निर्माण कार्य भलावी कोलढाना ju दमुआ | New | 0 | 0 | 2025-04-07
CHHINDWARA / PARASIA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1736006008/IF/22012034617116 — मवेशी शेड निर्माण कार्य सुरेश /साबू बरकड़े दमुआ | Ongoing | 101804.91 | 0 | 2020-10-13
CHHINDWARA / PARASIA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736006008/IF/22012035109594 — Khet talab nirman karya shyamlal/Lakhu ke khet me damua | Ongoing | 201236.65 | 0 | 2023-06-21
CHHINDWARA / PARASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736006008/IF/22012035114586 — Koop nirman karya baliya bai /kallu parani damua | Ongoing | 282417.57 | 0 | 2024-06-18
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736006008/IF/22012035326157 — खेत तालाब निर्माण कार्य उडानिया /चिरनलाल दमुआ | Approved | 0 | 0 | 2025-04-07
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736006008/IF/22012035326196 — खेत तालाब निर्माण कार्य झुनलाल /कुरलाल दमुआ | Approved | 0 | 0 | 2025-04-07
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1736006008/IF/22012035408512 — Dug well Recharge pit Baliya bai junadhana damua | Approved | 0 | 0 | 2025-04-14
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1736006008/IF/22012035422005 — Dug well Recharge pit ramesh saryam damua | Approved | 0 | 0 | 2025-04-14
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1736006008/IF/22012035422348 — Dug well Recharge pit Baliya bai junadhana damua | Approved | 0 | 0 | 2025-04-14
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736006008/IF/22012035603922 — Ek bagiya maa ke nam Sunita kakodiya damua | Ongoing | 283386.03 | 10200 | 2025-09-09
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736006008/IF/22012035614374 — Ek Bagiya Maa Ka Naam Gram Panchayat Damua SUKHWATI KARPE | Ongoing | 282386.03 | 9000 | 2025-09-11
CHHINDWARA / PARASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006008/IF/IAY/4645245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136914348 | Ongoing | 28500 | 1000 | 2024-10-24
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006008/IF/IAY/5271044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107023507 | Physically Completed | 28500 | 1000 | 2025-09-09 | 2026-10-04
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006008/IF/IAY/5295952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141686114 | Ongoing | 28500 | 4520 | 2025-04-22
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006008/IF/IAY/5323391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147888612 | Ongoing | 28500 | 2520 | 2025-04-22
CHHINDWARA / PARASIA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1736006008/RC/22012034675069 — सीसी रोड निर्माण कार्य दमुआ | New | 0 | 0 | 2024-01-27
CHHINDWARA / PARASIA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1736006008/WC/22012035249240 — गली प्लग निर्माण कार्य लाधोड वाली नाला दमुआ | Approved | 96348.02 | 0 | 2025-01-27
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006008/WC/22012035282695 — gli plag udansi ke khet ke pass 20 nag damua | Ongoing | 142521.33 | 1100 | 2026-02-26
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006008/WC/22012035328146 — gali plag kodulal ke khet se birbhan ke khet tk | New | 0 | 0 | 2026-01-24
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plug for Community | Boulder Check/Gully Plug | 1736006008/WC/22012035328153 — gali plag kodulal ke khet se birbhan ke khet tk | Approved | 80997.69 | 0 | 2026-01-24
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1736006008/WC/22012035328155 — gly plag badi nadi se bad tak junadhana | Approved | 96348.02 | 0 | 2026-01-24
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1736006008/WC/22012035328158 — gli plag nadi se ramsing ke khet tak | Approved | 96348.02 | 0 | 2026-01-24
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736006008/WC/22012035328169 — Contour Trench komrakol khati junadhana | Approved | 175583.51 | 0 | 2026-01-24
CHHINDWARA / PARASIA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006008/WC/VB/22012035330687 — bouldar chek dem ghoghra dhana jamun jhil damua | New | 0 | 0 | 2026-07-07
CHHINDWARA / PARASIA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006008/WC/VB/22012035330719 — bouldar chek dem ghoghra dhana jamun jhil damua | Deleted | 0 | 0 | 2026-07-07
CHHINDWARA / PARASIA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006008/WC/VB/22012035330726 — bouldar chek dem ghoghra dhana jamun jhil damua | Deleted | 0 | 0 | 2026-07-14
CHHINDWARA / PARASIA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736006008/WC/VB/22012035331500 — bouldar chek dem ghoghra dhana jamun jhil damua | Deleted | 0 | 0 | 2026-07-07
CHHINDWARA / PARASIA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1736006008/WC/VB/YD/22012035335336 — Constr of Stone boulder Gully Plugs for Comm sahitram ke khet ke pas gp damua | Approved | 149640.11 | 0 | 2026-04-14
CHHINDWARA / PARASIA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1736/RC/22012034680453 — Sudoor Sadak with Puliya Damua to Sarekhadhana L 1.30Km Gram Danua | Ongoing | 3888000 | 68380 | 2024-06-18