## Work List
Exported on: 2026-10-23 18:52:44
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: CHABADIKALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / PARASIA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1736006063/AV/22012034542163 — गौशाला निर्माण कार्य (दूध डेरी के पास) छाबड़ी खुर्द | Ongoing | 3804449.17 | 0 | 2021-02-05
CHHINDWARA / PARASIA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1736006063/AV/22012034577981 — डायनिंग टेबल अरेंजमेंट शासकीय प्राथमिक शाला छाबड़ी कला | Ongoing | 24125.52 | 0 | 2021-09-30
CHHINDWARA / PARASIA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1736006063/AV/22012034577988 — डायनिंग टेबल अरेंजमेंट शासकीय प्राथमिक शाला छाबड़ी खुर्द | Ongoing | 31450.01 | 0 | 2021-09-30
CHHINDWARA / PARASIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1736006063/DP/22012034434700 — निर्मल नीर निर्माण कार्य (मोक्षधाम के पास छाबडी कला) | Ongoing | 445000 | 0 | 2019-02-22
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1736006063/IF/22012035385426 — Recharge Structure Kapil Dhara Jagdish/Gendlal Pawar Chhabdi khurd | Ongoing | 27899.46 | 0 | 2025-04-29
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1736006063/IF/22012035386673 — Recharge Structure Kapil Dhara Koop Baldev/kaliram Pawar Chhabdi kala | Ongoing | 27899.46 | 0 | 2025-04-29
CHHINDWARA / PARASIA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1736006063/IF/22012035401678 — JGSA Recharge Structure Kapil Dhara Kraparam/Daya Pawar Chhabdi kala | Ongoing | 27899.46 | 0 | 2025-04-30
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736006063/IF/22012035407363 — JSGA Khet Talab nirman karya Shravan Nagwanshi ke khet me Chhabdi khurd | Approved | 399942.92 | 0 | 2025-04-14
CHHINDWARA / PARASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/4604526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123764768 | Completed | 28500 | 0 | 2024-09-24 | 2026-10-08
CHHINDWARA / PARASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/4668122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149109355 | Completed | 28500 | 0 | 2024-09-24 | 2026-10-08
CHHINDWARA / PARASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/4768836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123767248 | Ongoing | 28500 | 0 | 2024-11-08
CHHINDWARA / PARASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/4907987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120604763 | Completed | 28500 | 0 | 2025-02-26 | 2026-10-08
CHHINDWARA / PARASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/4914816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149109239 | Completed | 28500 | 0 | 2025-02-23 | 2026-10-08
CHHINDWARA / PARASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/4959819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124086845 | Ongoing | 28500 | 0 | 2025-03-20
CHHINDWARA / PARASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/4987241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101012936 | Ongoing | 28500 | 0 | 2025-03-20
CHHINDWARA / PARASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/4987747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100842883 | Completed | 28500 | 0 | 2025-03-20 | 2026-10-08
CHHINDWARA / PARASIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5103724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149108599 | Ongoing | 28500 | 0 | 2025-03-20
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5507000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149108727 | Physically Completed | 28500 | 0 | 2025-04-29 | 2026-10-18
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5507001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149108974 | Completed | 28500 | 0 | 2025-04-29 | 2026-10-08
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5507002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149109216 | Completed | 28500 | 0 | 2025-04-29 | 2026-10-08
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5508855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124087412 | Completed | 28500 | 0 | 2025-04-29 | 2026-10-08
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5735834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101012847 | Ongoing | 28500 | 0 | 2025-08-30
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5735835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101012879 | Ongoing | 28500 | 0 | 2025-08-26
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5735960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120551535 | Ongoing | 28500 | 0 | 2026-02-24
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5737535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100858610 | Ongoing | 28500 | 0 | 2026-02-07
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5737813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123766717 | Ongoing | 28500 | 0 | 2025-08-30
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5737897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149108767 | Physically Completed | 28500 | 1200 | 2025-09-06 | 2026-10-11
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5738269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123765263 | Completed | 28500 | 3200 | 2025-08-30 | 2026-10-08
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5739047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121613935 | Ongoing | 28500 | 0 | 2025-08-30
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5739584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101137529 | Completed | 28500 | 0 | 2026-02-07 | 2026-10-08
CHHINDWARA / PARASIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/5792540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123766259 | Completed | 24795 | 0 | 2026-03-17 | 2026-09-29
CHHINDWARA / PARASIA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1736006063/IF/IAY/969046 — Construction of IAY House -IAY REG. NO. MP3526429 | Approved | 28500 | 0 | 2021-12-15
CHHINDWARA / PARASIA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1736006063/RC/22012034853580 — सी सी रोड महेश के घर से पवार के घर तक | New | 0 | 0 | 2026-02-09
CHHINDWARA / PARASIA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1736006063/RS/VB/YD/22012035140196 — Constr of NADEP Compost structure for 1 | Approved | 23001.75 | 0 | 2026-08-16