## Work List
Exported on: 2026-10-02 08:47:01
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MUJABRAMAL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / MOHKHED | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1736007007/DP/22012034434159 — NIRMAL NEER KUP MATAKOL TALAB KE PASS, Mujawar mal | Ongoing | 445000 | 0 | 2018-12-24
CHHINDWARA / MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1736007007/DP/22012034621823 — Plantation at Neem Tekari jaydidhana Mujawarmal | Ongoing | 812728.34 | 50344 | 2024-07-16
CHHINDWARA / MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1736007007/DP/22012034621824 — Plantation at Jamtara Tekari Jaydidhana Mujawarmal | Ongoing | 564685.45 | 16748 | 2024-07-16
CHHINDWARA / MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736007007/IF/22012035097146 — Khet Talab Nirman kary Manaklal Ivanati Mujawarmal | Ongoing | 223820.73 | 0 | 2023-10-06
CHHINDWARA / MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1736007007/IF/22012035300617 — Khet Talab Nirman Kary Bhudkum Madan | Approved | 422356.09 | 0 | 2025-01-24
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Bio-drainage Plantation for Individual | Plantation | 1736007007/IF/22012035608055 — Ek Bagiya Maa Ke Nam Saroj Marskole GP Mujawar Mal | Ongoing | 266577.25 | 855 | 2025-11-07
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/2670507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4130916 | Ongoing | 28500 | 0 | 2023-02-17
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/2688395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4967649 | Ongoing | 28500 | 0 | 2023-02-17
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/3228837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1391864 | Ongoing | 28500 | 0 | 2023-01-24
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/4619361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126927212 | Ongoing | 28500 | 0 | 2025-04-03
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/5587800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126687850 | Approved | 28500 | 0 | 2025-04-16
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/5708498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143415513 | Ongoing | 28500 | 11781 | 2026-02-12
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/5708548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126825158 | Approved | 28500 | 0 | 2025-06-17
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/5708580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142400607 | Ongoing | 28500 | 0 | 2025-12-13
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/5709089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143168400 | Ongoing | 28500 | 0 | 2025-12-09
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/5772051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126025053 | Ongoing | 28500 | 0 | 2026-03-13
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/5774467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126844463 | Ongoing | 28500 | 0 | 2026-02-12
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/5884594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143415544 | Approved | 28500 | 0 | 2025-06-17
CHHINDWARA / MOHKHED | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736007007/IF/IAY/5884853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143482863 | Ongoing | 28500 | 3654 | 2026-09-10
CHHINDWARA / MOHKHED | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation-Horticulture - Community / Canal Line Plantation for Community | Plantation | 1736007007/WC/22012034988192 — Plantation work at Amrat Sarover bhudkum Mujawrmal | Ongoing | 215694.17 | 7260 | 2022-09-04
CHHINDWARA / MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007007/WC/22012035171295 — कन्टूरट्रेंच निर्माण कार्य | New | 0 | 0 | 2023-10-02
CHHINDWARA / MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007007/WC/22012035212160 — BCD Nirman Kary Mangal Ke khet Ke Pass Jaydidhana Mujawarmal | Approved | 434186.51 | 0 | 2024-04-14
CHHINDWARA / MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1736007007/WC/22012035250880 — Contur trench at Nirman Kary Bada Talab Ke Pass | Approved | 199022.31 | 0 | 2025-01-24
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1736007007/WC/22012035271920 — Dugwell Recharge Pit Lohardhana Neermal Neer | Approved | 25899.46 | 0 | 2025-04-14
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1736007007/WC/22012035271927 — Dugwell Recharge Pit Ward No 12 Neermal Neer | Approved | 25899.46 | 0 | 2025-04-14
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1736007007/WC/22012035271940 — Dugwell Recharge Pit Jaydai Ward No 3 | Approved | 25899.46 | 0 | 2025-04-14
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1736007007/WC/22012035288184 — Dugwell Recharge Pit Nirman लोहारढाना | Ongoing | 25899.46 | 0 | 2025-05-11
CHHINDWARA / MOHKHED | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007007/WC/VB/22012035329733 — Boder Check dem Nirman Kary Jaydei | Deleted | 0 | 0 | 2026-04-14
CHHINDWARA / MOHKHED | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007007/WC/VB/22012035329740 — Boder Check dem Nirman Kary Jaydei | Approved | 0 | 0 | 2026-04-14