## Work List
Exported on: 2026-09-28 23:42:28
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PAUNAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1736007011/DP/22012034615090 — CNG Vasudha Vandan Amrit Vatika Tigai Road Talab Ke Pass Pounar | Ongoing | 988687.99 | 42655 | 2024-08-24
CHHINDWARA / MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007011/DP/22012034622754 — Plantation at Gohalari Pahadi contur trnch Ponar 625 | Ongoing | 853685.12 | 58389 | 2024-08-10
CHHINDWARA / MOHKHED | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1736007011/DP/VB/22012034630710 — Plantation School Parisar Pounar | Approved | 0 | 0 | 2026-06-05
CHHINDWARA / MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035085796 — Kapil Dhara Kup Nierman Nanakram / Chaitram Pawar | Ongoing | 259820.29 | 0 | 2023-05-30
CHHINDWARA / MOHKHED | 2024-2025 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage of chaur/waterlogged Land for Indiv / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1736007011/IF/22012035222518 — कपिलधारा कूप निमाण प्रवीण | Ongoing | 272950.76 | 0 | 2025-03-01
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035320226 — Kapildhara Kup Nirman Umesh / Heera Bhojkar | Ongoing | 283201.39 | 0 | 2025-05-05
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035323159 — Kapildhara Kup Nirman Somavati / Budhhman Chouriya | Ongoing | 288266.14 | 0 | 2025-05-24
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007011/IF/22012035369134 — Dugwell Recharge Pit Kapildhara Yashpal Pawar | Approved | 25899.46 | 0 | 2025-04-14
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/22012035369279 — Dugwell Recharge Pit kapildhara Bholaram Pawar | Approved | 25899.46 | 0 | 2025-04-14
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007011/IF/22012035369301 — Dugwell Recharge Pit Kapildhara Jagannath Pawar | Approved | 25899.46 | 0 | 2025-04-14
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736007011/IF/22012035584625 — Ek Bagiya Maa Ke Sushila Pawar MP36007011001 180 | Ongoing | 266577.25 | 0 | 2025-09-06
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736007011/IF/22012035584662 — Ek Bagiya Maa Ke Chhaya Pawar MP36007011001 119A | Approved | 266577.25 | 0 | 2025-08-01
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5365123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127941447 | Ongoing | 28500 | 3393 | 2025-07-05
CHHINDWARA / MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5814805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128617613 | Approved | 28500 | 0 | 2025-02-14
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5936213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146393078 | Completed | 28500 | 12789 | 2026-03-12 | 2026-09-18
CHHINDWARA / MOHKHED | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5936214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146396126 | Ongoing | 28500 | 0 | 2026-05-30
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007011/IF/IAY/5941233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145067197 | Ongoing | 28500 | 3654 | 2026-03-12
CHHINDWARA / MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007011/WC/22012035170760 — कन्टूरट्रेच निर्माण कार्य | New | 0 | 0 | 2023-10-02
CHHINDWARA / MOHKHED | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007011/WC/VB/22012035329941 — Gully Plug Nirman Kary Gohlari Pahadi Pounar | New | 0 | 0 | 2026-06-05