## Work List
Exported on: 2026-09-14 16:44:15
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: RAJADHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1736007045/AV/22012034582685 — daynig tebal ghs rajada | Closed | 0 | 0 | 2021-04-14
CHHINDWARA / MOHKHED | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1736007045/AV/22012034582687 — daynig tebal ghs rajada | Closed | 95914.9 | 0 | 2021-04-14
CHHINDWARA / MOHKHED | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1736007045/AV/22012034636209 — Dobhri Nala Pr Puliya Nirman Rajada | Physically Completed | 1467188.01 | 1434879.6 | 2023-06-16 | 2026-06-03
CHHINDWARA / MOHKHED | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007045/DP/22012034233222 — Plantation- खेल मैदान परिसर, ग्रा.पं. रजाडा | Completed | 257000 | 148159 | 2016-07-29 | 2020-07-02
CHHINDWARA / MOHKHED | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007045/DP/22012034237673 — Plantetion shanti dham | Deleted | 0 | 0 | 2017-01-26
CHHINDWARA / MOHKHED | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1736007045/DP/22012034423867 — Plantation Road Line- RAJADA SE KAMTHI Road | Completed | 342000 | 113544 | 2018-07-27 | 2021-06-15
CHHINDWARA / MOHKHED | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1736007045/DP/22012034423872 — Plantation Road Line- RAJADA SE CHABDI ROD | Physically Completed | 342000 | 101387 | 2018-07-27 | 2021-06-26
CHHINDWARA / MOHKHED | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007045/DP/22012034447274 — CONTOUR TRENCH PATHAR GHAT | Completed | 1044114.83 | 918530 | 2019-07-05 | 2021-01-10
CHHINDWARA / MOHKHED | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007045/DP/22012034521332 — CONTOUR TRENCH CHHABDI ROAD PATHAR | Completed | 227865.4 | 160360 | 2021-01-08 | 2022-07-11
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007045/DP/22012034530066 — CONTOUR TRENCH NAGJHIRI | Completed | 399712.05 | 342043 | 2022-02-18 | 2024-08-22
CHHINDWARA / MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1736007045/DP/22012034592209 — Vashudha vatika talab ke pass panchayte ke pichhe Rajada | Completed | 55847.4 | 20253 | 2023-08-25 | 2026-03-05
CHHINDWARA / MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007045/DP/22012034622884 — Plantation at Pathar Ghat 625 Rajada | Ongoing | 841684.76 | 76051 | 2024-08-23
CHHINDWARA / MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007045/DP/22012034622891 — Plantation at Chhabdi Road Pthar pahadi 200 Rajada | Ongoing | 399685.9 | 34352 | 2024-08-16
CHHINDWARA / MOHKHED | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1736007045/DP/22012034622894 — Plantation at Nagjhiri Pahadi Rajada 200 | Ongoing | 389685.93 | 15034 | 2024-09-13
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034309857 — वर्मी कम्पोस्ट बलदेव / ग़ुलाब चौधरी | Completed | 17000 | 16002.9 | 2016-12-30 | 2017-01-04
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034315398 — वर्मी कम्पोस्ट मनोहर / मंगनलाल | Completed | 17000 | 17003.39 | 2017-02-10 | 2017-02-15
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034315434 — Nadep taka Radheshyam choudhary | Deleted | 0 | 0 | 2017-01-26
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034315435 — Nadep taka Maniram Gadre | Deleted | 0 | 0 | 2017-01-26
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034316554 — नाडेप निर्माण फकीरा / फत्तु चौधरी | Completed | 11000 | 10963.5 | 2017-03-03 | 2017-03-08
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034316585 — वर्मी कम्पोट निर्माण सेवाराम / खुशी चौधरी | Completed | 17000 | 16002.9 | 2017-03-03 | 2017-03-08
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034316591 — नाडेप निर्माण राखडया / नारु शेरके | Completed | 11000 | 10963.5 | 2017-02-03 | 2017-02-08
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034325530 — सेवाराम / झिंगु घागरे नाडेप पिट निर्माण | Completed | 11000 | 10927.5 | 2017-03-10 | 2017-03-15
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034325544 — वर्मी कम्पोसट पिट निर्माण उदेराम / नागोराव चौधरी | Completed | 17000 | 16956.9 | 2017-03-10 | 2017-03-15
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034326300 — नाडेप पिट निर्मान जानू / टिकारम गाडरे | Completed | 11000 | 10927.5 | 2017-03-10 | 2017-03-15
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034326302 — नाडेप पिट निर्मान चम्पा / सम्पत गाडरे | Completed | 11000 | 10943.85 | 2017-03-17 | 2017-03-22
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1736007045/IF/22012034326307 — वर्मी कम्पोस्टिंग निर्मान अशोक / फकीरा नागलेकर | Completed | 17000 | 16979.39 | 2017-03-17 | 2017-03-22
CHHINDWARA / MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007045/IF/22012034339820 — Plantation PCP- Middle School Campus Rajada | Completed | 335000 | 182821 | 2017-05-19 | 2021-06-15
CHHINDWARA / MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007045/IF/22012034339832 — Plantation PCP - Shantidham at Rajada | Completed | 335000 | 151666 | 2017-05-19 | 2021-06-15
CHHINDWARA / MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007045/IF/22012034385193 — Kapildhara with Farm Pond | Deleted | 0 | 0 | 2017-11-01
CHHINDWARA / MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007045/IF/22012034385196 — Kapildhara with Farm Pond | Deleted | 0 | 0 | 2017-11-01
CHHINDWARA / MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1736007045/IF/22012034385197 — Plantation RCP Rajda | Deleted | 0 | 0 | 2017-11-01
CHHINDWARA / MOHKHED | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007045/IF/22012034457155 — Med Bandhan (Boldar) | Deleted | 0 | 0 | 2018-10-02
CHHINDWARA / MOHKHED | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007045/IF/22012034472371 — Med Bandhan Nirman (Bolder)Karya Champa /Sampat Gadre Rajada | Completed | 42000 | 33966 | 2019-03-10 | 2019-07-17
CHHINDWARA / MOHKHED | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone contour Bund for Individuals / Construction of Stone contour Bund for Individuals | Construction of Bund | 1736007045/IF/22012034502973 — boldar medbandhan duwarka gadre | Deleted | 0 | 0 | 2019-08-15
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034572731 — Neno Archid Falodhyan Nanhi / Shivram Gadre | Completed | 58286 | 46205 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034572740 — Neno Archid Falodhyan Jaydev / Gulab Choudhary | Completed | 58286 | 46205 | 2020-07-17 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034572741 — Neno Archid Falodhyan Uderam / Nagorav Choudhary | Completed | 58286 | 46398 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034572743 — Neno Archid Falodhyan Manirami / adkya Gadre | Completed | 58286 | 46398 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034573118 — Neno Archid Falodhyan Sevaram / Jhingu Ghagre | Completed | 58286 | 45997 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034573123 — Neno Archid Falodhyan Ashok / Fulchand Bhondekar | Completed | 58286 | 45282 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034573126 — Neno Archid Falodhyan Tarabai / Balakram Choudhary | Completed | 58286 | 44287 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034573138 — Neno Archid Falodhyan Nosa / Faggu Choudhary | Completed | 58286 | 46395 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034573141 — Neno Archid Falodhyan Ganesh / Chaita Ghagre | Completed | 58286 | 43536 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034573143 — Neno Archid Falodhyan Kamla / Gulab Choudhary | Completed | 58286 | 44127 | 2020-07-17 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034573146 — Neno Archid Falodhyan Chironji / Badya Choudhary | Completed | 58286 | 43976 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034579446 — Neno Archid Falidhyan sampat / punu choudhary | Completed | 58286 | 46395 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034579463 — Neno Archid Falidhyan Keshorao / Punu Choudhary | Completed | 58286 | 45400 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034579464 — Neno Archid Falidhyan Ithova / Nanho Ghagare | Completed | 58286 | 44854 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034579465 — Neno Archid Falidhyan Manduru / Nanhu Choudhary | Completed | 58286 | 41776 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034579466 — Neno Archid Falidhyan Radheshyam / Nagorao Choudhary | Completed | 58286 | 42143 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034579467 — Neno Archid Falidhyan Sahabrao / Kali Choudhary | Completed | 58286 | 42994 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034579468 — Neno Archid Falidhyan Shankar / Bhaglal sherake | Completed | 58286 | 44914 | 2020-07-10 | 2022-10-31
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012034585153 — Neno Archid Falodhyan Urmila/sewaram choudhary | Completed | 58286 | 46398 | 2020-07-24 | 2022-10-31
CHHINDWARA / MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007045/IF/22012034939052 — kpil dharakup | Closed | 0 | 0 | 2022-01-24
CHHINDWARA / MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736007045/IF/22012034939792 — medbandhan | Closed | 0 | 0 | 2022-01-24
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035031216 — Naino Archid Falodhayan Naresh / Phakira Nagalekar | Completed | 61085 | 45228.04 | 2022-11-11 | 2026-01-15
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035031568 — Naino Archid Falodhayan Champa / Lakhan Gadre | Physically Completed | 61085 | 49566.04 | 2022-11-11 | 2026-06-26
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035031580 — Naino Archid Falodhayan Suresh / Kapurchand bondekar | Physically Completed | 61085 | 49561.07 | 2022-11-11 | 2026-06-26
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035031921 — Naino Archid Falodhayan kesorao / Prasram Choudhary | Completed | 61085 | 44586.04 | 2022-11-11 | 2026-01-15
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035031977 — Naino Archid Falodhayan Srasvati / Salikram Gadre | Completed | 61085 | 45870.04 | 2022-11-11 | 2026-01-15
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035032022 — Naino Archid Falodhayan Prahlad / Dshrath Kalbhut | Completed | 61085 | 45927.07 | 2022-11-11 | 2026-01-15
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035032231 — Naino Archid Falodhayan Shesram / Maniram Bhade | Completed | 61085 | 44544.04 | 2022-11-11 | 2026-01-15
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035032242 — Naino Archid Falodhayan Dilip / Jayram Gadre | Physically Completed | 61085 | 49696.04 | 2022-11-11 | 2026-06-26
CHHINDWARA / MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035051895 — Naino Archid Falodhayan Janki /Ishnaji Choudhary | Physically Completed | 61085 | 48715 | 2023-09-29 | 2026-06-26
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035051933 — Naino Archid Falodhayan Yashwant / PunuChoudhary | Physically Completed | 61085 | 49393.04 | 2023-03-13 | 2026-06-26
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035051952 — Naino Archid Falodhayan Kachra / JayramChoudhary | Physically Completed | 61085 | 49441.07 | 2023-03-13 | 2026-06-26
CHHINDWARA / MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035052249 — Naino Archid Falodhayan Rukhkho / Kashiram Ghagre | Completed | 61085 | 45849.04 | 2023-06-02 | 2026-01-15
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035052783 — Naino Archid Falodhayan manni / Rmesh Choudhary | Physically Completed | 61085 | 49584.07 | 2023-03-13 | 2026-06-26
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035058819 — Naino Archid Falodhayan Lalita /Lalaji Gadre | Completed | 61085 | 47313.07 | 2023-03-13 | 2026-01-15
CHHINDWARA / MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035058832 — Naino Archid Falodhayan Remesh /Tikaram Gadrer | Physically Completed | 61085 | 49590.07 | 2023-05-19 | 2026-06-26
CHHINDWARA / MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035058836 — Naino Archid Falodhayan Lanka /Mitharam Ghagre | Physically Completed | 61085 | 49571.07 | 2023-06-09 | 2026-06-26
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035059455 — Naino Archid Falodhayan Chmeli / Ramdash Gadre | Physically Completed | 61085 | 49441.07 | 2023-03-13 | 2026-06-26
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035059497 — Naino Archid Falodhayan Kumlal /Gusaei Gadre | Physically Completed | 61085 | 49369.07 | 2023-03-13 | 2026-06-26
CHHINDWARA / MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035059724 — Naino Archid Falodhayan Gnesh / Keshorao Choudhary | Physically Completed | 61085 | 49651.07 | 2023-06-02 | 2026-06-26
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1736007045/IF/22012035059739 — Naino Archid Falodhayan Subhadra /Sirpat Choudhary | Physically Completed | 61085 | 49416.04 | 2023-03-13 | 2026-06-26
CHHINDWARA / MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007045/IF/22012035092014 — Khet Talab Nirman kary Champa Gadre Rajada | Closed | 90820.39 | 0 | 2023-04-14
CHHINDWARA / MOHKHED | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736007045/IF/22012035097403 — Khet Talab Nirman kary Dilip Jairam Gadre Rajada | Closed | 0 | 0 | 2023-04-14
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736007045/IF/22012035423010 — DUGWELL RECHARGE JAYDEV CHOUDHARY KE KUP PAR | New | 0 | 0 | 2025-04-14
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736007045/IF/22012035423073 — DUGWELL RECHARGE JAYDEV CHOUDHARY KE KUP PAR | New | 0 | 0 | 2025-04-14
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736007045/IF/22012035423178 — DUGWELL RECHARGE JAYDEV CHOUDHARY KE KUP PAR | New | 0 | 0 | 2025-04-14
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736007045/IF/22012035431718 — DUGWELL RECHARGE JAYDEV CHOUDHARY KE KUP PAR | New | 0 | 0 | 2025-04-14
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736007045/IF/22012035431959 — DUGWELL RECHARGE JAYDEV CHOUDHARY KE KUP PAR | Physically Completed | 25899.46 | 25432.09 | 2025-05-05 | 2026-04-11
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736007045/IF/22012035612422 — Ek Bagiya Maa Ke Naam Sreeta Choudhary | Ongoing | 266577.25 | 106979.22 | 2025-09-09
CHHINDWARA / MOHKHED | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1736007045/IF/9993717192 — Cattle Shed - Uderam Nagorao | Deleted | 0 | 0 | 2015-10-30
CHHINDWARA / MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Peripheral Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1736007045/IF/9993748816 — Med Bandhan - Baldev Gulab Chourdhary | Deleted | 132000 | 0 | 2016-06-24
CHHINDWARA / MOHKHED | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/1006077 — Construction of IAY House -IAY REG. NO. MP1369292 | Completed | 16340 | 16530 | 2018-04-13 | 2018-10-06
CHHINDWARA / MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/1098990 — Construction of IAY House -IAY REG. NO. MP3807947 | Completed | 16340 | 15480 | 2017-05-26 | 2017-12-19
CHHINDWARA / MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/1100289 — Construction of IAY House -IAY REG. NO. MP3973419 | Completed | 16340 | 15308 | 2017-08-18 | 2017-12-19
CHHINDWARA / MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/1153961 — Construction of IAY House -IAY REG. NO. MP2700558 | Completed | 16340 | 15136 | 2017-07-21 | 2017-12-19
CHHINDWARA / MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/121322 — Construction of IAY House -IAY REG. NO. MP-36-007-045-001/865 | Completed | 15105 | 14250 | 2016-07-22 | 2016-09-15
CHHINDWARA / MOHKHED | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/2440313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5667872 | Completed | 18050 | 18050 | 2020-05-08 | 2021-01-03
CHHINDWARA / MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/2667038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4117678 | Completed | 18050 | 17262 | 2021-04-23 | 2021-11-23
CHHINDWARA / MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/2671411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4950175 | Completed | 18050 | 17226 | 2021-04-23 | 2021-11-23
CHHINDWARA / MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/2710079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5706535 | Completed | 18050 | 17226 | 2021-04-23 | 2021-11-23
CHHINDWARA / MOHKHED | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/2710289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5555183 | Completed | 18050 | 17226 | 2021-04-23 | 2021-11-23
CHHINDWARA / MOHKHED | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/350544 — Construction of IAY House -IAY REG. NO. MP1127915 | Completed | 15865 | 15450 | 2017-03-03 | 2017-07-15
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/3839308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116879169 | Completed | 19380 | 18360 | 2022-07-01 | 2022-09-26
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/3894451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147853163 | Completed | 19380 | 18360 | 2022-07-15 | 2022-09-26
CHHINDWARA / MOHKHED | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/3908258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150074232 | Completed | 19380 | 18156 | 2022-07-01 | 2022-11-07
CHHINDWARA / MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/4651462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146046288 | Completed | 24795 | 24687 | 2024-11-08 | 2026-02-23
CHHINDWARA / MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/4651535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146065043 | Completed | 23085 | 23085 | 2024-11-08 | 2025-12-12
CHHINDWARA / MOHKHED | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/4657496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147867996 | Completed | 24795 | 23085 | 2024-11-08 | 2025-05-04
CHHINDWARA / MOHKHED | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5439981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146852790 | Ongoing | 28500 | 24795 | 2026-05-29
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5440966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118273236 | Completed | 24795 | 24795 | 2025-04-25 | 2025-12-12
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5441473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147852687 | Completed | 24795 | 24795 | 2025-04-25 | 2025-12-12
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5441662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148323278 | Completed | 24795 | 18792 | 2025-05-30 | 2025-12-12
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5442256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148312897 | Completed | 24795 | 24795 | 2026-03-06 | 2026-05-12
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5443524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150745235 | Completed | 24795 | 24795 | 2025-06-27 | 2026-01-06
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5444455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150073642 | Completed | 24795 | 24795 | 2025-05-23 | 2025-12-12
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5444456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150075418 | Completed | 24795 | 24795 | 2025-10-24 | 2026-02-23
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5444457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150075549 | Completed | 24795 | 24795 | 2025-06-06 | 2025-12-12
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5444491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118135343 | Completed | 24795 | 24795 | 2025-05-02 | 2025-12-12
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5449652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147187164 | Completed | 24795 | 24795 | 2025-05-23 | 2026-01-06
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5449695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146618994 | Completed | 24795 | 24795 | 2025-04-25 | 2025-12-12
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5450164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118276797 | Completed | 24795 | 24795 | 2025-07-25 | 2026-01-28
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5450588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148317184 | Completed | 24795 | 24795 | 2025-05-09 | 2025-12-12
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5450851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148305353 | Completed | 24795 | 24795 | 2025-08-15 | 2026-01-06
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5659540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127879750 | Completed | 24795 | 24795 | 2025-09-05 | 2026-01-06
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5921228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144234860 | Approved | 28500 | 0 | 2026-02-11
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5936161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150746582 | Approved | 28500 | 0 | 2026-01-29
CHHINDWARA / MOHKHED | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5936163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150746933 | Ongoing | 28500 | 24795 | 2026-01-29
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5936164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150747287 | Ongoing | 28500 | 20097 | 2026-03-13
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5936361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128032971 | Ongoing | 28500 | 24795 | 2026-03-13
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5936626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118135863 | Completed | 24795 | 24795 | 2026-03-13 | 2026-06-04
CHHINDWARA / MOHKHED | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5937017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150728567 | Ongoing | 28500 | 18270 | 2026-01-29
CHHINDWARA / MOHKHED | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5937052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147184344 | Ongoing | 28500 | 18270 | 2026-01-29
CHHINDWARA / MOHKHED | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5937590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127974839 | Physically Completed | 28500 | 24795 | 2026-05-08 | 2026-08-30
CHHINDWARA / MOHKHED | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5937894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150748725 | Ongoing | 28500 | 18009 | 2026-06-12
CHHINDWARA / MOHKHED | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5938891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119081850 | Ongoing | 28500 | 24795 | 2026-05-08
CHHINDWARA / MOHKHED | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5941466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146949222 | Ongoing | 28500 | 18270 | 2026-01-29
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5942427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147852932 | Completed | 24795 | 24795 | 2026-03-13 | 2026-06-04
CHHINDWARA / MOHKHED | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/5943054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128033529 | Approved | 28500 | 0 | 2026-01-29
CHHINDWARA / MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/633216 — Construction of IAY House -IAY REG. NO. MP1136324 | Completed | 15865 | 15480 | 2017-05-12 | 2017-12-19
CHHINDWARA / MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/695651 — Construction of IAY House -IAY REG. NO. MP1369295 | Completed | 15865 | 15480 | 2017-08-25 | 2017-12-19
CHHINDWARA / MOHKHED | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736007045/IF/IAY/734327 — Construction of IAY House -IAY REG. NO. MP2087684 | Completed | 15865 | 15480 | 2017-05-19 | 2017-12-19
CHHINDWARA / MOHKHED | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007045/LD/1004 — मेंढ बधान कार्य हिंमांशु / प्रेमचन्‍द्र ग्राम पंचायत रजाड़ा | Deleted | 10000 | 0 | 2009-04-01
CHHINDWARA / MOHKHED | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007045/LD/1032 — मेढ बंधान भूमि सुधार हिमांशु /प्रेमचंद | Deleted | 0 | 0 | 2010-01-26
CHHINDWARA / MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007045/LD/1406 — खेल मैदान राजाडा | Completed | 499000 | 484744.73 | 2012-01-22 | 2014-03-07
CHHINDWARA / MOHKHED | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007045/LD/22012034293207 — shanti dham nirman gram panchayt Rajada | Deleted | 0 | 0 | 2016-05-01
CHHINDWARA / MOHKHED | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007045/LD/22012034293210 — SANTI DHAM NIRMAN GP RAJADA | Completed | 503000 | 299944.07 | 2016-11-18 | 2017-03-22
CHHINDWARA / MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1736007045/LD/960 — मेड बंधान कार्य हिमांशु / प्रेमचंद्र | Deleted | 12000 | 0 | 2008-03-05
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007045/RC/22012034185259 — second class road (rajada to chhabde II part) | Completed | 498500 | 336220.7 | 2013-09-27 | 2014-06-13
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007045/RC/22012034201365 — ि‍द्वतीय श्रेणी सडक ि‍नर्माण रजाडा से छाबडी भाग-3 | Completed | 499000 | 303830.07 | 2014-01-31 | 2014-07-02
CHHINDWARA / MOHKHED | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007045/RC/22012034219382 — SUDUR GRAM SADAK YOJNA FROM RAMCHARAN HOUSE TO MORANDHANA ROAD | Completed | 888000 | 396221.42 | 2014-05-30 | 2018-08-12
CHHINDWARA / MOHKHED | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007045/RC/22012034285037 — Sudur Gram Sadak gram sadak | Completed | 766000 | 770690.42 | 2015-09-18 | 2018-08-12
CHHINDWARA / MOHKHED | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007045/RC/22012034302596 — Sudor Sadak Yojna- Rajada se Bhortalai | Deleted | 0 | 0 | 2015-10-30
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007045/RC/22012034322456 — suduer sadk | Deleted | 0 | 0 | 2017-01-26
CHHINDWARA / MOHKHED | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007045/RC/22012034331560 — CC ROAD NIRMAN PANI TANKI SE MAHESH NAGLE KE MAKAN TAK | Completed | 35000 | 12360 | 2017-03-17 | 2018-07-12
CHHINDWARA / MOHKHED | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007045/RC/22012034360353 — सी सी रोड & पक्की नाली निर्माण सखाराम देशमुख के मकान से अर्जुन देशमुख के मकान तक पटेल मोहल्ला | Completed | 96600 | 39279 | 2017-09-15 | 2018-07-12
CHHINDWARA / MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1736007045/RC/22012034552241 — MUDYAKHEDA DHNA SE RAJADA MUKHY MARG TAK | Closed | 0 | 0 | 2020-10-02
CHHINDWARA / MOHKHED | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007045/RC/22012034683721 — CCROAD NIRMAN KARY MAIN ROAD RAJADA CNNABDI MUKHY MARG SE MS SALA PRISAR TAK | Completed | 46445 | 38549 | 2024-03-16 | 2025-05-04
CHHINDWARA / MOHKHED | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007045/RC/9079 — द्वितीय श्रेणी सड़क निर्माण कार्य रजाड़ा से कामठी ग्राम पंचायत रजाड़ा | Completed | 492000 | 597189 | 2010-06-11 | 2011-04-27
CHHINDWARA / MOHKHED | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007045/RC/9102 — दितीय सडक निर्माण कार्य रजाडा से कामठी भाग-2 | Completed | 492000 | 564780 | 2011-01-14 | 2011-12-10
CHHINDWARA / MOHKHED | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007045/RC/9159 — दितीय सडक निर्माण कार्य कामठी रोड से नागझिरी ढाना | Completed | 499000 | 441956 | 2011-04-08 | 2011-12-10
CHHINDWARA / MOHKHED | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736007045/RC/9255 — cc रोड निर्माण कार्य सरस्‍वती शिशु मंदिर से मोहन क | Completed | 112000 | 78519.9 | 2012-10-08 | 2013-03-26
CHHINDWARA / MOHKHED | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007045/RC/9284 — द्वितीय श्रेणी सडक निर्माण राजाडा से छाबडी रोड भाग | Completed | 498000 | 419336.25 | 2013-02-08 | 2014-03-01
CHHINDWARA / MOHKHED | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736007045/RC/रजाडा 001 — द्वितीय श्रेणी सडक निर्माण रजाडा से डोलाढाना 0.5ckm | Completed | 240000 | 217357 | 2007-06-07 | 2011-12-18
CHHINDWARA / MOHKHED | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1736007045/RS/22012035126854 — NALI NIRMAN KARY KAMLESH DESHMUK KE GHAR SE KESHORAO CHOUDHARY KE GHAR TAK | Ongoing | 68000 | 221 | 2024-03-16
CHHINDWARA / MOHKHED | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1736007045/RS/22012035126857 — NALI NIRMAN KARY CHHOTELAL SAHU KE GAHR SE MADHU GHAGRE KE GHAR TAK | Ongoing | 77000 | 221 | 2024-03-16
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50818 — निर्मलभारत अभियान रजाडा गणेश/रामलाल साहू | Completed | 4400 | 4388 | 2013-07-08 | 2013-11-13
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50824 — निर्मल भारत अभियान रजाडा गंगा/दल्‍लू | Completed | 4400 | 4388 | 2013-07-06 | 2013-08-21
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50838 — निर्मल भारत अभियान रिजनलाल/तिजूलाल | Completed | 4400 | 4388 | 2013-07-04 | 2013-08-14
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50885 — NIRMAL BAHRAT MARYDA GUUDI/PARSU FARKARY | Completed | 4400 | 4388 | 2013-07-06 | 2013-08-28
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50893 — नर्मल भारत आभीयान राजू/धनधू | Completed | 4400 | 4388 | 2013-07-18 | 2013-11-20
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50895 — NIRMAL BAHRAT ABHIYAAN KASEINAATH/PANALAL | Completed | 4400 | 4388 | 2013-07-06 | 2013-08-14
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50897 — NIRMAL BAHARAT ABHIYAN KAMLA/GULLAB | Completed | 4400 | 4388 | 2013-07-08 | 2013-11-13
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50901 — NIRMAL BHARAT ABHIYAN LIHKIRAAM/SHANKAR | Completed | 4400 | 4388 | 2013-07-08 | 2013-08-28
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50904 — NIRMAL BAHRHAT ABHIYAN PURDDA/NANHU | Completed | 4400 | 4388 | 2013-07-08 | 2013-11-20
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50906 — NIRMAL BAHARAT ABHIYAN FAGULAL/DAMAJI | Completed | 4400 | 4388 | 2013-07-24 | 2013-08-06
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50909 — NIRMAL BAHRAT ABHIYAN RENUKA/KARU | Completed | 4400 | 4388 | 2013-07-04 | 2013-08-14
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50912 — NERMAL BHARAT ABHIYAN MANOHAR / JIAETRAAM | Completed | 4400 | 4388 | 2013-07-24 | 2013-08-06
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50915 — nermal bahrat abhiyan sampat / kothiya | Completed | 4400 | 4388 | 2013-07-06 | 2013-08-29
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50917 — NERAMAL BAHART ABHIYAAN BADAARAM / BALLAJI | Completed | 4400 | 4388 | 2013-07-24 | 2013-08-06
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50920 — NERMAL BAHARAT ABHIYAN RAMESH / GUDU | Completed | 4400 | 4388 | 2013-07-24 | 2013-09-06
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50926 — NERMAL BAHRAT ABHIYAN BABURAW / BAHKRYA | Completed | 4400 | 4388 | 2013-07-08 | 2013-09-04
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50930 — NERMAL BAHARAT ABHIYAN CHATU / CHINTAMAN | Completed | 4400 | 4388 | 2013-07-06 | 2013-09-04
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/50933 — NERAMAL BAHARAT ABHIYAN SURESH / NAGORAW | Completed | 4400 | 4388 | 2013-07-06 | 2013-08-21
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/51695 — निर्मल भारत अभियान गजानद/रामदास | Completed | 4400 | 4388 | 2013-07-08 | 2013-09-18
CHHINDWARA / MOHKHED | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1736007045/RS/51698 — निर्मल भारत अभियान सहदेव परसराम | Completed | 4400 | 4388 | 2013-07-06 | 2013-08-21
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007045/WC/22012034787706 — water harwesting panchayat bhavavn | Closed | 0 | 0 | 2021-04-14
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007045/WC/22012034787733 — sokhta gdda kup ke pass | Closed | 11168.48 | 0 | 2021-04-14
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007045/WC/22012034787756 — sokhta gdda henad pum ke pas | Closed | 17297.05 | 0 | 2021-04-14
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair maint of Stone boulder Gully Plugs for Comm / Repair and maintenance of Stone boulder Gully Plugs for Community | Repair & maint of Water Harvesting Structures | 1736007045/WC/22012034903414 — nala sudharikarn | Closed | 0 | 0 | 2022-01-26
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair maint of Stone boulder Gully Plugs for Comm / Repair and maintenance of Stone boulder Gully Plugs for Community | Repair & maint of Water Harvesting Structures | 1736007045/WC/22012034903416 — nala sudharikarn | Closed | 0 | 0 | 2022-01-26
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair maint of Stone boulder Gully Plugs for Comm / Repair and maintenance of Stone boulder Gully Plugs for Community | Repair & maint of Water Harvesting Structures | 1736007045/WC/22012034903417 — nala sudharikarn | Closed | 0 | 0 | 2022-01-26
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Groups / Raising of Nursery for Groups | Nursery Development | 1736007045/WC/22012034921139 — Maa ki bagiya ms school rajada | Closed | 0 | 0 | 2022-01-24
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Groups / Raising of Nursery for Groups | Nursery Development | 1736007045/WC/22012034921141 — Maa ki bagiya ms school rajada | Closed | 0 | 0 | 2022-01-24
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Groups / Raising of Nursery for Groups | Nursery Development | 1736007045/WC/22012034921142 — Maa ki bagiya ms school rajada | Closed | 0 | 0 | 2022-01-24
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Groups / Raising of Nursery for Groups | Nursery Development | 1736007045/WC/22012034921144 — Maa ki bagiya ms school rajada | Closed | 0 | 0 | 2022-01-24
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Groups / Raising of Nursery for Groups | Nursery Development | 1736007045/WC/22012034921149 — Maa ki bagiya ms school rajada | Closed | 9552.51 | 0 | 2022-01-24
CHHINDWARA / MOHKHED | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Groups / Raising of Nursery for Groups | Nursery Development | 1736007045/WC/22012034922294 — Maa ki bagiya hs school rajada | Closed | 0 | 0 | 2022-01-24
CHHINDWARA / MOHKHED | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1736007045/WC/22012034947134 — contour tranch tank chhabdi road pthar | Closed | 0 | 0 | 2022-04-11
CHHINDWARA / MOHKHED | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1736007045/WC/22012034947137 — contour tranch tank chhabdi road pthar | Closed | 0 | 0 | 2022-04-11
CHHINDWARA / MOHKHED | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736007045/WC/22012034966797 — CTR/10/Box trench nirman kary Pathar Pahadi Rajada | Closed | 0 | 0 | 2022-04-14
CHHINDWARA / MOHKHED | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1736007045/WC/22012034966802 — CTR/TS/10/Box Trench nirman kary chhabdi road pathar rajada | Closed | 0 | 0 | 2022-04-14
CHHINDWARA / MOHKHED | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1736007045/WC/22012034966819 — Nalla Pathopchar kary Badkuaa nalla rahjada | Closed | 0 | 0 | 2022-04-14
CHHINDWARA / MOHKHED | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1736007045/WC/22012034966823 — Nalla Pathopchar kary Mudiyakheda nalla rajada | Closed | 0 | 0 | 2022-04-14
CHHINDWARA / MOHKHED | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1736007045/WC/22012034988207 — Maa ki bagiya PS Morandhana Rajada | Closed | 0 | 0 | 2022-04-14
CHHINDWARA / MOHKHED | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1736007045/WC/22012035170753 — कन्टूरट्रेच निर्माण कार्य | New | 0 | 0 | 2023-10-02
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736007045/WC/22012035268356 — DUGWELL RECHARGE NRMALNIEKUP RIJANLAL KE GHAR KEPASS | Deleted | 0 | 0 | 2025-04-14
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007045/WC/22012035288459 — DUGWELL RECHARGE NRMALNIEKUP RIJANLAL KE GHAR KEPASS | Physically Completed | 25899.46 | 23565.09 | 2025-05-05 | 2026-04-11
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007045/WC/22012035297753 — Dugwell Recharage struture at Panghat Kup kamthi road Rajada | Physically Completed | 25899.46 | 23042.09 | 2025-05-08 | 2026-04-11
CHHINDWARA / MOHKHED | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736007045/WC/22012035297758 — Dugwell Recharage struture at Kadakha Kup dola road Rajada | Physically Completed | 25899.46 | 22782.09 | 2025-05-08 | 2026-04-11
CHHINDWARA / MOHKHED | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007045/WC/7984 — रजाडा/कूप न‍िर्माण कप‍िल धारा /ह‍िमांशू/प्रेमचंद रजाडा | Completed | 1000 | 143399.94 | 2009-02-09 | 2009-07-20
CHHINDWARA / MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1736007045/WC/8319 — कपिल धारा कूप निर्माण कार्य मनोहर/मगनलाल | Completed | 220000 | 136275 | 2011-05-01 | 2011-08-29
CHHINDWARA / MOHKHED | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1736007045/WC/8392 — नीरमल नीर कुप निर्माण रजाडा | Completed | 280000 | 169478 | 2011-10-19 | 2012-08-31
CHHINDWARA / MOHKHED | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1736007045/WC/कुप निर्माण1/3 — कुप निर्माण कपिल धारा उपयोजना | Completed | 111000 | 92543 | 2007-12-16 | 2011-08-31
CHHINDWARA / MOHKHED | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1736007045/WH/19961644 — निस्तारी तालाब जीर्णोद्धार पंचायत भवन के पीछे | Completed | 160000 | 161049.72 | 2017-05-26 | 2019-07-17
CHHINDWARA / MOHKHED | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1736007045/WH/19961671 — Talab Jeernoudhar Dola Dhana Rajada | Completed | 203000 | 143105.81 | 2017-05-26 | 2019-07-30
CHHINDWARA / MOHKHED | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736007045/WH/19961674 — बडकुआ तालाब रजाडा | Completed | 288000 | 189350.07 | 2017-05-26 | 2019-07-30
CHHINDWARA / MOHKHED | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1736007045/WH/19961677 — Talab Jirnoudhar नागझिरी के पास रजाडा | Completed | 194000 | 183418.6 | 2017-05-26 | 2019-07-30
CHHINDWARA / MOHKHED | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1736/RC/22012034561088 — ग्रेवल रोड(सुदूर सड़क )प्राथमिक शाला रजाडा से मोरनढाना (1row-6,1-fcwपुलिया सहित )2600 मी.ग्राम-मोरनढा | Completed | 8189000 | 6178045.13 | 2021-03-05 | 2025-04-25