## Work List
Exported on: 2026-10-11 23:22:31
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: NANDEWANI
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / SAUSAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736009019/IF/22012035037316 — kapil dara kup nirman karya sanak markam g p nandewani | Physically Completed | 236156.75 | 186190.81 | 2023-06-01 | 2026-05-16
CHHINDWARA / SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1736009019/IF/22012035330170 — Ket talab nirman karya balak Dhurve g p nandewani | Physically Completed | 450885.64 | 440353.7 | 2025-04-16 | 2026-04-13
CHHINDWARA / SAUSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736009019/IF/22012035440295 — JGSA Recharge fit nirman karya panchilal gajame ke kup ke pass g p nandewani | Physically Completed | 25899.46 | 25434.44 | 2025-05-03 | 2026-04-13
CHHINDWARA / SAUSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1736009019/IF/22012035440367 — JGSA Recharge fit nirman karya danraj markam ke kapil dara ke pass gp nandewani | Physically Completed | 25899.46 | 25434.44 | 2025-05-03 | 2026-04-13
CHHINDWARA / SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736009019/IF/22012035469252 — Ket talab nirman karya Mantri Sunku g p nandewani | Physically Completed | 55865.38 | 53826 | 2025-05-14 | 2026-04-13
CHHINDWARA / SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1736009019/IF/22012035494958 — Ket talab nirman karya Ramaji Ahake g p nandewani | Physically Completed | 147621.16 | 140468.1 | 2025-05-12 | 2026-04-13
CHHINDWARA / SAUSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1736009019/IF/IAY/5153191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148608629 | Physically Completed | 24795 | 22707 | 2025-04-08 | 2026-01-29
CHHINDWARA / SAUSAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736009019/RC/22012034544866 — ket sadak ambada rod se sunku ivanati ke ket tak | Physically Completed | 1371721.51 | 1131873.16 | 2020-12-01 | 2026-05-14
CHHINDWARA / SAUSAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1736009019/RC/22012034546398 — ket sadak men rod se keshu ke ket tak | Physically Completed | 1345852.86 | 1113541.84 | 2020-12-01 | 2026-05-14
CHHINDWARA / SAUSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736009019/WC/22012035273195 — JGSA Dugwell recharge fit sarvjanik kuva ke pass g p nandewani | Physically Completed | 25899.46 | 23085.44 | 2025-04-25 | 2026-04-13
CHHINDWARA / SAUSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1736009019/WC/22012035273238 — JGSA Dugwell recharge fit vard no 1 nirmal nir ke pass g p nandewani | Physically Completed | 25899.46 | 23868.44 | 2025-04-25 | 2026-04-13
CHHINDWARA / SAUSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1736009019/WC/22012035290634 — JGSA Recharge fit nirman karya sarkikapa rode per sarvjanik kup ke pass g p nandewani | Physically Completed | 25899.46 | 23085.44 | 2025-05-03 | 2026-04-13
CHHINDWARA / SAUSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1736009019/WC/22012035302405 — Shamudaik khet talab nirman karya jhumak kudape ke khet ke pass Gp nandewani | Physically Completed | 450885.64 | 418683.3 | 2025-05-14 | 2026-04-13
CHHINDWARA / SAUSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1736009019/WC/22012035328118 — Cuntur trench nirman karya mantu vatke ke ket ke pass nadi kinare g p nandewani | Physically Completed | 283049.2 | 234117 | 2026-02-13 | 2026-06-03