## Work List
Exported on: 2026-10-21 14:01:09
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MARKAWARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / PANDHURNA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1736011032/AV/22012034653599 — Puliya Nirman Karya ADKYA Vittu ke khet ke pass kalaphata | Ongoing | 1084004.9 | 0 | 2024-03-16
CHHINDWARA / PANDHURNA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Avenue Plantation for Community | Plantation | 1736011032/DP/22012034570117 — Road side plantation gram markawada se markawada bus stop tak | Ongoing | 410718.19 | 0 | 2023-07-22
CHHINDWARA / PANDHURNA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Line Plantation of Forestry Trees for Individual | Plantation | 1736011032/IF/22012035172243 — Niji Khet Me Falodhan Sukhavanti Shyamrao | Ongoing | 173284 | 0 | 2023-10-09
CHHINDWARA / PANDHURNA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Line Plantation of Forestry Trees for Individual | Plantation | 1736011032/IF/22012035172270 — Niji Khet Me Falodhan Anita Shankar | Ongoing | 173284 | 13311 | 2023-10-09
CHHINDWARA / PANDHURNA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1736011032/IF/22012035172273 — Niji Khet Me Falodhan Omkar Ukandya | Ongoing | 173284 | 9135 | 2024-01-06
CHHINDWARA / PANDHURNA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Line Plantation of Forestry Trees for Individual | Plantation | 1736011032/IF/22012035172280 — Niji Khet Me Falodhan Kanhaiya Ajab | Ongoing | 173284 | 12006 | 2023-10-09
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011032/IF/22012035585599 — EK BAGIYA MAA KE NAAM KALPANA KAMLESH | Ongoing | 278005.93 | 134684 | 2025-09-09
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011032/IF/22012035585616 — EK BAGIYA MAA KE NAAM CHANDRAKALA ROSHAN DESHMUKH | Ongoing | 278005.93 | 120200 | 2025-09-06
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011032/IF/22012035588292 — EK BAGIYA MAA KE NAAM DEVNA ANKIT PARADKAR MP36011032002 275 | Ongoing | 278005.93 | 132022.93 | 2025-09-06
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011032/IF/22012035591033 — EK BAGIYA MAA KE NAAM KALA SADASHIV DESHMUKH | Ongoing | 278005.93 | 138284 | 2025-09-09
CHHINDWARA / PANDHURNA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011032/IF/IAY/2904856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5028661 | Approved | 28500 | 0 | 2021-03-16
CHHINDWARA / PANDHURNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011032/IF/IAY/5207674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131148331 | Ongoing | 28500 | 0 | 2026-06-09
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011032/IF/IAY/5226915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131209094 | Completed | 28500 | 14031 | 2026-01-24 | 2026-09-29
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011032/IF/IAY/5727423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131371325 | Ongoing | 28500 | 0 | 2025-12-05
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011032/IF/IAY/5819154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131371115 | Approved | 28500 | 0 | 2025-02-18
CHHINDWARA / PANDHURNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011032/IF/IAY/5866385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131370884 | Ongoing | 28500 | 14331 | 2026-06-09
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011032/IF/IAY/6270931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131371073 | Approved | 28500 | 0 | 2025-03-21
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011032/IF/IAY/6270932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131371085 | Approved | 28500 | 0 | 2025-02-25
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011032/IF/IAY/6271145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131223016 | Approved | 28500 | 0 | 2025-03-21
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011032/IF/IAY/6271395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131409068 | Approved | 28500 | 0 | 2024-09-26
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011032/IF/IAY/6271685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131371194 | Approved | 28500 | 0 | 2025-02-17
CHHINDWARA / PANDHURNA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1736011032/WC/22012034951433 — NALA SUDHARIKARN KARY GRAM MARKAWADA | Ongoing | 1326785.89 | 0 | 2024-02-03
CHHINDWARA / PANDHURNA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736011032/WC/VB/YD/22012035335866 — CONTOUR TRENCH NIRMAN KARY HEERAJI KUMRE KE KHET KE PAS KALAPATHA GP MARKAWADA | Ongoing | 999824.87 | 0 | 2026-10-10