## Work List
Exported on: 2026-10-21 11:46:18
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PIPAR PANI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / PANDHURNA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Plantation in Coastal Area for Community | Plantation | 1736011037/DP/22012034624064 — व्रचारोपण निर्माण कार्य ओझा झिरी में | Approved | 412288.12 | 0 | 2024-04-14
CHHINDWARA / PANDHURNA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1736011037/IF/22012035021884 — निजी खेत में फलौदयन गोविंद पूनाजी कमरे | Ongoing | 158351 | 0 | 2022-09-20
CHHINDWARA / PANDHURNA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011037/IF/22012035164272 — निजी खेत में फलौदयन गणपति मवजी bhade | Ongoing | 173284 | 0 | 2023-10-18
CHHINDWARA / PANDHURNA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011037/IF/22012035164277 — निजी खेत में foudayan रमेश गुलजू बोबडे | Ongoing | 173284 | 0 | 2023-10-18
CHHINDWARA / PANDHURNA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011037/IF/22012035164281 — निजी खेत में foudayan सुखदेव भोरेलाल नायक | Ongoing | 173284 | 0 | 2023-10-23
CHHINDWARA / PANDHURNA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011037/IF/22012035164292 — निजि खेत में floudayan कमला यादोराव guddhe | Ongoing | 173284 | 0 | 2023-10-18
CHHINDWARA / PANDHURNA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011037/IF/22012035174828 — NIJI KHET ME FLOUDAYAN YADURAV GOJAN Nagwanshi | Ongoing | 173284 | 0 | 2023-12-21
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1736011037/IF/22012035204365 — KAPILDHARA KUP NIRMAN KRYA SATIFULA PATI NOKHELAL NAGWANSHI | Ongoing | 282417.57 | 0 | 2024-06-16
CHHINDWARA / PANDHURNA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1736011037/IF/22012035467551 — RECHARGE PIT KAPILDHARA KUP SUKAN AMRAWANSHI BORGAON | Ongoing | 25899.46 | 0 | 2025-05-06
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011037/IF/22012035591133 — Ek Bagiya Maa Ke Naam Pinki Pati Naresh Barange MP 21004020003 111 | Ongoing | 278005.93 | 15900 | 2025-09-08
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011037/IF/22012035591181 — Ek Bagiya Maa Ke Naam Premvati Pati Kisanlal Lanjewar MP21004020003 111 | Ongoing | 278005.93 | 27000 | 2025-09-08
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011037/IF/22012035591209 — Ek Bagiya Maa Ke naam Kamal Pati kailash Barange MP21004020003 111 | Ongoing | 278005.93 | 27300 | 2025-09-08
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011037/IF/22012035591283 — Ek Bagiya Maa Ke Naam Kamal Pati Bhaskar Barange MP21004020003 111 | Ongoing | 278005.93 | 0 | 2025-09-08
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011037/IF/22012035616710 — Ek Bagiya Maa Ke Naam Archana Pati Vijesh Bhade MP21004020003 543 | Ongoing | 278005.93 | 0 | 2025-09-13
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/4605070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123586837 | Physically Completed | 24795 | 0 | 2024-09-13 | 2026-07-26
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5584061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124811767 | Approved | 28500 | 0 | 2025-04-07
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5584125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119554522 | Approved | 28500 | 0 | 2025-02-22
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5585455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130429502 | Approved | 28500 | 0 | 2025-04-07
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5586007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118119314 | Approved | 28500 | 0 | 2025-03-04
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5763710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132133290 | Approved | 28500 | 0 | 2025-02-22
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5764019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119556318 | Approved | 28500 | 0 | 2025-02-22
CHHINDWARA / PANDHURNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5764930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132134256 | Ongoing | 28500 | 0 | 2026-07-23
CHHINDWARA / PANDHURNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5863305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130116949 | Ongoing | 28500 | 1305 | 2026-04-14
CHHINDWARA / PANDHURNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5863313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132132200 | Ongoing | 28500 | 0 | 2026-05-29
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5863315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116100627 | Physically Completed | 28500 | 0 | 2025-12-10 | 2026-10-18
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5863355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118327201 | Approved | 28500 | 0 | 2025-03-03
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011037/IF/IAY/5920017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116255233 | Approved | 28500 | 0 | 2025-02-22
CHHINDWARA / PANDHURNA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1736011037/RC/22012034832926 — शमशान घाट में सीमेंट कंक्रीट रोड निर्माण कार्य 140मीटर | Approved | 64000 | 0 | 2024-12-22
CHHINDWARA / PANDHURNA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736011037/WC/22012035208046 — BOLDAR CHEK DEM SUNDARLAL IRPACHI KE KHET KE PAS | Approved | 521171.95 | 0 | 2024-04-14
CHHINDWARA / PANDHURNA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1736011037/WC/22012035208052 — BOLDAR CHEK DEM GANGADHAR PARTETI KE KHET KE PAS | Approved | 499088.89 | 0 | 2024-04-14
CHHINDWARA / PANDHURNA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1736011037/WC/22012035227879 — Nistari talab vitthal sable ke khet ke pass borgaon | Ongoing | 2410702.17 | 0 | 2025-02-22
CHHINDWARA / PANDHURNA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1736011037/WC/22012035287996 — RECHARGE PIT SARVAJANIK KUP MUNAJ DHURVE KE MAKAN KE PASS PIPARPANI | Approved | 24899.46 | 0 | 2025-04-14
CHHINDWARA / PANDHURNA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736011037/WC/VB/22012035331039 — CONTOUR TRENCH GHAGHRA GHONDI PHADI ME PIPARPANI | Approved | 0 | 0 | 2026-04-15
CHHINDWARA / PANDHURNA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736011037/WC/VB/22012035331047 — CONTOUR TRENCH GHAGHRA GHONDI PHADI ME PIPARPANI PART-3 | Approved | 405999.84 | 0 | 2026-04-15
CHHINDWARA / PANDHURNA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736011037/WC/VB/22012035331055 — CONTOUR TRENCH PORA GHONDI PAHADI ME GRAM BORGAON PART-3 | Approved | 404000.32 | 0 | 2026-04-15
CHHINDWARA / PANDHURNA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736011037/WC/VB/YD/22012035334646 — CONTOUR TRENCH NIRMAN KARYA GHOGRAGONDI PAHADI ME PART 3 GRAM PIPALPANI | Ongoing | 999902.97 | 268500 | 2026-09-14
CHHINDWARA / PANDHURNA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736011037/WC/VB/YD/22012035334647 — CONTOUR TRENCH NIRMAN KARYA PORAGHONDI PAHADI ME PART 3 GRAM BORGAON | Ongoing | 999801.08 | 575400 | 2026-09-14