## Work List
Exported on: 2026-10-23 04:16:54
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MALEGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035177734 — निजी खेत में नंदन फलोउद्यान कार्य तुकड्या पिता नारायण जाती पवार | Ongoing | 173284 | 6732 | 2024-10-22
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035177780 — निजी खेत में नंदन फलोउद्यान कार्य धनराज पिता पुनाजी जाती पवार | Ongoing | 173284 | 8532 | 2024-10-29
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035177805 — निजी खेत में नंदन फलोउद्यान कार्य मधुकर पीता बाबूराव जाति पवार | Ongoing | 173284 | 17532 | 2024-10-29
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035177841 — निजी खेत में नंदन फलोउद्यान कार्य धनराज पिता भीमराव जाति पवार | Ongoing | 173284 | 18864 | 2024-10-29
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035260799 — निजी खेत फलोद्यान तेजराम पिता भीमराव | Ongoing | 190531 | 36864 | 2024-10-29
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035261698 — निजी खेत फलोद्यान पंढरी पिता पुनाजी गाकरे | Ongoing | 190531 | 10800 | 2024-10-29
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035261722 — निजी खेत फलोद्यान गजानन पिता राघो धारपूरे | Ongoing | 190531 | 28152 | 2024-11-05
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035261877 — निजी खेत फलोद्यान अरविंद पिता रमेश सेवतकर | Ongoing | 190531 | 22698 | 2024-10-29
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035261880 — निजी खेत फलोद्यान विजय पिता नामदेव सहारे | Ongoing | 190531 | 23796 | 2024-10-22
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035261894 — निजी खेत फलोद्यान शेषराव पिता रामराव देशमुख | Ongoing | 190531 | 12132 | 2024-10-29
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035261902 — निजी खेत फलोद्यान रामराव पिता हरिराम डिगरसे | Ongoing | 190531 | 1566 | 2024-10-29
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035261918 — निजी खेत फलोद्यान मनोज पिता मरोती बागडे | Ongoing | 190531 | 0 | 2024-10-29
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035607224 — Ek Bagiya Maa Ke Naam Rita Prabhakar Gakre MP36011062002 284 | Ongoing | 278005.93 | 32292 | 2025-09-09
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1736011062/IF/22012035607240 — Ek Bagiya Maa Ke Naam Pushpa Suresh Ghagre MP36011062002 190 | Ongoing | 278005.93 | 17208 | 2025-09-09
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/4635903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131321595 | Ongoing | 28500 | 16455 | 2025-01-21
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/5176488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130217039 | Ongoing | 28500 | 6003 | 2025-04-29
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/5240670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144131777 | Ongoing | 28500 | 18489 | 2025-05-13
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/5584038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126457733 | Ongoing | 28500 | 15411 | 2026-01-29
CHHINDWARA / PANDHURNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/5730219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130788735 | Approved | 28500 | 0 | 2025-02-19
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/5951301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130217023 | Ongoing | 28500 | 18021 | 2026-03-17
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/5954198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131319879 | Completed | 28500 | 1305 | 2026-03-17 | 2026-09-29
CHHINDWARA / PANDHURNA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/5954199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131320081 | Physically Completed | 28500 | 1305 | 2026-04-21 | 2026-10-18
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/5954204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130155006 | Approved | 28500 | 0 | 2026-02-02
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/5959630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129247771 | Physically Completed | 28500 | 1044 | 2026-03-17 | 2026-10-18
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/5963752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130155104 | Ongoing | 28500 | 6264 | 2026-03-17
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/6164259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130832083 | Approved | 28500 | 0 | 2026-02-27
CHHINDWARA / PANDHURNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1736011062/IF/IAY/6272240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131320368 | Approved | 28500 | 0 | 2026-02-02
CHHINDWARA / PANDHURNA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1736011062/WC/22012035278341 — RECHARGE PIT DUGWELL MOKSHDHAM MALEGAON | Approved | 25899.46 | 0 | 2025-04-14
CHHINDWARA / PANDHURNA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1736011062/WC/22012035281349 — RECHARGE PIT DUGWELL JATRAGODI MALEGAON | Approved | 25899.46 | 0 | 2025-04-14
CHHINDWARA / PANDHURNA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1736011062/WC/22012035281376 — RECHARGE PIT KAPILDHARA SIDHARTH BAGDE MALEGAON | Approved | 104678.18 | 0 | 2025-04-14
CHHINDWARA / PANDHURNA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1736011062/WC/22012035281483 — RECHARGE PIT DUGWELL GHOGRA NADI KE PASS KUKDIKHAPA | Approved | 25899.46 | 0 | 2025-04-14
CHHINDWARA / PANDHURNA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1736011062/WC/VB/YD/22012035335674 — CONTOUR TRENCH NIRMAN KARYA BHOOTA PAHADI GRAM MALEGAON | Ongoing | 397795.45 | 51170 | 2026-10-06