## Work List
Exported on: 2026-08-18 17:45:10
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BADNAOUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI / LAKHNADON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1737001091/DP/22012034575534 — NIRMAL NEER NIRMAN KARY KHAIRI RAIYAT | Ongoing | 523110.34 | 0 | 2023-05-10
SEONI / LAKHNADON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1737001091/FR/22012034321564 — Khet talab nirman kary Omprakash/Mangle | New | 0 | 0 | 2024-06-12
SEONI / LAKHNADON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1737001091/IF/22012035076353 — KAPILDHARA KOOP NIRMAN KARY MASTAN/TANTU BADNOUR | Ongoing | 245888.32 | 0 | 2024-02-01
SEONI / LAKHNADON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1737001091/IF/22012035076375 — KAPILDHARA KOOP NIRMAN KARY PANNALAL/SHIVLAL | Ongoing | 260888.32 | 0 | 2023-07-01
SEONI / LAKHNADON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1737001091/IF/22012035215559 — KAPIL DHARA KOOP NIRMAN KARY JUBBO BAI | Ongoing | 246154.63 | 0 | 2024-03-17
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1737001091/IF/22012035351430 — JGSA FORM POND NIRMAN KARY HEMRAJ/BHAKKU GRAM BADNOUR GP BADNOUR | Approved | 199851.94 | 0 | 2025-04-05
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1737001091/IF/22012035659269 — EK BAGIYA MA KE NAM SHASHI BAI/ BHAGATRAMGRAM BADNORE | New | 0 | 0 | 2025-04-01
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1737001091/IF/22012035659278 — एक बगिया माँ के नाम श्याकली ग्राम डूंगरिया रैयत ग्राम पांचयत बदनौर | Ongoing | 269185.1 | 0 | 2026-01-29
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1737001091/IF/22012035660411 — ek bagiya ma ke nam shyamkali /mojilal gram dungariya raiyat | New | 0 | 0 | 2025-08-15
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1737001091/IF/22012035660482 — Ek Bagiya Maa Ke Naam Shadhi /Bhagatram Gram Badnour Gram Panchayat Badnour | New | 0 | 0 | 2025-11-15
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/4787438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132170868 | Ongoing | 24795 | 0 | 2025-07-27
SEONI / LAKHNADON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/4787442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132177034 | Approved | 24795 | 0 | 2024-09-10
SEONI / LAKHNADON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/4792578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144341095 | Ongoing | 24795 | 0 | 2025-03-22
SEONI / LAKHNADON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/4792579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144341616 | Physically Completed | 24795 | 0 | 2024-12-19 | 2026-08-09
SEONI / LAKHNADON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/4793965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145729119 | Ongoing | 24795 | 0 | 2025-02-08
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/4849982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145710886 | Ongoing | 24795 | 0 | 2026-01-19
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/5553395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144345196 | Ongoing | 24795 | 0 | 2025-05-23
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/5556095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122092078 | Ongoing | 24795 | 0 | 2025-08-12
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/5559035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145119362 | Ongoing | 24795 | 0 | 2025-07-27
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/5563691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122095746 | Ongoing | 24795 | 0 | 2025-08-12
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/5567312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144338559 | Ongoing | 24795 | 0 | 2025-10-29
SEONI / LAKHNADON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/5695852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144160431 | Approved | 24795 | 0 | 2025-02-28
SEONI / LAKHNADON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6059910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144345444 | Ongoing | 24795 | 0 | 2026-05-05
SEONI / LAKHNADON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6059911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144345571 | Ongoing | 24795 | 0 | 2026-05-05
SEONI / LAKHNADON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6060879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132170179 | Ongoing | 24795 | 0 | 2026-07-31
SEONI / LAKHNADON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6062472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122090181 | Ongoing | 24795 | 0 | 2026-07-31
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6064949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132162274 | Approved | 24795 | 0 | 2026-01-29
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6065306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132165359 | Approved | 24795 | 0 | 2026-01-29
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6081884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122089534 | Approved | 24795 | 0 | 2026-01-29
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6081889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122095140 | Approved | 24795 | 0 | 2026-01-29
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6092947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130488361 | Approved | 24795 | 0 | 2026-01-29
SEONI / LAKHNADON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6092948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130488431 | Ongoing | 24795 | 0 | 2026-07-31
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6092950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130489359 | Approved | 24795 | 0 | 2026-02-02
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6092951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130489479 | Approved | 24795 | 0 | 2026-01-29
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6094194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132162249 | Approved | 24795 | 0 | 2026-01-29
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6094196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132162537 | Approved | 24795 | 0 | 2026-01-29
SEONI / LAKHNADON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6094201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132170577 | Ongoing | 24795 | 0 | 2026-07-31
SEONI / LAKHNADON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6094202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132170682 | Approved | 24795 | 0 | 2026-01-29
SEONI / LAKHNADON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6096721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144339424 | Ongoing | 24795 | 0 | 2026-07-31
SEONI / LAKHNADON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6096722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144341885 | Ongoing | 24795 | 0 | 2026-07-31
SEONI / LAKHNADON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737001091/IF/IAY/6096724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144344852 | Ongoing | 24795 | 0 | 2026-07-31
SEONI / LAKHNADON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1737001091/WC/22012035160643 — Countoor trench nirman kary | New | 0 | 0 | 2023-01-25
SEONI / LAKHNADON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1737001091/WC/22012035160644 — Countoor trench nirman kary | New | 0 | 0 | 2023-01-25
SEONI / LAKHNADON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1737001091/WC/22012035160646 — Countoor trench nirman kary | New | 0 | 0 | 2023-01-25
SEONI / LAKHNADON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1737001091/WC/22012035266233 — JGSA DUGWELL RICHARCH PIT NIRMAN KARY DUNGRIYA RAIYAT GP BADNOUR | Approved | 25899.46 | 0 | 2025-04-05
SEONI / LAKHNADON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1737001091/WC/22012035266246 — JGSA DUGWELL RICHARCH PIT NIRMAN KARY KHAIRY RAIYAT GP BADNOUR | Approved | 25899.46 | 0 | 2025-04-05
SEONI / LAKHNADON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1737001091/WC/22012035266252 — JGSA DUGWELL RICHARCH PIT NIRMAN KARY GRAM KHAIRY MALL GP BADNOUR | Approved | 25899.46 | 0 | 2025-04-05
SEONI / LAKHNADON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1737001091/WC/22012035266258 — JGSA DUGWELL RICHARCH PIT NIRMAN KARY GRAM BADNOUR GP BADNOUR | Approved | 25899.46 | 0 | 2025-04-05
SEONI / LAKHNADON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1737001091/WC/22012035326681 — परकुलेशन टेंक निर्माण कार्य ग्राम बदनौर पार्ट3 ग्राम पंचायत बदनोर | Approved | 0 | 0 | 2025-10-02
SEONI / LAKHNADON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1737001091/WH/22012034943666 — PERCOLATION TANK NIRMAN KARY KHAIRY RYT GP BADNOUR | Approved | 0 | 0 | 2025-04-01
SEONI / LAKHNADON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1737001091/WH/22012034943667 — PERCOLATION TANK NIRMAN KARY GRAM BADNOUR GP BADNOUR | Approved | 0 | 0 | 2025-04-01
SEONI / LAKHNADON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1737001091/WH/22012034944534 — JGSA PERCOLATION TANK NIRMAN KARY KHAIRY RYT GP BADNOUR | Approved | 0 | 0 | 2025-04-14
SEONI / LAKHNADON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1737001091/WH/22012034945661 — CPT बॉल निर्माण कार्य ग्राम बदनौर | Approved | 0 | 0 | 2026-01-27