## Work List
Exported on: 2026-10-19 18:42:09
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: GWARI-1
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI / KEOLARI | 2020-2021 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of Workshed for SHG for Community | Construction of building/workshed for SHG | 1737005002/AV/22012034508880 — shantidham main shed nirman karya gwari | Physically Completed | 195535.43 | 0 | 2020-12-22 | 2026-07-21
SEONI / KEOLARI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1737005002/DP/22012034587855 — वसुधा वंदन -अमृत वाटिका 75 विकास कार्य शाला परिसर में ग्राम पंचायत ग्वारी-1 | Ongoing | 55847.4 | 0 | 2023-08-09
SEONI / KEOLARI | 2025-2026 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1737005002/FP/22012034642278 — Nala Saf Safai Work Aam ghat se Ganga nadi ki or GP Gawari1 | Ongoing | 494684.05 | 45700 | 2026-02-06
SEONI / KEOLARI | 2025-2026 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1737005002/FP/22012034642305 — Nala Saf Safai Work Stopdam se mahbub ke khet ki or khairi GP Gawari1 | Ongoing | 496684.65 | 9615 | 2026-02-06
SEONI / KEOLARI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Bio-gas plant for individual / Construction of Biogas Plant for Individual | Bio-gas plant | 1737005002/IF/22012035245588 — नंदन फल उद्यान नजमा बी ग्राम सिंगोडी ग्राम पंचायत ग्वारी घंसौर | Ongoing | 74819.24 | 0 | 2024-08-29
SEONI / KEOLARI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Bio-gas plant for individual / Construction of Biogas Plant for Individual | Bio-gas plant | 1737005002/IF/22012035245591 — नंदन फल उद्यान मंजुलता ग्राम सिंगोडी ग्राम पंचायत ग्वारी घंसौर | Ongoing | 77501.96 | 7240 | 2024-08-29
SEONI / KEOLARI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Bio-gas plant for individual / Construction of Biogas Plant for Individual | Bio-gas plant | 1737005002/IF/22012035245593 — नंदन फल उद्यान नीलू राय ग्राम सिंगोडी ग्राम पंचायत ग्वारी घंसौर | Ongoing | 76944.57 | 2760 | 2024-08-29
SEONI / KEOLARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1737005002/IF/22012035490227 — JGSA Khet Talab Nafija / Ajada GP Gawari1 | Ongoing | 183127.72 | 0 | 2025-05-20
SEONI / KEOLARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1737005002/IF/22012035499069 — JGSA Khet Talab Matin kha / Nasim kha GP Gawari1 | New | 0 | 0 | 2025-04-14
SEONI / KEOLARI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/3756319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119435171 | Ongoing | 28500 | 10920 | 2024-02-21
SEONI / KEOLARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/4680585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142138446 | Ongoing | 28500 | 15360 | 2025-04-30
SEONI / KEOLARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/4757109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119437811 | Ongoing | 28500 | 11580 | 2025-07-08
SEONI / KEOLARI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/4791418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142142679 | Ongoing | 28500 | 0 | 2025-02-14
SEONI / KEOLARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/4791421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142143782 | Ongoing | 28500 | 0 | 2026-01-12
SEONI / KEOLARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/5095246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142142246 | Ongoing | 28500 | 3900 | 2025-07-08
SEONI / KEOLARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/5172707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142141746 | Completed | 24795 | 0 | 2026-02-26 | 2026-07-30
SEONI / KEOLARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/5652067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119435650 | Ongoing | 28500 | 0 | 2025-08-26
SEONI / KEOLARI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/5848142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119435040 | Ongoing | 28500 | 20120 | 2026-05-22
SEONI / KEOLARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/5848425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121659346 | Completed | 24795 | 0 | 2025-12-26 | 2026-07-31
SEONI / KEOLARI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/5967294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142137071 | Ongoing | 28500 | 4060 | 2026-07-13
SEONI / KEOLARI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/5969012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121651091 | Ongoing | 28500 | 7680 | 2026-06-08
SEONI / KEOLARI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/5969438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121688362 | Ongoing | 28500 | 12320 | 2026-05-22
SEONI / KEOLARI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/6078966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119318452 | Ongoing | 28500 | 15920 | 2026-06-19
SEONI / KEOLARI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/6079071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119439431 | Ongoing | 28500 | 11880 | 2026-06-25
SEONI / KEOLARI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/6096090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142141678 | Ongoing | 28500 | 3360 | 2026-07-24
SEONI / KEOLARI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/6096092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142142788 | Ongoing | 28500 | 14760 | 2026-07-13
SEONI / KEOLARI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/6096094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142146301 | Ongoing | 28500 | 14760 | 2026-07-13
SEONI / KEOLARI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/6096100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142148657 | Ongoing | 28500 | 7500 | 2026-07-13
SEONI / KEOLARI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/6229943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119435536 | Ongoing | 24795 | 0 | 2026-05-27
SEONI / KEOLARI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1737005002/IF/IAY/6296527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119436137 | Approved | 28500 | 0 | 2026-02-03
SEONI / KEOLARI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1737005002/LD/22012034595164 — samtalikarn work ps school kheri gp gwari 1 | Ongoing | 898483.99 | 0 | 2023-10-10
SEONI / KEOLARI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1737005002/RC/22012034675317 — ग्वारी से मेनापेपरिया रोड निर्मा0 | New | 0 | 0 | 2024-01-27
SEONI / KEOLARI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1737005002/RC/22012034675322 — ग्वारी से देवघाट सुदूर सपर्क मार्ग | New | 0 | 0 | 2024-01-27
SEONI / KEOLARI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1737005002/RC/22012034675326 — 3 रो पुलिया निर्मा0देवघाट रोड में | New | 0 | 0 | 2024-01-27
SEONI / KEOLARI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1737005002/WC/22012035122153 — Parculation Tank Nirman Work Khairi GP Gwari-1 | Ongoing | 996345.26 | 0 | 2023-10-03
SEONI / KEOLARI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1737/WC/22012035210529 — नवीन तालाब निर्माण कार्य नीरज के खेत के पास ग्राम पंचायत ग्‍वारी RES | Ongoing | 2678000 | 0 | 2025-12-02