## Work List
Exported on: 2026-09-30 16:33:43
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KHANKRA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI / KURAI | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1737007014/AV/22012034538424 — baundeeribal nirmad kary kaniyya school khankra | Ongoing | 361000 | 0 | 2020-10-27
SEONI / KURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1737007014/DP/22012034564200 — Sitafal plantation Shantidham ke pass Beltola_(Khakra) Part-1 | Ongoing | 745191.92 | 0 | 2022-09-10
SEONI / KURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1737007014/DP/22012034564201 — Sitafal plantation Shantidham ke pass Beltola_(Khakra) Part-2 | Ongoing | 745191.92 | 0 | 2022-09-10
SEONI / KURAI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1737007014/DP/22012034567153 — Aavla plantation Beltola_(Khakra) Part-3 | Ongoing | 776691.92 | 0 | 2022-09-18
SEONI / KURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1737007014/DP/22012034591101 — Plantation work Meri mati Mera desh(Amrat vatika_bada talab ke pass Khakra)GP Khakra | Ongoing | 55847.4 | 0 | 2023-08-09
SEONI / KURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1737007014/DP/22012034598262 — Shantidham Parisar Gram Khankra GP Khankra Me Plantation Karya | Ongoing | 380327.94 | 0 | 2023-08-18
SEONI / KURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1737007014/DP/22012034628057 — CNG Hostel campus H S School Khakra G P Khakra | Approved | 0 | 0 | 2024-08-15
SEONI / KURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1737007014/FP/22012034641624 — Nala nal Sambardhan Karya_ (BadaNala Retlal ke khet ke pass se Krishna kumar ke khet ki aur)_Khakra | New | 0 | 0 | 2024-10-02
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1737007014/IF/22012034593157 — Punaram/musaddi ke khet me plantation | Ongoing | 113000 | 0 | 2022-01-25
SEONI / KURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1737007014/IF/22012035198159 — Khet Talab Nirmad Kay Mahadev/Fulshing | Ongoing | 398069.28 | 0 | 2024-02-07
SEONI / KURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1737007014/IF/22012035204137 — Khet Talab Nirmand Kay Tarshing/Sukman Grampanchayat Khankra(katageebanjar) | Ongoing | 400607.88 | 0 | 2024-02-09
SEONI / KURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1737007014/IF/22012035207986 — Khet Talab Nirmand Kay Sukku/Munshilal | Ongoing | 391569.28 | 0 | 2024-02-22
SEONI / KURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1737007014/IF/22012035209829 — Khet Talab Nirmand Kay Durgesh/Suklal | Ongoing | 397071.13 | 0 | 2024-02-22
SEONI / KURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1737007014/IF/22012035209830 — Khet Talab Nirmand Kay Kirpal/Chhotelal | Ongoing | 397071.13 | 0 | 2024-02-22
SEONI / KURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1737007014/IF/22012035352990 — JGSA_Farm Pond Nirman Karya Ganaram/Manglu Khankra(Rajabarra) G.P. Khankra | Ongoing | 147621.16 | 0 | 2025-05-05
SEONI / KURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1737007014/IF/22012035411359 — JGSA_Farm Pond Nirman Karya Maya/Rikhiram Khankra G.P. Khankra | Ongoing | 147621.16 | 0 | 2025-05-14
SEONI / KURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1737007014/IF/22012035482900 — JGSA_Farm Pond Nirman Karya Rajesh/Sukhram Beltola G.P.Khankra | Ongoing | 147621.16 | 0 | 2025-05-19
SEONI / KURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/2356571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1075664 | Ongoing | 28500 | 0 | 2024-04-27
SEONI / KURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/2358899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3460778 | Ongoing | 28500 | 0 | 2024-04-27
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/2797981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3108579 | Ongoing | 28500 | 0 | 2021-04-06
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3203304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3131790 | Ongoing | 28500 | 0 | 2021-09-29
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3288696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2687429 | Approved | 28500 | 0 | 2021-10-26
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3289186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3108475 | Ongoing | 28500 | 0 | 2022-01-25
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3289212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3136332 | Approved | 28500 | 0 | 2021-10-26
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3289241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3155910 | Ongoing | 28500 | 0 | 2022-01-25
SEONI / KURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3289904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3709198 | Ongoing | 28500 | 0 | 2024-02-20
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3289912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3714357 | Ongoing | 28500 | 0 | 2022-03-07
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3293362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4851366 | Approved | 28500 | 0 | 2021-10-26
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3296963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5419005 | Ongoing | 28500 | 0 | 2022-03-07
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3339945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3800262 | Ongoing | 28500 | 0 | 2022-01-25
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3389141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3131782 | Approved | 28500 | 0 | 2021-11-27
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3389638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3166811 | Approved | 28500 | 0 | 2021-11-27
SEONI / KURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3394534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3701672 | Ongoing | 28500 | 0 | 2026-05-21
SEONI / KURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3452082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3845234 | Ongoing | 28500 | 0 | 2024-04-10
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3452218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3895919 | Approved | 28500 | 0 | 2021-12-04
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3454657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4778601 | Ongoing | 28500 | 0 | 2022-03-07
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3456605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5373534 | Ongoing | 28500 | 0 | 2022-03-07
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3456670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5396955 | Approved | 28500 | 0 | 2021-12-04
SEONI / KURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3629572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3124767 | Ongoing | 28500 | 0 | 2022-12-01
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3633917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1764423 | Approved | 28500 | 0 | 2022-01-21
SEONI / KURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/3634449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3124670 | Approved | 28500 | 0 | 2022-01-21
SEONI / KURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/4150702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150238537 | Ongoing | 28500 | 0 | 2024-02-20
SEONI / KURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/4376898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145750021 | Ongoing | 28500 | 0 | 2024-02-20
SEONI / KURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/4410157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150168358 | Ongoing | 28500 | 0 | 2024-07-15
SEONI / KURAI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/464168 — Construction of IAY House -IAY REG. NO. MP1750512 | Ongoing | 28500 | 0 | 2017-04-25
SEONI / KURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/4664425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150955485 | Ongoing | 28500 | 0 | 2025-03-20
SEONI / KURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/4665920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150205556 | Ongoing | 28500 | 0 | 2025-02-18
SEONI / KURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/4797899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149129438 | Ongoing | 28500 | 0 | 2025-02-24
SEONI / KURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/4798838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148834550 | Ongoing | 28500 | 0 | 2025-03-20
SEONI / KURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/4798839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148834617 | Ongoing | 28500 | 0 | 2025-03-20
SEONI / KURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/4802638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151046351 | Ongoing | 28500 | 0 | 2025-03-19
SEONI / KURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/4803505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145058233 | Physically Completed | 24795 | 0 | 2025-03-20 | 2026-07-05
SEONI / KURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/5267428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149926358 | Ongoing | 28500 | 0 | 2025-04-17
SEONI / KURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/5275020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151292254 | Ongoing | 28500 | 0 | 2025-04-17
SEONI / KURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/5301226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150258490 | Ongoing | 28500 | 0 | 2025-04-17
SEONI / KURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1737007014/IF/IAY/5319323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151230808 | Ongoing | 28500 | 0 | 2025-11-08
SEONI / KURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1737007014/WC/22012035182492 — Check Dam Nirmand Kay Mahesh Verma Ke khet Ke Pass Khankra | Ongoing | 1230369.48 | 0 | 2024-03-14
SEONI / KURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1737007014/WC/22012035248345 — Perculation Pit Nirmar Shaskeey bhumi Katangibanger GP Khakra | Ongoing | 479541.05 | 0 | 2025-02-11
SEONI / KURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1737007014/WC/22012035291863 — JGSA_Dug Well Recharge Structure Jaware Ghat Ke Pass Katangi Banjar G.P. Khankra | Ongoing | 25899.46 | 0 | 2025-05-14
SEONI / KURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1737/RC/22012034659529 — सुदूर सडक निर्माण कार्य ग्राम बेलटोल से चक्‍कीखमरिया लंबाई 2.50 km (RES) | Ongoing | 3957000 | 0 | 2023-12-21