## Work List
Exported on: 2026-09-08 07:10:10
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MADANPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BALAGHAT / WARASEONI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1738004036/DP/22012034617851 — मदनपुर नाले से उपवन तक रोड के दोनों वृक्षारोपण कार्य | Approved | 0 | 0 | 2024-06-09
BALAGHAT / WARASEONI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738004036/IF/22012035282803 — khet Talab Nirman Deviprasad / Roopchand | New | 0 | 0 | 2024-12-23
BALAGHAT / WARASEONI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738004036/IF/22012035282804 — khet Talab Nirman Deviprasad / Roopchand | New | 0 | 0 | 2024-12-23
BALAGHAT / WARASEONI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738004036/IF/22012035312990 — खेत तालाब रूपचंद / हगरू निर्माण कार्य | Approved | 372910.02 | 0 | 2025-02-25
BALAGHAT / WARASEONI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1738004036/IF/22012035388547 — JGSA 2025 Recharge peet nirman yogendra / narayan 22012035388451 | Approved | 0 | 0 | 2025-04-11
BALAGHAT / WARASEONI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1738004036/IF/22012035388925 — JGSA 2025 Recharge peet nirman Narayan / Shobharam | Approved | 0 | 0 | 2025-04-11
BALAGHAT / WARASEONI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738004036/IF/22012035521845 — JGSA 2025 khet talab baliram/shivlal harinkhede | Approved | 99724.08 | 0 | 2025-04-14
BALAGHAT / WARASEONI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/125394 — Construction of IAY House -IAY REG. NO. MP-38-004-036-001/6536 | Approved | 28500 | 0 | 2015-10-05
BALAGHAT / WARASEONI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/3586495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5385435 | Ongoing | 28500 | 0 | 2022-03-28
BALAGHAT / WARASEONI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/3613395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5595822 | Approved | 28500 | 0 | 2022-01-03
BALAGHAT / WARASEONI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/4708838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124277731 | Ongoing | 28500 | 0 | 2024-11-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6080721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120879828 | Completed | 24795 | 0 | 2026-04-16 | 2026-08-10
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6083026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123024012 | Physically Completed | 24795 | 7467 | 2026-05-06 | 2026-08-19
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6083747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123557669 | Physically Completed | 24795 | 6843 | 2026-05-06 | 2026-08-19
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6083748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123557834 | Completed | 24795 | 0 | 2026-05-06 | 2026-08-10
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124239016 | Completed | 24795 | 0 | 2026-04-16 | 2026-08-10
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124239381 | Completed | 24795 | 0 | 2026-04-16 | 2026-08-10
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124239753 | Completed | 24795 | 0 | 2026-04-16 | 2026-08-10
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124247743 | Physically Completed | 24795 | 0 | 2026-04-16 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124249539 | Physically Completed | 24795 | 7467 | 2026-05-06 | 2026-08-19
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124255378 | Physically Completed | 24795 | 0 | 2026-05-06 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124258214 | Physically Completed | 24795 | 9600 | 2026-05-06 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124275541 | Physically Completed | 24795 | 9600 | 2026-05-06 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124276161 | Physically Completed | 24795 | 7500 | 2026-04-16 | 2026-07-31
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124276746 | Ongoing | 28500 | 4800 | 2026-05-06
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124279351 | Physically Completed | 24795 | 7800 | 2026-05-06 | 2026-08-05
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124286562 | Physically Completed | 24795 | 4800 | 2026-04-16 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124464663 | Physically Completed | 24795 | 9600 | 2026-05-22 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124473395 | Ongoing | 28500 | 4800 | 2026-05-06
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124475968 | Physically Completed | 24795 | 0 | 2026-04-16 | 2026-08-05
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124479092 | Physically Completed | 24795 | 0 | 2026-04-16 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6084962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124480635 | Physically Completed | 24795 | 0 | 2026-05-06 | 2026-08-05
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6085028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124520775 | Physically Completed | 24795 | 0 | 2026-04-16 | 2026-08-05
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6085066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124540071 | Physically Completed | 24795 | 0 | 2026-05-06 | 2026-08-05
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6085258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124751276 | Physically Completed | 24795 | 6843 | 2026-05-06 | 2026-08-19
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6085425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124825241 | Physically Completed | 24795 | 7800 | 2026-05-22 | 2026-08-05
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6085429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124826101 | Physically Completed | 24795 | 0 | 2026-05-13 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6085435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124827997 | Physically Completed | 24795 | 9600 | 2026-05-06 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6085723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125088541 | Physically Completed | 24795 | 0 | 2026-05-06 | 2026-08-05
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6086873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125869406 | Physically Completed | 24795 | 0 | 2026-04-16 | 2026-08-05
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6087199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126078420 | Physically Completed | 24795 | 6843 | 2026-05-06 | 2026-08-19
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6087231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126096687 | Completed | 24795 | 0 | 2026-04-16 | 2026-08-10
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6087242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126100194 | Physically Completed | 24795 | 6843 | 2026-05-06 | 2026-08-19
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6087445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126236018 | Completed | 24795 | 0 | 2026-04-16 | 2026-08-10
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6087454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126238941 | Ongoing | 28500 | 6300 | 2026-05-22
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6087477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126249071 | Physically Completed | 24795 | 4800 | 2026-05-06 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6087499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126257491 | Ongoing | 28500 | 4800 | 2026-05-06
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6089722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127217240 | Completed | 24795 | 0 | 2026-04-16 | 2026-08-10
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6089729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127225111 | Ongoing | 28500 | 6600 | 2026-05-06
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6089798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127268787 | Physically Completed | 24795 | 9843 | 2026-05-06 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6090149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127497610 | Physically Completed | 24795 | 0 | 2026-05-06 | 2026-08-05
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6090204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127535536 | Completed | 24795 | 0 | 2026-04-16 | 2026-08-10
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6090249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127578759 | Physically Completed | 24795 | 6843 | 2026-05-06 | 2026-08-19
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6091020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128182947 | Physically Completed | 24795 | 6843 | 2026-05-06 | 2026-08-19
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6091028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128187523 | Physically Completed | 24795 | 0 | 2026-04-16 | 2026-08-05
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6131476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124134659 | Physically Completed | 24795 | 0 | 2026-05-06 | 2026-08-05
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6146170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120666820 | Ongoing | 28500 | 9600 | 2026-05-22
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6152699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124281057 | Physically Completed | 24795 | 9600 | 2026-05-06 | 2026-08-17
BALAGHAT / WARASEONI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738004036/IF/IAY/6162838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120864902 | Ongoing | 28500 | 11100 | 2026-05-06
BALAGHAT / WARASEONI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738004036/RC/22012034838323 — सी सी सड़क निर्माण दुर्गाप्रसाद बोपचे के घर से धनलाल नागेश्वर के घर तक 36 मी | Approved | 0 | 0 | 2025-01-20
BALAGHAT / WARASEONI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1738004036/RS/22012034585778 — से‍ग्रिगेशन निर्माण कार्य मदनपुर | Ongoing | 597931.81 | 0 | 2021-10-21
BALAGHAT / WARASEONI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soakage Channel for Community / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1738004036/RS/22012035123521 — banshi pardhi ke ghar se devichouk tak Rcc nali ,nirman | New | 0 | 0 | 2024-04-02
BALAGHAT / WARASEONI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1738004036/WC/22012035201783 — Chabbilal harinkhede ke khet ke pass nale par stop dam nirman karya | Approved | 0 | 0 | 2024-06-04
BALAGHAT / WARASEONI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1738004036/WC/22012035203268 — नाला केचमेंट ट्रीटमेंट कार्य गणेश बाहेश्वर के खेत से बीड तक 1200 मीटर | Approved | 0 | 0 | 2024-06-10
BALAGHAT / WARASEONI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1738004036/WC/22012035233470 — मदनपुर ढोडी के पास परकोलेशन टेंक निर्माण कार्य | Approved | 199997.43 | 0 | 2024-11-21
BALAGHAT / WARASEONI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1738004036/WC/22012035250774 — gram madanpur me chhoti beed me navin talab nirman kary | Approved | 0 | 0 | 2024-12-23
BALAGHAT / WARASEONI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1738004036/WC/22012035259964 — gram madanpur me chhoti beed me navin talab nirman kary | Approved | 0 | 0 | 2025-04-02
BALAGHAT / WARASEONI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1738004036/WH/22012034942781 — ग्राम मदनपुर मे छोटी बीड मे नवीन तालाब निर्माण कार्य | Approved | 0 | 0 | 2024-12-23