## Work List
Exported on: 2026-09-02 22:18:01
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MOHBATTA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BALAGHAT / BAIHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1738007038/AV/22012034652772 — VCW AT NALA | New | 0 | 0 | 2024-01-26
BALAGHAT / BAIHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1738007038/DP/22012034613178 — CNG- Development of cummuntiy nutri garden gp -mobatta | Ongoing | 848484.59 | 0 | 2024-02-14
BALAGHAT / BAIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1738007038/IC/22012034886240 — nirmal neer koop bijora gp mohbatta | New | 0 | 0 | 2024-10-03
BALAGHAT / BAIHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1738007038/IF/22012035242881 — नंदन फ्लोदयान - अलताफ़ / शेख सत्तर ग्राम पंचायत mohbatta | Ongoing | 149819.37 | 6300 | 2024-07-19
BALAGHAT / BAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738007038/IF/22012035452508 — kapil dhara kup pratap parwar / jammu das gp mohbatta | New | 0 | 0 | 2025-04-01
BALAGHAT / BAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1738007038/IF/22012035452833 — kapil dhara kup pratap parwar / jammu das gp mohbatta | Approved | 190104.41 | 0 | 2025-04-01
BALAGHAT / BAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738007038/IF/22012035575680 — JSM khet talab hirma bai / madan gp mohbatta | New | 0 | 0 | 2025-04-01
BALAGHAT / BAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738007038/IF/22012035589926 — Ek Bagiya Maa Ke Naam Kalawati / Ashok Gp Mohbatta | Ongoing | 188104.63 | 300 | 2025-09-20
BALAGHAT / BAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738007038/IF/22012035590731 — Ek Bagiya Maa Ke Naam Plantation Malti / Matuk gram bijora Gp Mohbatta | Ongoing | 184817.52 | 0 | 2025-09-10
BALAGHAT / BAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738007038/IF/22012035615667 — ebmkn kala uikey mohbatta | New | 0 | 0 | 2025-08-01
BALAGHAT / BAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738007038/IF/22012035615676 — ebmkn malti bijora | New | 0 | 0 | 2025-08-01
BALAGHAT / BAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738007038/IF/22012035618017 — ebmkn akavati mohbbatta | Ongoing | 193426.81 | 2100 | 2025-09-19
BALAGHAT / BAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738007038/IF/22012035655882 — khet talab bhagwati / sammat bijora gp MOHBATTA | New | 0 | 0 | 2025-10-02
BALAGHAT / BAIHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/195177 — Construction of IAY House -IAY REG. NO. MP-38-007-038-001/7510 | Approved | 28500 | 0 | 2015-10-05
BALAGHAT / BAIHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/2764249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4071545 | Approved | 28500 | 0 | 2020-10-24
BALAGHAT / BAIHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/3306779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1617439 | Approved | 28500 | 0 | 2021-10-31
BALAGHAT / BAIHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/3312005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5246072 | Approved | 28500 | 0 | 2021-10-31
BALAGHAT / BAIHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/3313440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5589913 | Ongoing | 28500 | 0 | 2022-04-01
BALAGHAT / BAIHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/3313861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5686634 | Approved | 28500 | 0 | 2021-10-31
BALAGHAT / BAIHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/3779311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125821202 | Approved | 28500 | 0 | 2022-05-01
BALAGHAT / BAIHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/3781115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124091866 | Approved | 28500 | 0 | 2022-05-01
BALAGHAT / BAIHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4015943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128517163 | Approved | 28500 | 0 | 2022-05-07
BALAGHAT / BAIHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4016611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126857661 | Approved | 28500 | 0 | 2022-05-07
BALAGHAT / BAIHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4024992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145441215 | Approved | 28500 | 0 | 2022-05-07
BALAGHAT / BAIHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4294032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126009168 | Ongoing | 28500 | 0 | 2022-10-08
BALAGHAT / BAIHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4437268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151956451 | Ongoing | 28500 | 0 | 2024-02-22
BALAGHAT / BAIHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4489301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151948558 | Approved | 28500 | 0 | 2024-01-08
BALAGHAT / BAIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4499187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151970166 | Approved | 28500 | 0 | 2024-06-25
BALAGHAT / BAIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4616127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125782634 | Ongoing | 28500 | 0 | 2025-03-30
BALAGHAT / BAIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4625206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126871984 | Ongoing | 28500 | 0 | 2025-03-30
BALAGHAT / BAIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4778491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126854579 | Ongoing | 28500 | 0 | 2025-03-30
BALAGHAT / BAIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4812336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152060638 | Physically Completed | 24795 | 0 | 2025-01-24 | 2026-07-26
BALAGHAT / BAIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/4958961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122802077 | Ongoing | 28500 | 0 | 2025-03-30
BALAGHAT / BAIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/5211604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125820650 | Ongoing | 28500 | 0 | 2025-03-30
BALAGHAT / BAIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/5602252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122804665 | Approved | 28500 | 0 | 2025-03-21
BALAGHAT / BAIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/5603088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122805231 | Approved | 28500 | 0 | 2025-03-21
BALAGHAT / BAIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/5603089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122805750 | Ongoing | 28500 | 0 | 2026-05-14
BALAGHAT / BAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/5652720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124493497 | Approved | 28500 | 0 | 2025-05-07
BALAGHAT / BAIHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/622648 — Construction of IAY House -IAY REG. NO. MP1013343 | Approved | 28500 | 0 | 2017-02-07
BALAGHAT / BAIHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738007038/IF/IAY/626901 — Construction of IAY House -IAY REG. NO. MP1013525 | Approved | 28500 | 0 | 2017-02-08
BALAGHAT / BAIHAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1738007038/WC/22012035295128 — Dug Well Recharge Struture GP Mohbatta | Approved | 26000.03 | 0 | 2025-04-01
BALAGHAT / BAIHAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1738007038/WC/22012035328018 — const of Earthen Gully Plugs gp mohbatta | Approved | 0 | 0 | 2026-01-26
BALAGHAT / BAIHAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1738007038/WC/22012035329035 — CONTS OF Percolation Tank badi mundi barra gp Mohbatta | Approved | 199998.99 | 0 | 2026-01-26
BALAGHAT / BAIHAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1738007038/WC/VB/22012035332038 — Construction of Bolder Check Dam chamar nala gp mohbatta | Ongoing | 73650.95 | 0 | 2026-08-15
BALAGHAT / BAIHAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1738007038/WC/VB/22012035332615 — Construction of Bolder Check Dam goma nala gp mohbatta | Ongoing | 73650.95 | 0 | 2026-08-31
BALAGHAT / BAIHAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1738007038/WC/VB/22012035332620 — Construction of Bolder Check Dam aama nala gram bijora gp mohbatta | Ongoing | 73650.95 | 0 | 2026-08-19
BALAGHAT / BAIHAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1738007038/WC/VB/22012035332621 — Construction of Bolder Check Dam banjari nala gram bijora gp mohbatta | Ongoing | 73650.95 | 0 | 2026-08-18