## Work List
Exported on: 2026-10-18 04:25:18
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JAMUNIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BALAGHAT / BIRSA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1738009017/AV/22012034653131 — SICHAI TALAB NALA ME KHET PAHUCH MARG CULVERT PULIYA NIRMAN KARYA DORLI | Physically Completed | 1499832.89 | 0 | 2024-03-16 | 2026-08-06
BALAGHAT / BIRSA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1738009017/AV/22012034655949 — Conc.Stopdam cum puliya at Jamunia tola to Bori Road | Physically Completed | 2433994.58 | 0 | 2024-06-11 | 2026-08-06
BALAGHAT / BIRSA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1738009017/DP/22012034580370 — TREE PLANATION WORK DHOBINANDH SHASKIY BHUMI JAMUNIYA | Ongoing | 756626.83 | 47700 | 2023-08-09
BALAGHAT / BIRSA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1738009017/DP/22012034580371 — TREE PLANATION WORK SHANTIDHAM JAMUNIYA TOLA | Ongoing | 756626.83 | 46800 | 2023-09-13
BALAGHAT / BIRSA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Avenue Plantation for Community | Plantation | 1738009017/DP/22012034617665 — JAMUNIYA TOLA TO NAYATOLA APPROCHA ROAD SIDE PLANTATION WORK | Approved | 334600.19 | 0 | 2024-06-10
BALAGHAT / BIRSA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1738009017/IF/22012035287973 — LIKHANLAL/PREMLAL LAGHU TALAB WORK JAMUNIYA | Approved | 0 | 0 | 2024-08-15
BALAGHAT / BIRSA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738009017/IF/22012035622681 — GP jamuniya Gram Dorli Ek Bagiya maa ke naam BHUMESHWARI PARTE | Ongoing | 192410.61 | 2400 | 2025-12-08
BALAGHAT / BIRSA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738009017/IF/22012035656038 — Ek Bagiya Maa ke Name Loudibai/Hirasinh Dorlee | Ongoing | 171818.19 | 3600 | 2026-01-13
BALAGHAT / BIRSA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738009017/IF/22012035656417 — Ek Bagiya Maa ke Name Duklibai sori /Sahrusinh dorlee | Ongoing | 171818.19 | 1500 | 2026-01-13
BALAGHAT / BIRSA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738009017/IF/IAY/3750714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121594888 | Physically Completed | 28500 | 0 | 2022-07-24 | 2026-09-09
BALAGHAT / BIRSA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738009017/IF/IAY/4900801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150159269 | Completed | 24795 | 0 | 2025-03-19 | 2026-07-28
BALAGHAT / BIRSA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738009017/IF/IAY/4900804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150159764 | Ongoing | 28500 | 11400 | 2026-05-03
BALAGHAT / BIRSA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738009017/IF/IAY/4900806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150160238 | Ongoing | 28500 | 9900 | 2025-03-19
BALAGHAT / BIRSA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738009017/IF/IAY/4900810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150160807 | Completed | 24795 | 0 | 2025-03-19 | 2026-07-28
BALAGHAT / BIRSA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738009017/IF/IAY/4901087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126915055 | Completed | 24795 | 0 | 2025-03-19 | 2026-07-28
BALAGHAT / BIRSA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738009017/IF/IAY/4901390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147705623 | Physically Completed | 24795 | 3600 | 2025-07-26 | 2026-07-26
BALAGHAT / BIRSA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738009017/IF/IAY/4901820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148970731 | Ongoing | 28500 | 1800 | 2025-03-16
BALAGHAT / BIRSA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738009017/IF/IAY/4901824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148982242 | Ongoing | 28500 | 5400 | 2026-07-14
BALAGHAT / BIRSA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1738009017/WC/22012035309529 — Amrit sarovar talab nirman dhobi Nala Jamuniya | Approved | 0 | 0 | 2025-04-14
BALAGHAT / BIRSA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1738009017/WC/VB/22012035331025 — Jamuniya Recharge pit MS School Jamuniya ke parisar me | Approved | 0 | 0 | 2026-07-02
BALAGHAT / BIRSA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1738009017/WC/VB/22012035331026 — Jamuniya Recharge pit Biagatola Jamuniya me | Approved | 29241.15 | 0 | 2026-07-02