## Work List
Exported on: 2026-09-26 19:13:07
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: THANEGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BALAGHAT / LANJI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1738010034/AV/22012034657483 — THANEGAON UCHIT MULYA DUKAN SAH GODAM | Approved | 1453662.31 | 0 | 2024-06-08
BALAGHAT / LANJI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1738010034/AV/22012034663985 — THANEGAON MOKSHDHAM KE SAMIP KHEL MEDAN | Approved | 649617.53 | 0 | 2024-10-02
BALAGHAT / LANJI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738010034/IF/22012035618754 — Thanegaon Ek Bagiya Maa ke naam Meena /Baburao MP38010034001/151 | Ongoing | 180181.96 | 0 | 2025-11-19
BALAGHAT / LANJI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/4646899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140430436 | Approved | 28500 | 0 | 2024-09-10
BALAGHAT / LANJI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5093700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP135193823 | Ongoing | 28500 | 0 | 2025-03-21
BALAGHAT / LANJI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5094130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136922427 | Ongoing | 28500 | 0 | 2025-03-21
BALAGHAT / LANJI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5588658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133746629 | Ongoing | 28500 | 0 | 2025-08-03
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5926945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122779672 | Ongoing | 28500 | 7830 | 2026-07-04
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5931524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130705745 | Physically Completed | 24795 | 1827 | 2026-04-11 | 2026-08-03
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5951567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122783010 | Ongoing | 28500 | 3915 | 2026-08-08
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5952088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145765503 | Ongoing | 28500 | 7830 | 2026-07-04
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5954232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP139035303 | Physically Completed | 24795 | 5220 | 2026-04-02 | 2026-08-01
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5954233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP139035586 | Ongoing | 28500 | 7830 | 2026-05-09
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5954238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137483023 | Ongoing | 28500 | 3915 | 2026-08-08
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5954378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137181061 | Ongoing | 28500 | 3915 | 2026-08-08
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5954380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137181340 | Ongoing | 28500 | 0 | 2026-04-11
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5955677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133731411 | Ongoing | 28500 | 5220 | 2026-04-11
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5957608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140430241 | Physically Completed | 24795 | 5220 | 2026-04-02 | 2026-08-01
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5957610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140430883 | Ongoing | 28500 | 3915 | 2026-08-08
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5958170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136662111 | Physically Completed | 24795 | 5220 | 2026-04-02 | 2026-08-01
BALAGHAT / LANJI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5958171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136663204 | Approved | 28500 | 0 | 2026-02-09
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5958172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136663531 | Ongoing | 28500 | 7830 | 2026-05-09
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5958173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136663838 | Physically Completed | 24795 | 5220 | 2026-04-02 | 2026-08-01
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5959487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123462938 | Ongoing | 28500 | 7830 | 2026-07-04
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5961592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122868648 | Ongoing | 28500 | 3915 | 2026-08-08
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5963432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145766012 | Ongoing | 28500 | 3915 | 2026-08-08
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5964166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123840581 | Ongoing | 28500 | 0 | 2026-05-09
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5964413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133711502 | Ongoing | 28500 | 0 | 2026-05-09
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5965617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136967162 | Ongoing | 28500 | 3915 | 2026-08-08
BALAGHAT / LANJI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/5966278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137343629 | Approved | 28500 | 0 | 2026-02-09
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/6078847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118857519 | Ongoing | 28500 | 9135 | 2026-05-02
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/6082733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122777004 | Ongoing | 28500 | 7830 | 2026-07-04
BALAGHAT / LANJI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/6095189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137181220 | Ongoing | 28500 | 9135 | 2026-05-02
BALAGHAT / LANJI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010034/IF/IAY/6160100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137181366 | Approved | 28500 | 0 | 2026-02-09