## Work List
Exported on: 2026-10-10 23:18:26
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: ANDHIYATOLA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BALAGHAT / LANJI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food Grain Storage Building for Community | Constr of Food Grain storage | 1738010040/AV/22012034592631 — ANDHIYATOLA KATTIPAR ME ANAJ BHANDARAN HETU GODOWN NIRMAN | Ongoing | 1283000.43 | 0 | 2021-11-19
BALAGHAT / LANJI | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1738010040/AV/VB/22012034669706 — ANDHIYATOLA PIPE PULIYA NIRMAN KARYA | Approved | 729238.86 | 0 | 2026-04-15
BALAGHAT / LANJI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1738010040/IF/22012035205735 — cattel shed santosh bijewar | New | 0 | 0 | 2024-01-24
BALAGHAT / LANJI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1738010040/IF/22012035270779 — ANDHIYATOLA KHET TALAB JANABAI/DASHARAM | New | 0 | 0 | 2024-10-02
BALAGHAT / LANJI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1738010040/IF/22012035283348 — ANDHIYATOLA KHET TALAB NARBAD/DASHARAM | Approved | 359698.77 | 0 | 2024-10-02
BALAGHAT / LANJI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738010040/IF/22012035592320 — ANDHIYATOLA EK BAGIYA MAA KE NAAM ANUSHAYA MP38010040001 204 | Ongoing | 191234.66 | 0 | 2025-11-13
BALAGHAT / LANJI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738010040/IF/IAY/1866387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2489897 | Approved | 28500 | 0 | 2018-06-27
BALAGHAT / LANJI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738010040/IF/IAY/2682766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5114983 | Approved | 28500 | 0 | 2020-11-27
BALAGHAT / LANJI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1738010040/IF/IAY/4155608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106926640 | Ongoing | 28500 | 0 | 2022-10-31
BALAGHAT / LANJI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1738010040/RC/22012034840378 — ANDHIYATOLA SUBHASH KE MAKAN SE DHUTITOLA PAHUNCH MARGA TAK GRAVEL ROAD | Ongoing | 1796545.37 | 0 | 2025-03-31
BALAGHAT / LANJI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1738010040/RC/VB/22012034854835 — FDFD | Approved | 0 | 0 | 2026-08-15
BALAGHAT / LANJI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1738010040/WC/22012035169025 — dhutitola me nwin talab nirman kary | New | 0 | 0 | 2024-01-24