## Work List
Exported on: 2026-10-01 12:29:04
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: DONGARGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BALAGHAT / LANJI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1738010052/DP/22012034562388 — DONGARGAON BLOCK PLANTATION LALIGHAT KE PASS | Ongoing | 397861.17 | 0 | 2022-08-09
BALAGHAT / LANJI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1738010052/DP/22012034585587 — VASUDHA VANDAN G.P. DONGARGAON PAWER HOUSE TALAB KE PASS | Ongoing | 54564.94 | 0 | 2023-08-26
BALAGHAT / LANJI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1738010052/IF/22012034611267 — DONGARGAON CATTALE SHED DURGAPRASAD / GANNU | Ongoing | 63531.21 | 0 | 2023-06-22
BALAGHAT / LANJI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1738010052/IF/22012035130888 — DONGARGAON NIJI PHALODHODHAN NIRA MAHARADAS DAHARE | Ongoing | 133212.69 | 0 | 2023-07-24
BALAGHAT / LANJI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1738010052/IF/22012035205715 — DONGARGAON GUNIRAM PICHHORE DURGAPRSAD CATTALE SHED NIRMAN KARY | New | 0 | 0 | 2024-01-24
BALAGHAT / LANJI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738010052/IF/22012035268800 — DONGARGAON KHET TALAB CHAMRADAS/SOBHU | Approved | 390942.26 | 0 | 2024-10-02
BALAGHAT / LANJI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1738010052/IF/22012035268806 — DONGARGAON KHET TALAB SAWITRI/HEMRAJ | Approved | 398428.09 | 0 | 2024-10-02
BALAGHAT / LANJI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738010052/IF/22012035590811 — DONGARGAON EK BAGIYA MAA KE NAAM MAMTA LILHARE MP38010052001 327 | New | 0 | 0 | 2025-07-21
BALAGHAT / LANJI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1738010052/IF/22012035592306 — DONGARGAON EK BAGIYA MAA KE NAAM ANITA CHIKHALE MP38010052001 284/B | Ongoing | 191234.66 | 0 | 2025-09-17
BALAGHAT / LANJI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1738010052/IF/IAY/3730579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115637368 | Ongoing | 28500 | 0 | 2022-05-20
BALAGHAT / LANJI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1738010052/RC/22012034678031 — DONGARGAON GORE ROD SE SADARAM FULLARE KE GHAR TAK SUDUR SADK NIRMAN KARY | New | 0 | 0 | 2024-01-24
BALAGHAT / LANJI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1738010052/RC/22012034843700 — DURGESH LILHARE KE GHAR SE AMRIT LILHARE KE GHAR TAK CC ROAD | Ongoing | 19000 | 0 | 2025-05-27
BALAGHAT / LANJI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1738010052/WC/22012035232079 — DONGARGAON PERCOLATION TANK DHANRAJ DAHARE KE KHET KE PASS | Approved | 197562 | 0 | 2024-10-02
BALAGHAT / LANJI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1738010052/WC/22012035232080 — DONGARGAON PERCOLATION TANK DARABHARRI ME | Approved | 197562 | 0 | 2024-10-02
BALAGHAT / LANJI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1738010052/WC/22012035235782 — DONGARGAON KAVALCHAND FULHARE KE KHET KE PASS LAGHU TALAB NIRMAN | Approved | 549555.64 | 0 | 2024-10-02
BALAGHAT / LANJI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1738010052/WC/22012035326198 — Dongargaon Gorre Road Plantation Ke Pass Laghu Talab Nirman | Ongoing | 474409.55 | 0 | 2026-02-23
BALAGHAT / LANJI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1738010052/WH/22012034938963 — DONGARGAON TALAB NIRMAN NKATA NALA PUL KE PASS | New | 0 | 0 | 2024-01-24