## Work List
Exported on: 2026-09-07 05:35:13
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: GOPALPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHEOPUR / BIJEYPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1739001035/DP/22012034615373 — Samudayak please batiks to gopalpur | Ongoing | 1019212.98 | 0 | 2025-01-08
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1739001035/IC/22012034891201 — अमृत सरोवर तलाव निर्माण झिनी झोर के नाले पर हनुमान मंदिर की और | New | 0 | 0 | 2025-04-30
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1739001035/IF/22012035375192 — खेत तालाब हेमकुमार श्रीवास पुत्र हरिज्ञान श्रीवास गोपालपुर | Approved | 147621.16 | 0 | 2025-04-15
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1739001035/IF/22012035450945 — अमृत सरोवर तलाव निर्माण झिनी झोर के नाले पर हनुमान मंदिर की और | New | 0 | 0 | 2025-04-30
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1739001035/IF/22012035633816 — Ek Bagiya Maa Ke Name Lekha GP Gopalpura | Approved | 266578.64 | 0 | 2025-10-02
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1739001035/IF/22012035635531 — Ek Bagiya Maa Ke Mame Guddi GP Gopalpur | Ongoing | 266578.64 | 0 | 2025-11-29
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1739001035/IF/22012035641384 — Ek Bagiya Maa Ke Name Bekunti GP Gopalpur | Ongoing | 266578.64 | 0 | 2025-11-29
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1739001035/IF/22012035641386 — Ek Bagiya Maa Ke Name Bekunti GP Gopalpur | New | 0 | 0 | 2025-08-15
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/2200535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1880656 | Ongoing | 27000 | 0 | 2024-05-10
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/2203095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3442647 | Ongoing | 27000 | 0 | 2024-10-13
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4049018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129463106 | Physically Completed | 23490 | 0 | 2024-08-01 | 2026-08-02
SHEOPUR / BIJEYPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4097469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128616239 | Ongoing | 27000 | 5400 | 2023-09-08
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4097750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137635074 | Ongoing | 27000 | 3600 | 2025-01-29
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4099677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128694623 | Ongoing | 27000 | 3600 | 2024-11-26
SHEOPUR / BIJEYPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4099725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128709191 | Ongoing | 27000 | 3600 | 2022-08-26
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4205142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149504312 | Ongoing | 27000 | 0 | 2024-08-01
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4488198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020306 | Ongoing | 27000 | 0 | 2024-06-01
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4488351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151950843 | Physically Completed | 23490 | 0 | 2025-01-29 | 2026-08-16
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4488423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151781675 | Ongoing | 27000 | 0 | 2025-01-29
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4488427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151783611 | Ongoing | 27000 | 0 | 2025-01-29
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4488602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151879081 | Approved | 27000 | 0 | 2024-05-15
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4503087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151770001 | Ongoing | 27000 | 900 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4503095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151770124 | Ongoing | 27000 | 0 | 2025-03-07
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4503198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151965536 | Ongoing | 27000 | 0 | 2025-07-13
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4503383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151778457 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4503865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151939123 | Ongoing | 27000 | 0 | 2025-03-05
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4503871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151939472 | Ongoing | 27000 | 0 | 2024-12-04
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4504263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151867783 | Ongoing | 27000 | 0 | 2025-07-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4504809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032895 | Ongoing | 27000 | 0 | 2025-07-07
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4506256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151945726 | Ongoing | 27000 | 0 | 2025-01-29
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4506336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151950837 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4727517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151778422 | Ongoing | 27000 | 0 | 2025-03-05
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4727548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779494 | Ongoing | 27000 | 0 | 2025-01-29
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4728026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151939349 | Ongoing | 27000 | 0 | 2025-07-18
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4728027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151939372 | Ongoing | 27000 | 0 | 2025-01-16
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4728047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151940013 | Ongoing | 27000 | 0 | 2025-01-29
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4728569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152019637 | Physically Completed | 23490 | 0 | 2025-01-29 | 2026-08-16
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4728582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152020693 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4728607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152022133 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4730182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151770447 | Ongoing | 27000 | 3600 | 2025-01-14
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4733102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151783651 | Ongoing | 27000 | 0 | 2025-07-25
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4834736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151772704 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4834737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151772705 | Ongoing | 27000 | 0 | 2025-01-29
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4834740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151772779 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4835269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779282 | Ongoing | 27000 | 0 | 2025-01-29
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4835280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779650 | Ongoing | 27000 | 0 | 2025-03-05
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4835286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779798 | Ongoing | 27000 | 0 | 2024-12-04
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4835396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151781599 | Ongoing | 27000 | 0 | 2025-07-16
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4835407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151781663 | Ongoing | 27000 | 0 | 2025-01-16
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4837436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151934769 | Ongoing | 27000 | 0 | 2025-03-05
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4837571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151938850 | Ongoing | 27000 | 0 | 2025-03-05
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4837585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151939224 | Physically Completed | 23490 | 0 | 2025-01-29 | 2026-08-16
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4837879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151768242 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4838274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151932780 | Ongoing | 27000 | 0 | 2025-01-16
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4840893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152030457 | Physically Completed | 23490 | 0 | 2025-03-05 | 2026-08-16
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4841253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031541 | Ongoing | 27000 | 0 | 2025-03-07
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4841255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031573 | Physically Completed | 23490 | 0 | 2025-03-07 | 2026-08-02
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4844363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152058494 | Ongoing | 27000 | 0 | 2025-07-05
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4868532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151950893 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4868576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152034422 | Ongoing | 27000 | 0 | 2025-03-07
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4868701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779056 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4869038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151783590 | Ongoing | 27000 | 0 | 2025-01-16
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4869118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031568 | Ongoing | 27000 | 0 | 2025-03-05
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4869126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032396 | Ongoing | 27000 | 0 | 2025-02-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4869305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152022129 | Ongoing | 27000 | 0 | 2025-03-07
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4869357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151989010 | Ongoing | 27000 | 0 | 2025-09-01
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4869662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151939192 | Ongoing | 27000 | 0 | 2025-01-16
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4871454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130310438 | Ongoing | 27000 | 0 | 2024-12-28
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4871484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141726709 | Ongoing | 27000 | 10800 | 2024-12-28
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4871724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130095393 | Ongoing | 27000 | 0 | 2024-12-28
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4871849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133110819 | Ongoing | 27000 | 1200 | 2025-09-19
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4871864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143676016 | Approved | 27000 | 0 | 2024-10-04
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4872246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136641568 | Ongoing | 27000 | 3600 | 2024-12-28
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4872505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643586 | Ongoing | 27000 | 1200 | 2024-12-28
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4872506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643599 | Ongoing | 27000 | 0 | 2024-12-28
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4872507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643626 | Ongoing | 27000 | 2400 | 2024-12-28
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4872508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643667 | Ongoing | 27000 | 0 | 2024-12-28
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4872509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643684 | Approved | 27000 | 0 | 2024-09-21
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4873612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151950835 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4873614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151950873 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4874093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151966132 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4875905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152058472 | Ongoing | 27000 | 0 | 2025-07-07
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4875958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152065427 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4877065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152005636 | Ongoing | 27000 | 0 | 2025-01-16
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4877120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152032391 | Ongoing | 27000 | 0 | 2025-02-14
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/4877269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152018638 | Ongoing | 27000 | 0 | 2025-01-14
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5109326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151919472 | Ongoing | 27000 | 0 | 2025-07-07
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5110722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152018657 | Ongoing | 27000 | 0 | 2025-09-15
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5111013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152030358 | Ongoing | 27000 | 0 | 2025-08-07
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5111017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152030447 | Ongoing | 27000 | 0 | 2026-02-24
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5111027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152031185 | Ongoing | 27000 | 0 | 2025-11-01
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5517926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144072268 | Approved | 27000 | 0 | 2025-03-19
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5519316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141329186 | Physically Completed | 23490 | 0 | 2025-09-19 | 2026-08-02
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5522564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130944870 | Physically Completed | 27000 | 0 | 2025-03-19 | 2026-09-06
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5524274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643703 | Approved | 27000 | 0 | 2025-03-19
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5526311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137584085 | Approved | 27000 | 0 | 2025-03-17
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5528391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142642454 | Approved | 27000 | 0 | 2025-03-30
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5528392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142642483 | Approved | 27000 | 0 | 2025-03-17
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5570452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144606392 | Approved | 27000 | 0 | 2025-03-30
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5570830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130095147 | Approved | 27000 | 0 | 2025-03-17
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5570911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132294001 | Approved | 27000 | 0 | 2025-03-30
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5571478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643612 | Approved | 27000 | 0 | 2024-12-29
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5572266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146158571 | Approved | 27000 | 0 | 2025-03-30
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5572798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142019488 | Approved | 27000 | 0 | 2025-03-30
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5573649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142642457 | Physically Completed | 27000 | 0 | 2025-03-19 | 2026-09-06
SHEOPUR / BIJEYPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5573650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142642474 | Approved | 27000 | 0 | 2025-03-17
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5654692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152092572 | Approved | 27000 | 0 | 2025-05-05
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5655443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152092134 | Physically Completed | 23490 | 0 | 2026-02-24 | 2026-08-02
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5655445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152092189 | Ongoing | 27000 | 0 | 2026-02-24
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5655449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152092330 | Physically Completed | 23490 | 0 | 2026-02-23 | 2026-08-02
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5655450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152092333 | Physically Completed | 27000 | 0 | 2026-02-23 | 2026-08-30
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5655876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152092992 | Ongoing | 27000 | 0 | 2026-02-24
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5655877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152092994 | Physically Completed | 27000 | 0 | 2026-02-24 | 2026-08-30
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5721757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128625230 | Approved | 27000 | 0 | 2025-05-23
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5725068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129473188 | Ongoing | 27000 | 0 | 2025-10-30
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5726235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142642435 | Approved | 27000 | 0 | 2025-06-30
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/5732599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643571 | Approved | 27000 | 0 | 2025-05-23
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6137431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128697423 | Approved | 27000 | 0 | 2026-03-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6138028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148865033 | Approved | 27000 | 0 | 2026-03-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6151223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128695550 | Approved | 27000 | 0 | 2026-03-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6166910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142642479 | Approved | 27000 | 0 | 2026-03-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6166958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643894 | Approved | 27000 | 0 | 2026-03-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6170345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643596 | Approved | 27000 | 0 | 2025-06-30
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6170346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643646 | Approved | 27000 | 0 | 2026-03-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6170347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643661 | Approved | 27000 | 0 | 2026-03-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6170348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643678 | Approved | 27000 | 0 | 2026-03-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6178596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142642471 | Approved | 27000 | 0 | 2026-03-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6179185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129640381 | Approved | 27000 | 0 | 2025-05-23
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6190178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142642393 | Approved | 27000 | 0 | 2026-03-10
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6191100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144122161 | Approved | 27000 | 0 | 2026-03-20
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6192046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149933975 | Approved | 27000 | 0 | 2026-03-20
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6194525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143675932 | Approved | 27000 | 0 | 2026-03-20
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6194843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141330642 | Approved | 27000 | 0 | 2026-03-10
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6198989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142279969 | Approved | 27000 | 0 | 2026-03-10
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6202422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149935670 | Approved | 27000 | 0 | 2026-03-20
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6202560 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150038717 | Approved | 27000 | 0 | 2026-03-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6206358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142642684 | Approved | 27000 | 0 | 2026-03-13
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6207549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643579 | Approved | 27000 | 0 | 2026-03-20
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6208026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130944896 | Approved | 27000 | 0 | 2026-03-10
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6208120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129464183 | Approved | 27000 | 0 | 2026-03-10
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6213761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142642420 | Approved | 27000 | 0 | 2026-03-10
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6215418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129036744 | Approved | 27000 | 0 | 2026-03-10
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6217166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142643617 | Approved | 27000 | 0 | 2026-03-20
SHEOPUR / BIJEYPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1739001035/IF/IAY/6217382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128697504 | Approved | 27000 | 0 | 2026-03-20
SHEOPUR / BIJEYPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1739001035/RC/22012034638433 — Rapata Cum Puliya Nirman Kamalsingh Ke Khet Ke Pass GP. Gopalpura | Ongoing | 1464566.5 | 0 | 2023-08-08
SHEOPUR / BIJEYPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1739001035/RC/22012034638440 — Rapata Cum Puliya Nirman Gopal Ke Khet Ke Pass GP. Gopalpura | Ongoing | 1457726.05 | 0 | 2023-08-08
SHEOPUR / BIJEYPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1739001035/RC/22012034639588 — Rapata Cum Puliya Nirman Aam Rasta Kharer Par Chhack Ke Upar GP. Gopalpura | Ongoing | 1446016.78 | 0 | 2023-08-08
SHEOPUR / BIJEYPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035223047 — Naveen Taliya Niraman karya babu bairkike pass GP Gopalpura | Approved | 0 | 0 | 2024-08-15
SHEOPUR / BIJEYPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035223048 — Naveen Taliya Niraman karya chamcham ke pass GP Gopalpura | New | 0 | 0 | 2024-08-15
SHEOPUR / BIJEYPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035223049 — Naveen Taliya Niraman karya chamcham ke pass GP Gopalpura | Approved | 0 | 0 | 2024-08-15
SHEOPUR / BIJEYPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035223050 — Naveen Taliya Niraman karya neeb ke pass GP Gopalpura | Approved | 0 | 0 | 2024-08-15
SHEOPUR / BIJEYPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035223051 — Naveen Taliya Niramanlakhan ke khet ke pass GP Gopalpura | Approved | 0 | 0 | 2024-08-15
SHEOPUR / BIJEYPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035223052 — Naveen Taliya Niraman karya kas ke pass GP Gopalpura | Approved | 0 | 0 | 2024-08-15
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1739001035/WC/22012035300053 — नवीन तालाब निर्माण मंदिर के पास बाले नाले पर GP गोपालपुर | Approved | 0 | 0 | 2025-04-30
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035309626 — amrit sarovar nirman behar ke patpare ke pass gp gopalpura | Ongoing | 2495268.9 | 0 | 2025-06-07
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035310005 — Navin talab nirman karya jhini jhor ke nale par hanuman ji ke mandir ki ore | Approved | 0 | 0 | 2025-04-14
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313380 — talab nirman karya jhini jhore ke nale par hanuman ji ke mandir ki ore gopalpur | Ongoing | 2487914.07 | 0 | 2025-06-16
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313427 — Talaiya piching and best bear nirmad kary jhinejhur ke pass gp gopalpur | Approved | 0 | 0 | 2025-04-14
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313431 — Talaiya piching and best bear nirmad kary Ramnivas Kushawah ke khet ke khurdbarapass gp gopalpur | Approved | 0 | 0 | 2025-04-14
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1739001035/WC/22012035313551 — Nabin talab nirmadkarya situapura ke pas g p gopalpur | Approved | 1473007.85 | 0 | 2025-04-14
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313561 — Taliya nirman | New | 0 | 0 | 2025-05-10
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313596 — Naveen talab nirmad kary sutua pura ke pass gp gopalpur | Approved | 0 | 0 | 2025-04-14
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313597 — Naveen talab nirmad kary chakk sahrane ke pas gp gopalpur | Ongoing | 1468662.1 | 0 | 2025-06-20
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313599 — Talaiya nirmad kary adiwasi basti ke upar gp gopalpur | Approved | 0 | 0 | 2025-04-14
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313600 — Naveen talab nirmad kary shukh nadi ke pas gp gopalpur | Approved | 1471369.47 | 0 | 2025-04-14
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313601 — Naveen talab nirmad kary situapura ke upar dagi baba ke pas gp gopalpur | Approved | 1460264.84 | 0 | 2025-04-14
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313603 — nabeen talab nirmad teen sed ke upar gp gopalpur | Approved | 1475973.93 | 0 | 2025-04-14
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313605 — Naveen talab nirmad kary hanuman mandir ke pas gp gopalpur | Approved | 1464523.01 | 0 | 2025-04-14
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313607 — Naveen talab nirmad kary khirkai ke pas gp gopalpur | Ongoing | 1467631.74 | 0 | 2025-07-07
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313609 — Naveen talab nirmad kary Patpare ke upar gp gopalpur | Ongoing | 1471460.48 | 0 | 2025-06-20
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313610 — Naveen talab nirmad kary Jaypura ke pas gp gopalpur | Ongoing | 1467599.76 | 0 | 2025-06-20
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313612 — Naveen talab nirmad kary hanuman mandir jaypura ke beechke pas gp gopalpur | Approved | 0 | 0 | 2025-04-14
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313614 — nabeen talab nirmad hanuman mandir or jaypura ke beech gp gopalpur | Ongoing | 1468218.12 | 0 | 2025-06-20
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313615 — nabeen talab nirmad gopalpur kirkai be beech gp gopalpur | Ongoing | 1456151.88 | 0 | 2025-06-20
SHEOPUR / BIJEYPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1739001035/WC/22012035313616 — Nabeen talaiya nirmd medabali ki kirkai ke pas purana gaw Bichpuri | Approved | 0 | 0 | 2025-04-14