## Work List
Exported on: 2026-09-14 11:51:08
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BHAREWA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
UMARIA / MANPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1740001006/AV/22012034649950 — CONSTRUCTION OF NEW DRAIN CHHEDAMI KE GHAR SE GUDDI KE GHAR TAK | Ongoing | 88000 | 0 | 2023-10-12
UMARIA / MANPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of SHG/Fed building for Groups / Construction of SHG Building for Community | Construction of building/workshed for SHG | 1740001006/AV/22012034662575 — CONTRUCTION OF JAN CHAUPAL CHAUDHARI MOHALLA BHAREWA | Ongoing | 73000 | 0 | 2025-03-20
UMARIA / MANPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1740001006/AV/22012034662576 — CONTRUCTION OF SLAB CULVERT AT ASHOK MISHRA KE GHAR PAAS | Approved | 28000 | 0 | 2024-10-02
UMARIA / MANPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1740001006/IF/22012034623203 — pashu shed nirman suneeta mishra | Ongoing | 101804.91 | 0 | 2021-01-31
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1740001006/IF/22012034896784 — PASU SED NIRMAN AHILYA BAI | Ongoing | 103482.45 | 0 | 2022-05-27
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1740001006/IF/22012034897589 — pasu sed nirman pushpa devi/ramkrashna mishra | Ongoing | 103482.45 | 0 | 2022-05-27
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1740001006/IF/22012034897596 — pasu sed nirman kalpna mishra /additya mishra | Ongoing | 103482.45 | 0 | 2022-05-27
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1740001006/IF/22012034897612 — pasu sed nirman prabha mishra /anil mishra | Ongoing | 103482.45 | 0 | 2022-05-27
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1740001006/IF/22012034992943 — pasu sed nirman paisun gautam/ramkinkar gautam | Ongoing | 103482.45 | 0 | 2022-05-27
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1740001006/IF/22012034992946 — PASHU SED MIRMAN ARACHANA MISHRA | Ongoing | 103482.45 | 0 | 2022-05-27
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1740001006/IF/22012035046330 — पशु शेड निर्माण किरण गौतम/प्रवीण गौतम ग्राम पंचायत भरेवा | Ongoing | 125121.52 | 0 | 2024-06-08
UMARIA / MANPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/22012035074847 — प्रधानमंत्री आवास अशोक/रामनरेश तिवारी MP126246865 | Ongoing | 19380 | 0 | 2023-04-28
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/22012035075992 — pm awas sonaiya chaudhari | Ongoing | 19380 | 0 | 2024-10-09
UMARIA / MANPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/22012035076043 — pm awas premshankar | Ongoing | 19380 | 0 | 2023-05-31
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1740001006/IF/22012035241509 — khet talab nirman karya suresh kol | Ongoing | 199697.77 | 0 | 2024-11-21
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1740001006/IF/22012035278627 — khet talab nirman karya mamta mishra | New | 0 | 0 | 2024-10-02
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1740001006/IF/22012035386897 — khet talab nirman karya-Maniklal Chaudhary Bharewa | Ongoing | 185441.45 | 0 | 2025-05-29
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1740001006/IF/22012035446025 — Dugwell Recharge pit Indrabhan Mishra ke ghar pass Bharewa | Ongoing | 25899.46 | 0 | 2025-05-10
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1740001006/IF/22012035446069 — Dugwell Recharge pit Satish Bhatt ke ghar pass Bharewa | Ongoing | 25899.46 | 0 | 2025-05-10
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1740001006/IF/22012035446125 — Dugwell Recharge pit Anuj Payasi ke ghar pass Bharewa | Ongoing | 25899.46 | 0 | 2025-05-10
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1740001006/IF/22012035446246 — Dugwell Recharge pit Shivnarayan Mishra ke ghar pass Bharewa | Ongoing | 25899.46 | 0 | 2025-05-10
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1740001006/IF/22012035557424 — Contruction of iay/if/ Raju Chaudhari mp140881472 | Ongoing | 19000 | 0 | 2025-09-23
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1740001006/IF/22012035655345 — pashushed nirman karya devsharan bhatt gp bharewa | Approved | 0 | 0 | 2025-04-14
UMARIA / MANPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/3138224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5537795 | Ongoing | 28500 | 0 | 2021-06-23
UMARIA / MANPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/3138599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5662843 | Ongoing | 28500 | 0 | 2021-06-23
UMARIA / MANPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/3145176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5197221 | Ongoing | 28500 | 0 | 2021-06-23
UMARIA / MANPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/3145201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4442423 | Ongoing | 28500 | 0 | 2021-06-23
UMARIA / MANPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/3166605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5625888 | Ongoing | 28500 | 0 | 2021-06-23
UMARIA / MANPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/3184954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5512466 | Ongoing | 28500 | 0 | 2021-09-24
UMARIA / MANPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/3184961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5218948 | Ongoing | 28500 | 0 | 2021-09-26
UMARIA / MANPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/3279530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5613935 | Ongoing | 28500 | 0 | 2022-02-04
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/3698236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105391830 | Approved | 28500 | 0 | 2022-05-01
UMARIA / MANPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/3871523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140868095 | Ongoing | 28500 | 0 | 2024-01-03
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4218118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140906305 | Approved | 28500 | 0 | 2022-06-06
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4253735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126644773 | Ongoing | 28500 | 0 | 2022-07-29
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4255781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140544365 | Ongoing | 28500 | 0 | 2022-09-08
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4255785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140597328 | Ongoing | 28500 | 0 | 2022-07-29
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4367300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140650842 | Approved | 28500 | 0 | 2022-06-09
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4384363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140847132 | Approved | 28500 | 0 | 2022-09-25
UMARIA / MANPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4477045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140523865 | Approved | 28500 | 0 | 2022-09-25
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4817122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100473156 | Ongoing | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4817691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102240845 | Ongoing | 28500 | 0 | 2025-10-10
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4818653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105392454 | Approved | 28500 | 0 | 2024-09-14
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4819682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114172873 | Approved | 28500 | 0 | 2024-09-10
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4819683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114173300 | Ongoing | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4828095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126277649 | Ongoing | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4828097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126279479 | Approved | 28500 | 0 | 2024-09-10
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4828099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126282513 | Approved | 28500 | 0 | 2024-09-10
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4829538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126238742 | Approved | 28500 | 0 | 2024-09-15
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4829563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126261900 | Approved | 28500 | 0 | 2024-09-14
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4829574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126271163 | Ongoing | 28500 | 0 | 2025-02-08
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140325824 | Ongoing | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140436307 | Approved | 28500 | 0 | 2024-09-14
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140454639 | Ongoing | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140519895 | Ongoing | 28500 | 0 | 2025-11-29
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140528744 | Approved | 28500 | 0 | 2024-09-15
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140531840 | Approved | 28500 | 0 | 2024-09-12
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140531872 | Ongoing | 28500 | 0 | 2025-04-07
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140552448 | Ongoing | 28500 | 0 | 2025-04-07
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140658815 | Approved | 28500 | 0 | 2024-09-15
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140815354 | Ongoing | 28500 | 0 | 2025-04-07
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140854768 | Approved | 28500 | 0 | 2024-09-10
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140861177 | Approved | 28500 | 0 | 2024-09-19
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140872654 | Ongoing | 28500 | 0 | 2025-05-14
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140878964 | Ongoing | 28500 | 0 | 2025-04-07
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140881855 | Approved | 28500 | 0 | 2024-09-14
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140886719 | Approved | 28500 | 0 | 2024-09-15
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140939531 | Ongoing | 28500 | 0 | 2025-02-08
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4831943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140980480 | Physically Completed | 24795 | 0 | 2025-01-17 | 2026-07-19
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4854672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114173107 | Ongoing | 28500 | 0 | 2025-11-29
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4855330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140610470 | Approved | 28500 | 0 | 2024-09-19
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4855331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140677481 | Ongoing | 28500 | 0 | 2025-11-29
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4855333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140815507 | Approved | 28500 | 0 | 2024-09-15
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4871005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114172142 | Approved | 28500 | 0 | 2024-09-14
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4871007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114172766 | Approved | 28500 | 0 | 2024-09-14
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4871587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140637655 | Ongoing | 28500 | 0 | 2025-11-29
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4871588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140677533 | Ongoing | 28500 | 0 | 2025-10-10
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4887370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114174112 | Approved | 28500 | 0 | 2024-09-14
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4903819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140583669 | Ongoing | 28500 | 0 | 2025-11-29
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4904679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140799953 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4904680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140820058 | Ongoing | 28500 | 0 | 2025-09-23
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4904681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140913686 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/4998487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115274321 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5017262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125290686 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5018109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126231691 | Ongoing | 28500 | 0 | 2025-10-10
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5094476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140518716 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5094521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140880777 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5094523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140895924 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5094524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140898639 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5263387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140917060 | Approved | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5293228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140552392 | Ongoing | 28500 | 0 | 2026-05-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5296110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140929068 | Approved | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5301983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140824047 | Approved | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5306210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140671374 | Approved | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5313330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140910229 | Approved | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5336290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140931542 | Approved | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5526168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140575461 | Approved | 28500 | 0 | 2025-04-01
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5526984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126233759 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5527093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140516934 | Approved | 28500 | 0 | 2025-04-01
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5528867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140525096 | Approved | 28500 | 0 | 2025-04-01
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5531658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126597306 | Ongoing | 28500 | 0 | 2026-02-03
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5695332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140880875 | Approved | 28500 | 0 | 2024-09-27
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5696151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140677911 | Ongoing | 28500 | 0 | 2025-11-29
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5696935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126675530 | Approved | 28500 | 0 | 2025-04-01
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5697251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140630029 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5697340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105392676 | Approved | 28500 | 0 | 2024-09-14
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5721167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126258739 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5721861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114173211 | Approved | 28500 | 0 | 2024-09-12
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5723601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140881397 | Approved | 28500 | 0 | 2024-09-27
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5723602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140883770 | Approved | 28500 | 0 | 2025-04-17
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5724187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125888257 | Approved | 28500 | 0 | 2025-07-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5727461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140694877 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5729638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140519522 | Approved | 28500 | 0 | 2025-07-24
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5729650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141090319 | Ongoing | 28500 | 0 | 2025-11-29
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5731066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140819432 | Approved | 28500 | 0 | 2025-07-24
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5731068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140910210 | Approved | 28500 | 0 | 2025-07-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5731258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140444214 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5732609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140515285 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5732965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115274278 | Ongoing | 28500 | 0 | 2026-05-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5732971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140676352 | Approved | 28500 | 0 | 2025-02-28
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5812966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140886846 | Approved | 28500 | 0 | 2025-08-28
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5813148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140514838 | Approved | 28500 | 0 | 2025-08-28
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5813172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105393051 | Approved | 28500 | 0 | 2025-08-28
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5870728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126273462 | Approved | 28500 | 0 | 2025-04-01
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5870735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140740994 | Approved | 28500 | 0 | 2025-09-23
UMARIA / MANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5870740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126571762 | Ongoing | 28500 | 0 | 2026-05-24
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5906846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126675030 | Approved | 28500 | 0 | 2025-09-23
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5910509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125507165 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5910655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126675924 | Approved | 28500 | 0 | 2025-01-24
UMARIA / MANPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/5913768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105898755 | Approved | 28500 | 0 | 2025-04-29
UMARIA / MANPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/615202 — Construction of IAY House -IAY REG. NO. MP2101807 | Approved | 28500 | 0 | 2017-02-06
UMARIA / MANPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740001006/IF/IAY/6376716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114173573 | Approved | 28500 | 0 | 2026-07-07
UMARIA / MANPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1740001006/RC/22012034445725 — Cc Road Nirman Kodara Kol Ke Ghar Se Kanjilal Ke Ghar Tak | Ongoing | 100000 | 0 | 2019-03-10
UMARIA / MANPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1740001006/RC/22012034445727 — Cc Road Nirman Dayaram Ke Ghar Se Kher Mai Ke Ghar Tak | Ongoing | 100000 | 0 | 2019-03-10
UMARIA / MANPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1740001006/RS/22012034487250 — shokhta nirman high scool ke hend pamp me | Ongoing | 15211.4 | 0 | 2020-10-07
UMARIA / MANPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1740001006/RS/22012034487251 — sokhta nirman high school parisar hendpamp me | Ongoing | 14805.29 | 0 | 2020-10-07
UMARIA / MANPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1740001006/RS/22012034487253 — sokhta nirman high school hostal parisar | Ongoing | 14283.77 | 0 | 2020-10-07
UMARIA / MANPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1740001006/RS/22012034596189 — SLWM WORK NADEP NIRMAN ramnaresh kol/chaita kol | Ongoing | 14006.51 | 0 | 2022-03-31
UMARIA / MANPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1740001006/RS/22012034605233 — SLWM WORK NADEP NIRMAN gaya kol/manja kol | Ongoing | 14006.51 | 0 | 2022-03-22
UMARIA / MANPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1740001006/RS/22012034605259 — SLWM WORK NADEP NIRMAN lalu/parsadi | Ongoing | 14006.51 | 0 | 2022-05-27
UMARIA / MANPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1740001006/RS/22012034605263 — SLWM WORK NADEP NIRMAN mithlesh /keshw gautam | Ongoing | 14006.51 | 0 | 2022-05-27
UMARIA / MANPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1740001006/RS/22012034606190 — SLWM WORK NADEP NIRMAN sukali kol | Ongoing | 14006.51 | 0 | 2022-05-27
UMARIA / MANPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1740001006/RS/22012034606229 — SLWM WORK NADEP NIRMAN sharda gautam /girja gautam | Ongoing | 14006.51 | 0 | 2022-05-27
UMARIA / MANPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1740001006/RS/22012035120036 — PULIYA NIRMAN RAMKRASHN MISHRA KE GHAR KE PICHHE | Ongoing | 46000 | 0 | 2023-10-12
UMARIA / MANPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740001006/WC/22012035212589 — जल गंगा संवर्धन तालाब विस्तारीकरण जाताखान तालाब | Ongoing | 289000 | 0 | 2024-07-09
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1740001006/WC/22012035278126 — Dugwell Recharge pit Indrabhan Mishra ke ghar pass Bharewa | Approved | 25899.46 | 0 | 2025-04-14
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1740001006/WC/22012035278128 — Dugwell Recharge pit Anand Kumar Mishra ke ghar pass Bharewa | Approved | 25899.46 | 0 | 2025-04-14
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1740001006/WC/22012035278134 — Dugwell Recharge pit Shivnarayan Mishra ke ghar pass Bharewa | Approved | 25899.46 | 0 | 2025-04-14
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1740001006/WC/22012035278137 — Dugwell Recharge pit Anuj Payasi ke ghar pass Bharewa | Approved | 25899.46 | 0 | 2025-04-14
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1740001006/WC/22012035278143 — Dugwell Recharge pit Prathmik shala Bharewa | Approved | 25899.46 | 0 | 2025-04-14
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1740001006/WC/22012035278149 — Dugwell Recharge pit Sateesh Bhatt ke ghar pass bharewa | Approved | 25899.46 | 0 | 2025-04-14
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740001006/WC/22012035278172 — Jal Ganga Sambardhan karya Malla talab Adiwashi Mohalla Bharewa | Approved | 0 | 0 | 2025-04-14
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740001006/WC/22012035278181 — Jal Ganga Sambardhan karya Rauhai talab Bharewa | Approved | 0 | 0 | 2025-04-14
UMARIA / MANPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740001006/WC/22012035278188 — Jal Ganga Sambardhan karya Bada talabPurvi bhag Bharewa | Approved | 0 | 0 | 2025-04-14