## Work List
Exported on: 2026-09-25 17:06:44
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MARDARI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
UMARIA / KARKELI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1740002072/DP/22012034423039 — Talab ke kinare me braksharopan nirman -Mardari | Ongoing | 342000 | 0 | 2018-07-30
UMARIA / KARKELI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740002072/IF/22012034455518 — CONTRUCTION OF KAPIL DHARA RAMMILAN S/O HEERA SINGH KE KHET ME | Ongoing | 200000 | 0 | 2019-02-28
UMARIA / KARKELI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740002072/IF/22012034464518 — कपिल धारा निर्माण कार्य दयाराम सिंह /दुर्पाल सिंह | Ongoing | 200000 | 0 | 2019-02-28
UMARIA / KARKELI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1740002072/IF/22012034464523 — कपिल धारा कूप निर्माण कार्य रत्नाभान सिंह /बारेलाल सिंह | Ongoing | 200000 | 0 | 2019-02-28
UMARIA / KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1740002072/IF/22012035630296 — Ek Bagiya maa ke Naam Omvati Bai GP Mardari | Approved | 0 | 0 | 2025-10-02
UMARIA / KARKELI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002072/IF/IAY/3761122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124802116 | Approved | 28500 | 0 | 2022-04-29
UMARIA / KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002072/IF/IAY/4867693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148477177 | Ongoing | 28500 | 0 | 2025-09-15
UMARIA / KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002072/IF/IAY/5174507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130614531 | Ongoing | 28500 | 1044 | 2025-08-31
UMARIA / KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002072/IF/IAY/5202888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142448210 | Ongoing | 28500 | 1044 | 2025-08-31
UMARIA / KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002072/IF/IAY/5258068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126492176 | Ongoing | 28500 | 0 | 2025-08-31
UMARIA / KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002072/IF/IAY/5258427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124801641 | Ongoing | 28500 | 0 | 2025-05-22
UMARIA / KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002072/IF/IAY/5299577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124796101 | Ongoing | 28500 | 0 | 2025-08-31
UMARIA / KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002072/IF/IAY/5505147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130614626 | Ongoing | 28500 | 0 | 2025-06-26
UMARIA / KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002072/IF/IAY/5628369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152092773 | Ongoing | 28500 | 6003 | 2025-08-31
UMARIA / KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002072/IF/IAY/5719411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130614560 | Ongoing | 28500 | 0 | 2025-08-31
UMARIA / KARKELI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1740002072/IF/IAY/5775957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129604264 | Ongoing | 28500 | 783 | 2026-03-03
UMARIA / KARKELI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1740002072/RS/22012034556934 — कचरा घर निर्माण कार्य सामुदायिक भवन के पास ग्राम पंचायत मरदरी में | Ongoing | 334480.49 | 0 | 2021-11-09
UMARIA / KARKELI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1740002072/WC/22012034482180 — RFR GHHORCHHATRA KHOLASHA NALA ME MARDARI 04 | Ongoing | 104827.72 | 0 | 2021-05-28
UMARIA / KARKELI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740002072/WC/22012035247163 — Earthen check dem Lamiya Bai ke khet pass mardari | Approved | 0 | 0 | 2025-01-24
UMARIA / KARKELI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1740002072/WC/22012035247180 — Earthen check dem Motelal Singh ke khet pass mardari | Approved | 0 | 0 | 2025-01-24