## Work List
Exported on: 2026-10-01 21:35:33
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: BAMANBARDI
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1741002004/AV/22012034389606 — Aanganwadhi (Bahawan Nirman chenpura) Bamanbardi | Completed | 312000 | 261358 | 2018-10-04 | 2020-09-03
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1741002004/AV/22012034389608 — Aanganwadhi (Bhawan Nirman Khermaliya) Bamanbadhi | Completed | 312000 | 133540 | 2018-10-06 | 2020-08-28
NEEMUCH / NEEMUCH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1741002004/dp/7 — व़क्षारोपण बामनबर्डी | Completed | 417000 | 3549.87 | 2008-08-27 | 2012-10-26
NEEMUCH / NEEMUCH | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1741002004/DP/9993627379 — Varksha Ropan Shantidham Parisar | Completed | 55000 | 6328 | 2014-07-31 | 2016-08-01
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741002004/IF/22012034350082 — Plantation (Rameshchand Pyarchand School avam Shantidham Parisar) Bamanbardi | Completed | 335000 | 281948 | 2017-06-14 | 2021-09-17
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741002004/IF/22012034355672 — Plantation Jamna shankar Sutar Sosayti Parisar | Completed | 335000 | 1032 | 2017-06-25 | 2019-07-21
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741002004/IF/22012034355698 — Plantation (Chunnilal Kishanlal Meghwal School Aur Shantidham parisar Khermaliya) Bamanbardi | Completed | 335000 | 77386 | 2017-06-29 | 2020-09-11
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741002004/IF/22012034355739 — Plantation (Ramprasad Bhanwarlala Gayari School Shamshan Parisar Chenpura) Bamanbadhi | Completed | 335000 | 82978 | 2017-06-25 | 2021-09-16
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741002004/IF/22012034379786 — Kapildhara With Khet Talab (Kawarshigh Rupsingh Rajput Chenpura Job No - 88) Bamanbadhi | Completed | 230000 | 106208 | 2017-10-30 | 2020-04-01
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741002004/IF/22012034379789 — Kapildhara With Khettalab (Kishanlal Buwan Sutar Jobcard No - 143) Bamanbardi | Completed | 230000 | 225720 | 2017-10-30 | 2019-05-21
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/IF/22012034406998 — Toilest Aawas Hitgrahi (Madansingh Bherusingh) Bamanbardi | Completed | 12000 | 8500 | 2018-09-01 | 2019-02-11
NEEMUCH / NEEMUCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1741002004/IF/22012034599522 — NIJI KHET (NANDAN FHALODI VIJAY SINGH SISODIYA S/O LAL SINGH) BAMANBARDI | Completed | 289800 | 221175 | 2020-09-22 | 2024-09-20
NEEMUCH / NEEMUCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone contour Bund for Individuals / Construction of Stone contour Bund for Individuals | Construction of Bund | 1741002004/IF/22012034711359 — Ston bund (Fatehlal Nanuram Maghwal) Gram Chainpura Bamanbadhi | Completed | 200000 | 199041 | 2021-05-02 | 2024-07-05
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1102773 — Construction of IAY House -IAY REG. NO. MP2477204 | Completed | 15480 | 15600 | 2017-08-04 | 2018-09-28
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1128916 — Construction of IAY House -IAY REG. NO. MP2293948 | Completed | 15480 | 15624 | 2017-10-05 | 2018-09-28
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1725189 — Construction of IAY House -IAY REG. NO. MP1631578 | Completed | 15660 | 15660 | 2018-09-14 | 2019-03-28
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1725198 — Construction of IAY House -IAY REG. NO. MP1726698 | Completed | 15660 | 15660 | 2018-09-12 | 2019-01-18
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1725347 — Construction of IAY House -IAY REG. NO. MP3214566 | Completed | 15660 | 15312 | 2018-09-12 | 2019-03-28
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1725642 — Construction of IAY House -IAY REG. NO. MP1453467 | Completed | 15660 | 14964 | 2018-06-07 | 2019-03-28
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1726097 — Construction of IAY House -IAY REG. NO. MP1726541 | Completed | 15660 | 15486 | 2018-06-07 | 2019-03-28
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1732420 — Construction of IAY House -IAY REG. NO. MP2865142 | Completed | 15660 | 15660 | 2018-06-07 | 2018-09-28
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1732464 — Construction of IAY House -IAY REG. NO. MP2874172 | Completed | 15660 | 15486 | 2018-06-07 | 2018-12-03
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1732909 — Construction of IAY House -IAY REG. NO. MP2875846 | Completed | 15660 | 15486 | 2018-06-07 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1732919 — Construction of IAY House -IAY REG. NO. MP2865263 | Completed | 15660 | 16530 | 2018-06-07 | 2018-11-06
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1733369 — Construction of IAY House -IAY REG. NO. MP3054677 | Completed | 15660 | 15486 | 2018-06-07 | 2019-04-01
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1734256 — Construction of IAY House -IAY REG. NO. MP3214997 | Completed | 15660 | 15138 | 2018-06-07 | 2018-12-03
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1734331 — Construction of IAY House -IAY REG. NO. MP3229444 | Completed | 15660 | 15660 | 2018-06-07 | 2018-11-13
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1734399 — Construction of IAY House -IAY REG. NO. MP3241454 | Completed | 15660 | 15486 | 2018-06-07 | 2019-03-13
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1734400 — Construction of IAY House -IAY REG. NO. MP3241469 | Completed | 15660 | 15660 | 2018-06-07 | 2019-01-03
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1734457 — Construction of IAY House -IAY REG. NO. MP3250150 | Completed | 15660 | 15312 | 2018-06-07 | 2018-11-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1734748 — Construction of IAY House -IAY REG. NO. MP3274702 | Completed | 15660 | 15486 | 2018-06-07 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1737447 — Construction of IAY House -IAY REG. NO. MP3832741 | Completed | 15660 | 15486 | 2018-06-07 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1763774 — Construction of IAY House -IAY REG. NO. MP2879124 | Completed | 15660 | 15660 | 2018-06-07 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1764963 — Construction of IAY House -IAY REG. NO. MP3241051 | Completed | 15660 | 15486 | 2018-06-07 | 2018-12-03
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1768402 — Construction of IAY House -IAY REG. NO. MP3835882 | Completed | 15660 | 15486 | 2018-06-07 | 2019-02-05
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1811466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2886730 | Completed | 15660 | 15138 | 2018-06-07 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1864572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1557808 | Completed | 15660 | 15138 | 2018-08-10 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1864609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1541848 | Completed | 15660 | 15660 | 2018-08-10 | 2019-03-28
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1864626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1533765 | Completed | 15660 | 15660 | 2018-08-10 | 2019-01-21
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1865215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1713392 | Completed | 15660 | 15660 | 2018-10-10 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1867282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2814359 | Completed | 15660 | 15486 | 2018-08-10 | 2019-04-01
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1867357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2848334 | Completed | 15660 | 15138 | 2018-08-10 | 2019-03-28
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1867358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2848339 | Completed | 15660 | 15486 | 2018-08-10 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1867902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2847381 | Completed | 15660 | 15312 | 2018-08-10 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1867955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2866369 | Completed | 15660 | 15138 | 2018-08-10 | 2019-04-01
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1867958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2866923 | Completed | 15660 | 15312 | 2018-08-10 | 2019-01-05
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1868149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2947638 | Completed | 17100 | 5220 | 2018-10-11 | 2023-09-06
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1868892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3232730 | Completed | 15660 | 15660 | 2018-08-10 | 2019-01-21
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1868923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3241497 | Completed | 15660 | 15138 | 2018-08-10 | 2019-01-03
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1869019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3277326 | Completed | 15660 | 14964 | 2018-09-27 | 2019-01-05
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1869056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3294820 | Completed | 15660 | 15486 | 2018-08-10 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1870010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3853932 | Completed | 15660 | 15660 | 2018-08-10 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1870271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3962687 | Completed | 15660 | 15312 | 2018-10-11 | 2019-01-03
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1870312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3976603 | Completed | 15660 | 15660 | 2018-10-10 | 2019-04-01
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1872382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4668535 | Completed | 15660 | 15486 | 2018-08-10 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1875933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1725730 | Completed | 15660 | 15312 | 2018-08-10 | 2019-01-03
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1880977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4719424 | Completed | 15660 | 15312 | 2018-10-10 | 2019-01-03
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1881599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5291751 | Completed | 15660 | 15486 | 2018-08-10 | 2019-03-12
NEEMUCH / NEEMUCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/1919444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2866355 | Completed | 15660 | 15660 | 2018-08-10 | 2019-03-28
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3835191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125520023 | Completed | 23490 | 2448 | 2022-11-29 | 2025-08-13
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3850769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125779306 | Completed | 18360 | 17544 | 2022-07-01 | 2023-09-18
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3851794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126773138 | Completed | 18360 | 17357 | 2022-07-28 | 2023-09-18
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3853399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130524290 | Completed | 18360 | 17646 | 2022-08-10 | 2023-09-15
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3853400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130524344 | Completed | 18360 | 18190 | 2022-07-28 | 2024-01-23
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3856728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126827297 | Completed | 18360 | 17382 | 2022-11-29 | 2023-12-06
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3856771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126829821 | Completed | 18360 | 17748 | 2022-07-28 | 2023-08-16
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3869242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145134377 | Completed | 18360 | 16354 | 2022-11-26 | 2024-01-23
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3870675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140346035 | Completed | 18360 | 2679 | 2022-11-29 | 2025-01-10
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3870676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140346057 | Completed | 18360 | 18360 | 2022-07-28 | 2023-09-18
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3876108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141517783 | Completed | 18360 | 17034 | 2022-07-28 | 2023-09-18
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3876111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141518102 | Completed | 18360 | 17238 | 2022-12-22 | 2023-11-21
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3916934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127910983 | Completed | 18360 | 18224 | 2022-07-28 | 2023-09-18
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3916945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127911384 | Completed | 18360 | 18258 | 2022-07-28 | 2023-06-18
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3916948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127911809 | Completed | 18360 | 18122 | 2022-07-28 | 2023-09-18
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3916954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127912292 | Completed | 18360 | 11526 | 2022-07-28 | 2024-11-05
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/3916998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127916393 | Completed | 18360 | 16745 | 2022-07-28 | 2024-01-23
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4017693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127912722 | Completed | 18360 | 10608 | 2022-07-28 | 2024-01-06
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4017738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127923592 | Completed | 18360 | 18139 | 2022-11-29 | 2024-01-23
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4106324 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141517789 | Completed | 18360 | 17698 | 2022-07-28 | 2024-01-18
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4164815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126769586 | Completed | 18360 | 18037 | 2022-07-28 | 2023-06-21
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4166074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126287808 | Completed | 18360 | 17935 | 2022-11-29 | 2024-01-23
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4268817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127915973 | Completed | 18360 | 5423 | 2022-11-29 | 2024-11-05
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4268818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127916831 | Completed | 18360 | 10846 | 2022-11-29 | 2024-11-05
NEEMUCH / NEEMUCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/428041 — Construction of IAY House -IAY REG. NO. MP1381294 | Completed | 15030 | 1366 | 2017-02-02 | 2019-01-01
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4293641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141518083 | Completed | 18360 | 17004 | 2022-11-29 | 2023-12-21
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4352333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126819464 | Completed | 18360 | 1224 | 2022-11-29 | 2025-01-18
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4355276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141517035 | Completed | 18360 | 11713 | 2023-03-14 | 2024-11-05
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4371495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140346169 | Completed | 18360 | 5100 | 2023-03-14 | 2024-11-05
NEEMUCH / NEEMUCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4387774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128060514 | Completed | 18360 | 15810 | 2023-03-14 | 2024-05-15
NEEMUCH / NEEMUCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/442960 — Construction of IAY House -IAY REG. NO. MP1489620 | Completed | 15030 | 16316 | 2017-02-02 | 2018-09-28
NEEMUCH / NEEMUCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/446400 — Construction of IAY House -IAY REG. NO. MP1522961 | Completed | 15030 | 15057 | 2017-02-02 | 2018-08-29
NEEMUCH / NEEMUCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4623734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126815537 | Completed | 23490 | 21294 | 2024-12-12 | 2025-05-19
NEEMUCH / NEEMUCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4646867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140346841 | Completed | 23490 | 21294 | 2024-12-12 | 2025-07-19
NEEMUCH / NEEMUCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4827132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126817978 | Completed | 23490 | 21294 | 2024-12-12 | 2025-07-19
NEEMUCH / NEEMUCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4828125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126308426 | Completed | 23490 | 21294 | 2024-12-12 | 2025-07-19
NEEMUCH / NEEMUCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4829005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127925955 | Completed | 23490 | 15813 | 2024-12-12 | 2025-05-21
NEEMUCH / NEEMUCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4832363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141516559 | Completed | 23490 | 16065 | 2025-02-11 | 2026-02-03
NEEMUCH / NEEMUCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4832364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141517804 | Completed | 23490 | 15813 | 2024-12-12 | 2025-05-21
NEEMUCH / NEEMUCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/4849867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130524330 | Completed | 23490 | 21420 | 2024-12-31 | 2025-07-19
NEEMUCH / NEEMUCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/503141 — Construction of IAY House -IAY REG. NO. MP2293902 | Completed | 15030 | 15946 | 2017-02-02 | 2018-09-18
NEEMUCH / NEEMUCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/503252 — Construction of IAY House -IAY REG. NO. MP2295580 | Completed | 15030 | 15624 | 2017-02-02 | 2018-12-23
NEEMUCH / NEEMUCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/503674 — Construction of IAY House -IAY REG. NO. MP2302250 | Completed | 15030 | 167 | 2017-02-02 | 2019-01-06
NEEMUCH / NEEMUCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/509366 — Construction of IAY House -IAY REG. NO. MP2372207 | Completed | 15030 | 16232 | 2017-02-02 | 2018-09-18
NEEMUCH / NEEMUCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/518707 — Construction of IAY House -IAY REG. NO. MP2523007 | Completed | 15030 | 15516 | 2017-02-02 | 2018-05-29
NEEMUCH / NEEMUCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/59390 — Construction of IAY House -IAY REG. NO. MP-41-002-004-001/114 | Completed | 14310 | 13854 | 2016-02-21 | 2017-08-18
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/639526 — Construction of IAY House -IAY REG. NO. MP2998687 | Completed | 15030 | 15624 | 2017-08-04 | 2018-11-06
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/812478 — Construction of IAY House -IAY REG. NO. MP1589735 | Completed | 15480 | 15636 | 2017-10-05 | 2018-12-19
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/815426 — Construction of IAY House -IAY REG. NO. MP1816322 | Completed | 15480 | 15624 | 2017-10-05 | 2018-10-29
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/820719 — Construction of IAY House -IAY REG. NO. MP2294068 | Completed | 15480 | 14694 | 2017-08-04 | 2018-11-12
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/820720 — Construction of IAY House -IAY REG. NO. MP2294174 | Completed | 15480 | 15474 | 2017-08-04 | 2019-01-18
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/821728 — Construction of IAY House -IAY REG. NO. MP2394297 | Completed | 15480 | 15600 | 2017-10-05 | 2018-09-28
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/824475 — Construction of IAY House -IAY REG. NO. MP2814441 | Completed | 15480 | 15612 | 2017-10-05 | 2018-12-03
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/824693 — Construction of IAY House -IAY REG. NO. MP2848356 | Completed | 15480 | 15600 | 2017-10-05 | 2018-09-28
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/825179 — Construction of IAY House -IAY REG. NO. MP2945882 | Completed | 15480 | 15648 | 2018-02-25 | 2018-12-03
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/843452 — Construction of IAY House -IAY REG. NO. MP1403845 | Completed | 15480 | 15624 | 2017-10-05 | 2018-11-06
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/906464 — Construction of IAY House -IAY REG. NO. MP2226328 | Completed | 15480 | 15624 | 2017-10-05 | 2018-09-28
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/911336 — Construction of IAY House -IAY REG. NO. MP2294106 | Completed | 15480 | 15612 | 2017-10-05 | 2018-08-29
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/912093 — Construction of IAY House -IAY REG. NO. MP2305066 | Completed | 15480 | 15600 | 2017-08-04 | 2018-08-29
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/915585 — Construction of IAY House -IAY REG. NO. MP2356297 | Completed | 15480 | 15636 | 2017-10-05 | 2018-12-03
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/916586 — Construction of IAY House -IAY REG. NO. MP2370189 | Completed | 15480 | 15648 | 2017-10-05 | 2018-08-16
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/916622 — Construction of IAY House -IAY REG. NO. MP2370683 | Completed | 15480 | 15636 | 2017-10-05 | 2018-08-29
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/919987 — Construction of IAY House -IAY REG. NO. MP2420832 | Completed | 15480 | 15600 | 2017-10-05 | 2018-09-28
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/946264 — Construction of IAY House -IAY REG. NO. MP2947761 | Completed | 15480 | 15648 | 2017-10-05 | 2018-11-12
NEEMUCH / NEEMUCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741002004/IF/IAY/951746 — Construction of IAY House -IAY REG. NO. MP3088819 | Completed | 15480 | 15308 | 2017-08-04 | 2018-07-02
NEEMUCH / NEEMUCH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1741002004/LD/22012034240433 — SHANTIDHAM VIKAS KARY(SUKHE PATHARO KI SURAKSHA DIWAR) BAMANBARDI | Completed | 989000 | 465366 | 2015-12-10 | 2017-05-25
NEEMUCH / NEEMUCH | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1741002004/LD/22012034301721 — Shantidham (Muktidham vikas Shed Nirman chenpura khadan) bamanbardi | Completed | 180000 | 173544.93 | 2017-03-01 | 2018-02-13
NEEMUCH / NEEMUCH | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1741002004/LD/22012034301723 — Shantidham (Muktidham vikas Shed Nirman KHERMALIYA) bamanbardi | Completed | 180000 | 174910.93 | 2017-02-14 | 2018-02-13
NEEMUCH / NEEMUCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1741002004/LD/22012034526436 — Nutri- garden primary School bamanbadhi | Completed | 5000 | 4940 | 2020-11-06 | 2020-12-06
NEEMUCH / NEEMUCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1741002004/LD/22012034532112 — Sukhe Patharo ki surkha diwar (Shantidham parisar Gram Khermaliya) | Completed | 317000 | 255574 | 2020-12-09 | 2021-10-08
NEEMUCH / NEEMUCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1741002004/LD/22012034542441 — Sukhe patharo ki surkha diwar (Gram Chainpura khadan Shantidham Parisar) | Completed | 544000 | 568350 | 2021-03-14 | 2022-02-01
NEEMUCH / NEEMUCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1741002004/LD/3799396746 — Drys lapidary security wall | Completed | 344000 | 343196 | 2013-06-20 | 2014-09-17
NEEMUCH / NEEMUCH | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1741002004/PG/9425891613 — KHEL MEDAN (GRAMIN KRIDANGAN 100*100) BAMANBARDI | Completed | 353000 | 297120 | 2016-12-23 | 2018-07-26
NEEMUCH / NEEMUCH | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1741002004/PG/9425895177 — KHEL MEDAN (GRAMIN KRIDANGAN KHERMALIYA) BAMANBARDI | Completed | 353000 | 292591 | 2017-03-19 | 2019-07-17
NEEMUCH / NEEMUCH | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1741002004/PG/9425895178 — KHEL MEDAN (GRAMIN KRIDANGAN CHENPURA 100*100) BAMANBARDI | Completed | 353000 | 308203 | 2017-03-19 | 2019-01-08
NEEMUCH / NEEMUCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034154864 — सी.सी. रोड पापु बाव्जी से गायरी मोह्ळ्ले तक | Completed | 100700 | 99380 | 2012-12-19 | 2013-02-07
NEEMUCH / NEEMUCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034156649 — सी.सी. रोड किशनसिंह सौधिया के मकान से मंदिर तक | Completed | 100700 | 99380 | 2013-02-04 | 2013-03-30
NEEMUCH / NEEMUCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034178466 — CC Road Hanuman mandir se Eswarshing ke makan tk | Completed | 167000 | 164134 | 2013-08-15 | 2013-12-24
NEEMUCH / NEEMUCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034202413 — CC ROAD PARPADA TANKI SE MULCHAND K MAKAN KI OR | Completed | 82500 | 82494 | 2014-02-06 | 2014-09-17
NEEMUCH / NEEMUCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034202417 — CC ROAD HOLI CHOWK SE AJAYPAL CHORAHE TAK | Completed | 55700 | 55288 | 2014-02-03 | 2014-09-17
NEEMUCH / NEEMUCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741002004/RC/22012034202488 — SUDUR SADAK BAMANBARDI SE KHERMALIYA BAMANBARDI | Completed | 1463000 | 906883.28 | 2014-02-06 | 2016-07-18
NEEMUCH / NEEMUCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034202508 — CC ROAD MATA JI MANDIR SE BHARAT SINH KE MAKAN TAK | Completed | 33000 | 32910 | 2014-02-06 | 2014-09-17
NEEMUCH / NEEMUCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034210897 — CC ROAD LAXMINARAYAN KE GAR SE JAGDISH KE GAR TAK | Completed | 117500 | 116804 | 2014-03-03 | 2015-01-08
NEEMUCH / NEEMUCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034210907 — CC ROAD BHAGWAN LAL KE GAR SE GHEESALAL KE GAR TA | Completed | 39000 | 37107 | 2014-03-03 | 2016-06-24
NEEMUCH / NEEMUCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034224837 — CC Road Radhesyam Ke makan se Shantilal Ke makan t | Completed | 92800 | 90436 | 2014-07-17 | 2016-06-23
NEEMUCH / NEEMUCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1741002004/RC/22012034296842 — SUDUR SADAK (BAMANBARDHI SE CHENPURA MARG 1 KM TAK) BAMANBARDI | Completed | 1401000 | 160272 | 2016-01-20 | 2017-02-20
NEEMUCH / NEEMUCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1741002004/RC/22012034317748 — Sudur Sadak (Chainpura Khadan se Gasundi Bam- Bisalwas khurd raod Ki or 0 to 0.80 KM Tak) Bamanbardi | Completed | 981000 | 934550 | 2016-12-16 | 2019-03-28
NEEMUCH / NEEMUCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034329259 — CC ROAD SAH NALI NIRMAN (DEVILAL SUTHAR KE MAKAN SE MURARILAL KE MAKAN TAK DPR -01 ZP) BAMANBARDI | Completed | 265500 | 132036 | 2017-03-03 | 2018-04-18
NEEMUCH / NEEMUCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034347848 — CC Road Gram Khermaliya (Udayshingh ke makan wali gali) Vidhayak nidhi | Completed | 115800 | 40248 | 2017-08-04 | 2018-07-14
NEEMUCH / NEEMUCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1741002004/RC/22012034347855 — Sudur Gram Sadak Yojana (Gram Bamanbadhi se Chainpura Last work (0 se 2.00km) Bamanbardi | Completed | 2224000 | 1968636 | 2017-10-25 | 2019-01-08
NEEMUCH / NEEMUCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034364704 — CC Raod Holichok Bamanbadhi | Completed | 100000 | 60888 | 2017-10-25 | 2018-03-27
NEEMUCH / NEEMUCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034364707 — CC Raod Sarwan Suthar ke gar se Gowardhan suthar ke gar tk Bamanbadhi | Completed | 100000 | 93912 | 2017-10-25 | 2018-07-14
NEEMUCH / NEEMUCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034366724 — CC ROAD (MATAJI MANDIR SE JAGDISH SUTHAR KE MAKAN TAK DPR - 11) BAMANBARDI | Completed | 14400 | 10320 | 2017-11-29 | 2018-09-07
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034386809 — CC Road (Jagdish Gayari ke Gar se Gopal Gayari ke gar tak DPR - 05) Bamanbadhi | Completed | 35408 | 30276 | 2018-08-23 | 2019-01-18
NEEMUCH / NEEMUCH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034386810 — CC Road (Syamlal suthar ke Gar se Laxminarayan Gayri ke gar tak DPR - 04) Bamanbadhi | Completed | 22125 | 21120 | 2019-05-28 | 2019-06-17
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034386815 — CC Road (Ramchandra Teli ke makan se Gopla Brahman ke makan tak DPR - 12) Bamanbadhi | Completed | 39825 | 36540 | 2018-08-02 | 2019-01-18
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034394534 — CC Road Vidhayak Nidhi (Ramchand Netaji ke makan se Piche wali Gali) Bamanbdhi | Completed | 37500 | 34836 | 2018-10-04 | 2019-07-17
NEEMUCH / NEEMUCH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034473256 — CC Road Gram Chainpura (Gowardhan ke makan se rodilal Meghwal ke makan tk) GP Bamanbadhi | Completed | 60500 | 52800 | 2019-09-13 | 2020-09-19
NEEMUCH / NEEMUCH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1741002004/RC/22012034504111 — Sudur sadak khermaliya se shanti dham tak | Completed | 245714.46 | 160416 | 2019-11-21 | 2021-04-27
NEEMUCH / NEEMUCH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034515950 — CC Road Narayansingh Rajput ke makan wali gali Gram Chainpura | Completed | 21000 | 13728 | 2020-02-25 | 2020-03-25
NEEMUCH / NEEMUCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034530543 — CC Road Gram Bamanbadhi (Ghisalal Suthar ke makan se Kawarlal Suthar ke makan ki or) | Completed | 68300 | 67260 | 2020-08-14 | 2021-03-21
NEEMUCH / NEEMUCH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034652915 — CC Road Gram Bamanbadhi main Road Se Devnarayan mandir ki or | Completed | 44000 | 38443 | 2023-10-06 | 2025-02-24
NEEMUCH / NEEMUCH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034683153 — Nala nirman Gram Chainpura me mainroad par GP- Bamanbadhi | Completed | 424297.48 | 286053.87 | 2024-06-14 | 2025-08-05
NEEMUCH / NEEMUCH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034819475 — CC Road Nirman Gram Chainpura Gayari Mohhlla me Bamanbadi | Completed | 35000 | 34999.8 | 2024-08-24 | 2025-02-24
NEEMUCH / NEEMUCH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741002004/RC/22012034825849 — CC Road Ashok heeralal ke makan se basantilal sutar ke makan tk | Completed | 95000 | 81405 | 2024-10-23 | 2026-01-10
NEEMUCH / NEEMUCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034288492 — SBM (GOPAL CHATARHUJ) BAMANARDI | Completed | 3180 | 3180 | 2015-10-14 | 2016-06-21
NEEMUCH / NEEMUCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034288495 — SBM (GOPAL RAMLAL) BAMANARDI | Completed | 3180 | 3180 | 2015-10-14 | 2016-06-21
NEEMUCH / NEEMUCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034288496 — SBM (RAMSINGH HUR SINGH) BAMANARDI | Completed | 3180 | 3180 | 2015-10-14 | 2016-06-21
NEEMUCH / NEEMUCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034288498 — SBM (SOHANLAL LADURAM) BAMANARDI | Completed | 3180 | 3180 | 2015-10-14 | 2016-06-21
NEEMUCH / NEEMUCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034288499 — SBM (BANSHILAL HAGCHAND) BAMANARDI | Completed | 3180 | 3180 | 2015-10-14 | 2016-06-21
NEEMUCH / NEEMUCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034288500 — SBM (BAULAL KISHANLAL) BAMANARDI | Completed | 3180 | 3180 | 2015-10-14 | 2016-06-21
NEEMUCH / NEEMUCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034289234 — SBM Lalshingh Babulal Bamanbadhi | Completed | 3180 | 3180 | 2015-10-19 | 2016-06-21
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034408243 — Toilet- Avvas Hitgrahi Sampatbai | Completed | 12000 | 8500 | 2018-09-07 | 2019-02-11
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034408246 — tollet-Aawas hitgrahi pappu shankarlal | Completed | 12000 | 8500 | 2018-09-01 | 2019-08-24
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034408252 — tollet-Aawas hitgrahi hagamibai chaganlal | Completed | 12000 | 8500 | 2018-09-07 | 2019-02-18
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034408254 — tollet-aawas hitgrahi ramsingh amar banjara | Completed | 12000 | 8500 | 2018-09-07 | 2019-02-18
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034408259 — tollet-Aawas hitgrahi mangibai biharilal | Completed | 12000 | 8500 | 2018-09-07 | 2019-02-18
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034408261 — tollet-awas hitgrahi mohanbai nandlal | Completed | 12000 | 8500 | 2018-09-01 | 2019-02-18
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034408263 — tollet-Aawas hitgrahi balvant modiram | Completed | 12000 | 8500 | 2018-09-07 | 2019-08-24
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034408265 — tollet-aawas hitgrahi bhonibai gokul | Completed | 12000 | 8500 | 2018-09-07 | 2019-02-18
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034408266 — tollet-aaws hitgrahi shyamlal hajarilal | Completed | 12000 | 8500 | 2018-09-01 | 2019-02-18
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034408268 — Aawas-hitgrahi mukesh mangila | Completed | 12000 | 8500 | 2018-09-01 | 2019-08-24
NEEMUCH / NEEMUCH | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741002004/RS/22012034408270 — tollet -aawas hitgrahi gangaram bhagwan | Completed | 12000 | 8500 | 2018-09-01 | 2019-08-24
NEEMUCH / NEEMUCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1741002004/RS/22012034496753 — samudayik swachata parisar bamanbardi | Completed | 43700 | 38760 | 2020-11-18 | 2023-03-20
NEEMUCH / NEEMUCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1741002004/RS/22012034564275 — SLWM/CTR SAMUDAIK SOAK PIT NIRMAN 01 BAMANNARDI | Completed | 14467.3 | 10422 | 2021-09-17 | 2024-01-15
NEEMUCH / NEEMUCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1741002004/RS/22012034564280 — SLWM/CTR SAMUDAIK SOAK PIT NIRMAN 03 BAMANNARDI | Completed | 14467.3 | 9114 | 2021-09-17 | 2024-03-28
NEEMUCH / NEEMUCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1741002004/RS/22012034564282 — SLWM/CTR SAMUDAIK SOAK PIT NIRMAN 04 BAMANNARDI | Completed | 14467.3 | 4716 | 2021-09-17 | 2024-04-09
NEEMUCH / NEEMUCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1741002004/RS/22012034564284 — SLWM/CTR SAMUDAIK SOAK PIT NIRMAN 05 BAMANNARDI | Completed | 14467.3 | 1158 | 2021-09-17 | 2024-08-10
NEEMUCH / NEEMUCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1741002004/RS/22012034564285 — SLWM/CTR SAMUDAIK SOAK PIT NIRMAN 06 BAMANNARDI | Completed | 14467.3 | 2316 | 2021-09-17 | 2024-11-15
NEEMUCH / NEEMUCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1741002004/RS/22012034564288 — SLWM/CTR SAMUDAIK SOAK PIT NIRMAN 07 BAMANNARDI | Completed | 14467.3 | 1158 | 2021-09-17 | 2024-07-30
NEEMUCH / NEEMUCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1741002004/RS/22012034564291 — SLWM/CTR SAMUDAIK SOAK PIT NIRMAN 08 BAMANNARDI | Completed | 14467.3 | 7894 | 2021-09-17 | 2024-08-06
NEEMUCH / NEEMUCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1741002004/RS/22012034564293 — SLWM/CTR SAMUDAIK SOAK PIT NIRMAN 09 BAMANNARDI | Completed | 14467.3 | 2316 | 2021-09-17 | 2024-08-10
NEEMUCH / NEEMUCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1741002004/RS/22012034564295 — SLWM/CTR SAMUDAIK SOAK PIT NIRMAN 10 BAMANNARDI | Completed | 14467.3 | 4716 | 2021-09-17 | 2024-04-09
NEEMUCH / NEEMUCH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1741002004/RS/22012034637832 — Samudayik Swachta parisar Gram Khermaliya GP- Bamanbadhi | Completed | 43700 | 44268 | 2022-04-02 | 2024-01-09
NEEMUCH / NEEMUCH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1741002004/WC/22012034390113 — Talai Nirman (Talai NirmanChainpura) Bamanbadhi | Completed | 196000 | 178644 | 2018-10-06 | 2019-12-24
NEEMUCH / NEEMUCH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1741002004/WC/22012034390131 — Talai Nirman (Talai Nirman Khermaliya) Bamanbadhi | Completed | 196000 | 177588 | 2018-10-06 | 2019-12-24
NEEMUCH / NEEMUCH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1741002004/WC/22012034423127 — Nala Nirman (School se Kanhiyalal Mulchand Suthar ke makan ki or) Bamanbadhi | Completed | 1420000 | 996770 | 2018-10-04 | 2019-10-10
NEEMUCH / NEEMUCH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741002004/WC/22012034444614 — Parkoleshan tank bhom me Bamanbardi | Completed | 442888.75 | 399484 | 2019-03-10 | 2020-11-19
NEEMUCH / NEEMUCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1741002004/WC/22012034477492 — Nala nirman Gram Khermaliya Magwal mohalla (Shamshan Raste par) Bamanbadhi | Completed | 1037017.21 | 515664 | 2019-08-07 | 2020-11-19
NEEMUCH / NEEMUCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1741002004/WC/22012034479899 — CPT Nimran Gram Khermaliya shamshan parisar me 1 hac. Bamanbadhi | Completed | 47478.94 | 34848 | 2019-08-15 | 2019-10-14
NEEMUCH / NEEMUCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1741002004/WC/22012034479901 — CPT Bamanbadhi Bhom talab ke piche Gram Bamanbadhi GP:- Bamanbadhi | Completed | 94957.87 | 80784 | 2019-08-15 | 2020-11-18
NEEMUCH / NEEMUCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Masonry/CC Anicut for Community / Repair and Maintenance of Masonry/CC Check Dam for Community | Repair & maint of Water Harvesting Structures | 1741002004/WC/22012034479903 — CPT Work Gram Chainpura Maghwalo ka shamshan parisar Bamanbadhi | Completed | 23739.46 | 13728 | 2019-08-14 | 2019-10-14
NEEMUCH / NEEMUCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741002004/WC/22012034490396 — Parcolathion tank School parisar ke piche Bamanbadhi | Completed | 486392.83 | 326096 | 2019-12-05 | 2020-11-19
NEEMUCH / NEEMUCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1741002004/WC/22012034496078 — Nala nirman Kailash Sutar ke makan se Sarkari Tubwell tk Bamanbdhi | Completed | 771795.23 | 507740 | 2019-10-13 | 2024-12-20
NEEMUCH / NEEMUCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1741002004/WC/22012034496080 — Nala nimran Kishanshingh Soindiya ke makan se shantilal meena ke makan tk Khermaliya | Completed | 779230.77 | 406181.2 | 2019-10-13 | 2020-08-28
NEEMUCH / NEEMUCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1741002004/WC/22012034515936 — NALA NIRMAN DEVNARAYAN MANDIR WALI GALI BAMANBARDI | Completed | 602180.22 | 438426 | 2020-03-17 | 2021-04-27
NEEMUCH / NEEMUCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1741002004/WC/22012034640922 — CTR LOOSE BOULDER CHEK DEM NIRMAN MATA JI MANDIR WALE NALE PAR GP BAMANBARDI | Completed | 25273.34 | 11544 | 2021-05-02 | 2022-02-26
NEEMUCH / NEEMUCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1741002004/WC/22012034640926 — CTR LOOSE BOULDER CHEK DEM NIRMAN MATA JI MANDIR WALE NALE PAR CHENPURA 01 GP BAMANBARDI | Completed | 25987.86 | 17370 | 2021-05-02 | 2022-02-26
NEEMUCH / NEEMUCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741002004/WC/22012034692990 — CTR Percolation Tank Chainpura GP Bamanbadhi | Completed | 780670.38 | 254693 | 2021-12-03 | 2022-12-15
NEEMUCH / NEEMUCH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1741002004/WC/22012034692992 — CTR Percolathion Tank Bamanbadhi | Completed | 381481.77 | 242493 | 2023-11-24 | 2025-04-26
NEEMUCH / NEEMUCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1741002004/WC/22012034763193 — CTR Roof Water Harvesting Prathmic Vidhalay Bhawan Bamanbadhi | Completed | 18000 | 1711 | 2021-09-23 | 2024-04-13
NEEMUCH / NEEMUCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1741002004/WC/22012034763209 — CTR Roof Water Harvesting Prathmic Vidhalay Bhawan Chainpura Bamanbahi | Completed | 18000 | 2316 | 2021-09-23 | 2024-04-13
NEEMUCH / NEEMUCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1741002004/WC/22012034987598 — Amrit Sarovar (Talab nirman Chainpura khadan) Bamanbadhi | Completed | 345000 | 343477 | 2022-10-01 | 2025-04-29
NEEMUCH / NEEMUCH | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1741002004/WC/22012035140575 — Nala nirman Gisalal ke makan se sarlai marg | Completed | 34000 | 32960 | 2024-03-16 | 2025-04-11
NEEMUCH / NEEMUCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1741002004/WH/19959698 — RENOVATION (TALAB JIRNODWAR KARY CHENPURA) BAMANBARDI | Completed | 72000 | 65184 | 2019-08-27 | 2019-10-14
NEEMUCH / NEEMUCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1741002004/WH/22012034452759 — R) Stopdam Marramt Shamshan ke pas Chainpura Block Bamanbadhi | Completed | 244627.81 | 96432 | 2022-04-02 | 2022-12-15
NEEMUCH / NEEMUCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1741002004/WH/22012034452760 — R) Stopdam Marramat Khayalliya Puliya ke pas Bamanbadhi | Completed | 278057.66 | 132568 | 2022-04-02 | 2025-08-05
NEEMUCH / NEEMUCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741/IF/22012034495035 — NDI BHUMI PER FALOD I MANORAMA KALISHCHANDRA BAMANBARDI | Completed | 118250 | 56774 | 2019-08-07 | 2025-01-08