## Work List
Exported on: 2026-10-13 21:38:14
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: PALDA
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1741003049/AV/22012034368032 — शांतिधाम टीन शेड निर्माण पालडा | Completed | 180000 | 174687.84 | 2017-08-30 | 2018-07-16
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1741003049/AV/22012034390817 — आगनवाडी भवन निर्माण कार्य पिपलियासिंघाडीया पालडा | Completed | 312000 | 179395.72 | 2018-11-30 | 2020-09-08
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1741003049/AV/22012034390818 — आगनवाडी भवन निर्माण कार्य पालडा | Completed | 312000 | 284826.47 | 2018-11-30 | 2020-06-03
NEEMUCH / MANASA | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1741003049/DP/9993627773 — वुक्ष्‍ाा रोपण कार्य श्‍मशान घाट ts.no. 124 पालडा | Completed | 305000 | 49038 | 2014-08-16 | 2015-10-18
NEEMUCH / MANASA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1741003049/DP/TS.no 382 — व़क्षारोपण कार्य TS no 382 कराडीया (पालडा) | Completed | 338000 | 23260 | 2010-07-20 | 2015-03-02
NEEMUCH / MANASA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1741003049/DP/TS.no 383 — व़क्षारोपण कार्य TS no 383 कराडीया (पालडा) | Completed | 338000 | 24052 | 2010-07-25 | 2015-03-02
NEEMUCH / MANASA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1741003049/DP/TS.no 384 — व़क्षारोपण कार्य TS no 384 कराडीया (पालडा) | Completed | 338000 | 28416 | 2010-07-20 | 2015-03-02
NEEMUCH / MANASA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1741003049/DP/TS.no 385 — व़क्षारोपण कार्य TS no 385 कराडीया (पालडा) | Completed | 338000 | 27332 | 2010-07-25 | 2015-03-02
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003049/FP/22012034314612 — नाला निर्माण कार्य पंचायत भवन से नाले की ओर टीएस 472 | Completed | 835000 | 678521.04 | 2017-06-06 | 2019-08-16
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003049/FP/22012034360139 — पुलिया निर्माण कार्य कराडिया टीएस 40 पालडा | Completed | 446000 | 434598.96 | 2017-10-31 | 2018-07-13
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003049/FP/22012034360587 — पुलिया निर्माण कार्य सिंघाडिया पिपल्‍या से डोरियाखेडी टीएस 1276 सिंघाडियापिपल्‍या | Completed | 993000 | 959154.1 | 2018-02-04 | 2018-09-24
NEEMUCH / MANASA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1741003049/FP/22012034369656 — DRAINAIGE CHAINEL NIRMAN ( SCHOOL KAI SAMNEY ) PIPLIYASINGHADIYA | Completed | 623000 | 407695.56 | 2021-03-11 | 2025-03-20
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1741003049/FP/22012034628266 — DRAINAIGE CHAINEL NALI NIRMAN (CHARBHUJA MANDIR SE SCHOOL KI OR DORIYAKHEDI) PALDA | Completed | 43000 | 47274 | 2022-03-22 | 2025-06-25
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/22012034361203 — VRKSHA ROPAN MIDDLE SCHOOL PARISAR MAIDAN PIPLYASINGHADIYA PALADA | Completed | 335000 | 8160 | 2017-07-05 | 2019-09-18
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/22012034361205 — VRKSHA ROPAN SADAK KINARAY EK TARAF ROAD PER PIPLIYA SINGHADIYA PALADA | Completed | 335000 | 5160 | 2017-07-05 | 2019-09-18
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/22012034366249 — VRKSHA ROPAN NAHAR KINARAY PIPLIYASINGHADIYA PALADA JEEVAN RAMESH | Completed | 335000 | 9880 | 2017-08-01 | 2019-08-28
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/22012034368761 — VRKSHA ROPAN SHAMSHAN GHAT PALADA RAYSINGH SHANKARLAL | Completed | 335000 | 200732 | 2017-08-01 | 2022-07-05
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/22012034368763 — VRKSHA ROPAN SHAMSHAN GHAT PARISAR PALADA GOPAL KANEHYALAL | Completed | 335000 | 162588 | 2017-08-01 | 2024-02-08
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/22012034368766 — VRKSHA ROPAN SHAMSHAN GHAT PARISAR PALADA RADHYSHYAM BASANTILAL | Completed | 335000 | 113538 | 2017-08-01 | 2024-02-08
NEEMUCH / MANASA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/22012034482986 — KAPILDHARA KOOP NIRMAN(shantibhai bothalal) | Completed | 232455.24 | 194435.26 | 2019-07-02 | 2021-12-12
NEEMUCH / MANASA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1741003049/IF/22012035142678 — NIJI FALODHYAN ( GOPAL UKARLAL GAYRI) PALDA | Completed | 144900 | 54744 | 2023-10-06 | 2026-01-29
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003049/IF/22012035420072 — DUG WELL RECHARGE PIT INDIVIDUAL ( RADHESHYAM NONDRAM PATIDAR ) PALDA | Completed | 25899.46 | 23994 | 2025-04-30 | 2026-01-10
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003049/IF/22012035420148 — DUG WELL RECHARGE PIT INDIVIDUAL ( MUKESH SHANTILAL PATIDAR ) PALDA | Completed | 25899.46 | 23994 | 2025-04-30 | 2026-01-10
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003049/IF/22012035420222 — DUG WELL RECHARGE PIT INDIVIDUAL ( SHREERAM LALARAM PATIDAR ) PALDA | Completed | 25899.46 | 23994 | 2025-04-30 | 2026-01-10
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003049/IF/22012035420279 — DUG WELL RECHARGE PIT INDIVIDUAL ( BHERULAL NATHULAL BALAI ) PALDA | Completed | 25899.46 | 23994 | 2025-04-30 | 2026-01-30
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003049/IF/22012035420330 — DUG WELL RECHARGE PIT INDIVIDUAL ( PURALAL RATANLAL BALAI) PALDA | Completed | 25899.46 | 24019.2 | 2025-04-30 | 2026-01-10
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003049/IF/22012035420419 — DUG WELL RECHARGE PIT INDIVIDUAL ( RAJARAM BHAGWAN BALAI) PALDA | Completed | 25899.46 | 23994 | 2025-04-30 | 2026-01-10
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003049/IF/22012035420544 — DUG WELL RECHARGE PIT INDIVIDUAL ( BOTLAL MANGILAL BANJARA ) PALDA | Completed | 25899.46 | 23994 | 2025-04-30 | 2026-01-10
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003049/IF/22012035420626 — DUG WELL RECHARGE PIT INDIVIDUAL ( BHAGIRATH MANGILAL BANJARA ) PALDA | Completed | 25899.46 | 23994 | 2025-04-30 | 2026-01-10
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003049/IF/22012035420678 — DUG WELL RECHARGE PIT INDIVIDUAL ( BAPULAL MANGILAL BANJARA ) PALDA | Completed | 25899.46 | 21239.99 | 2025-04-30 | 2026-01-10
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003049/IF/22012035420743 — DUG WELL RECHARGE PIT INDIVIDUAL ( PANNALAL MANGILAL PATIDAR ) PALDA | Completed | 25899.46 | 23994 | 2025-04-30 | 2026-01-10
NEEMUCH / MANASA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/9926715412 — कपिल धारा कुप निर्माण मांगी बाई पति शंकरलाल ts no | Completed | 410000 | 286398.2 | 2014-03-08 | 2018-08-09
NEEMUCH / MANASA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/9926715417 — कपिल धारा कुप निर्माण ईशवरलाल जगन्‍नाथ ts no 252 | Completed | 410000 | 310605 | 2014-03-08 | 2017-08-20
NEEMUCH / MANASA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/9926720828 — कपिल धारा कुप निर्माण समरथ फतेहसिंह ts no 311 डोरि | Completed | 410000 | 299622 | 2014-03-26 | 2017-02-22
NEEMUCH / MANASA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/9926720832 — कपिल धारा कुप निर्माण विधाबाई सत्‍यनारायण ts no 31 | Completed | 410000 | 406250 | 2014-03-26 | 2017-03-31
NEEMUCH / MANASA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1741003049/IF/9993702615 — मवेश्‍िायो के लिए पक्‍का फर्श युरिन टेंक एवं नाद निर्माण गायत्री बाई मुकेश बैरागी ts no 1383 | Completed | 53800 | 49065.97 | 2016-01-30 | 2016-08-05
NEEMUCH / MANASA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/9993734640 — कपिल धारा कुप निर्माण पुष्‍पा बाई रमेश ts no 1611 | Completed | 398000 | 396762.9 | 2016-04-18 | 2017-08-20
NEEMUCH / MANASA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/9993735257 — कपिल धारा कुप निर्माण सम्‍पत बाई पति गोपालदास बैरागी ts no 1617 | Completed | 398000 | 327505 | 2016-05-05 | 2017-08-20
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1074230 — Construction of IAY House -IAY REG. NO. MP2133692 | Completed | 15480 | 15426 | 2017-10-25 | 2018-11-12
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1074749 — Construction of IAY House -IAY REG. NO. MP2158335 | Completed | 15480 | 15660 | 2018-05-22 | 2018-10-17
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1074949 — Construction of IAY House -IAY REG. NO. MP2167672 | Completed | 15480 | 14568 | 2017-10-27 | 2018-07-14
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1074998 — Construction of IAY House -IAY REG. NO. MP2169825 | Completed | 15480 | 15660 | 2017-10-27 | 2018-11-17
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1080636 — Construction of IAY House -IAY REG. NO. MP2414450 | Completed | 15480 | 14856 | 2017-10-07 | 2018-07-14
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1082513 — Construction of IAY House -IAY REG. NO. MP2518575 | Completed | 15480 | 15684 | 2018-09-15 | 2019-11-16
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1083102 — Construction of IAY House -IAY REG. NO. MP2555749 | Completed | 15480 | 14448 | 2017-10-27 | 2018-07-14
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1083707 — Construction of IAY House -IAY REG. NO. MP2596700 | Completed | 15480 | 15660 | 2018-09-15 | 2019-03-22
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1083716 — Construction of IAY House -IAY REG. NO. MP2597070 | Completed | 15480 | 15600 | 2017-10-07 | 2018-11-29
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1092518 — Construction of IAY House -IAY REG. NO. MP3240925 | Completed | 15480 | 15672 | 2017-10-31 | 2019-07-29
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1092981 — Construction of IAY House -IAY REG. NO. MP3276910 | Completed | 15480 | 15136 | 2017-10-25 | 2018-07-14
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1092989 — Construction of IAY House -IAY REG. NO. MP3277392 | Completed | 15480 | 15660 | 2018-05-22 | 2018-11-17
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1093001 — Construction of IAY House -IAY REG. NO. MP3278597 | Completed | 15480 | 14520 | 2017-10-27 | 2018-07-14
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1093003 — Construction of IAY House -IAY REG. NO. MP3278651 | Completed | 15480 | 15648 | 2017-10-31 | 2019-02-25
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1093022 — Construction of IAY House -IAY REG. NO. MP3280277 | Completed | 15480 | 15462 | 2017-10-27 | 2019-03-31
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1094030 — Construction of IAY House -IAY REG. NO. MP3359616 | Completed | 15480 | 15636 | 2017-10-27 | 2019-01-13
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1094688 — Construction of IAY House -IAY REG. NO. MP3408736 | Completed | 15480 | 15648 | 2017-10-27 | 2018-12-22
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1094966 — Construction of IAY House -IAY REG. NO. MP3427744 | Completed | 15480 | 14964 | 2017-10-25 | 2018-07-14
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1095013 — Construction of IAY House -IAY REG. NO. MP3431992 | Completed | 15480 | 14792 | 2017-10-31 | 2018-07-14
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1095315 — Construction of IAY House -IAY REG. NO. MP3457555 | Completed | 15480 | 15486 | 2018-07-19 | 2019-03-31
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1097874 — Construction of IAY House -IAY REG. NO. MP3675226 | Completed | 15480 | 14880 | 2017-10-25 | 2018-07-14
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1098065 — Construction of IAY House -IAY REG. NO. MP3697317 | Completed | 15480 | 15600 | 2017-10-31 | 2018-11-15
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1098502 — Construction of IAY House -IAY REG. NO. MP3749530 | Completed | 15480 | 15136 | 2017-10-25 | 2018-07-14
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1157917 — Construction of IAY House -IAY REG. NO. MP3425352 | Completed | 15480 | 15312 | 2018-05-22 | 2019-04-10
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1162370 — Construction of IAY House -IAY REG. NO. MP3798083 | Completed | 15480 | 15438 | 2017-10-27 | 2018-11-12
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1793238 — Construction of IAY House -IAY REG. NO. MP2142206 | Completed | 15660 | 15660 | 2018-05-22 | 2018-11-12
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1793572 — Construction of IAY House -IAY REG. NO. MP3135051 | Completed | 15660 | 15660 | 2018-05-22 | 2018-10-24
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1793584 — Construction of IAY House -IAY REG. NO. MP3178787 | Completed | 15660 | 15660 | 2018-05-22 | 2019-02-14
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1815814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2359948 | Completed | 15660 | 15486 | 2018-07-27 | 2018-10-17
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1844030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3785328 | Completed | 15660 | 15660 | 2018-09-15 | 2018-10-23
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1847269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3178378 | Completed | 15660 | 15486 | 2018-09-15 | 2019-04-10
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1847855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3758023 | Completed | 15660 | 15660 | 2018-09-15 | 2018-12-28
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1847870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3787669 | Completed | 15660 | 15660 | 2018-09-15 | 2018-12-28
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1847880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3817025 | Completed | 15660 | 15672 | 2018-09-15 | 2019-11-16
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1848058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3790133 | Completed | 15660 | 15660 | 2018-08-22 | 2018-10-23
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1857730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3771558 | Completed | 15660 | 15840 | 2018-10-25 | 2019-07-16
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1858201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3412846 | Completed | 15660 | 15660 | 2018-10-24 | 2019-01-16
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1865679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2150163 | Completed | 15660 | 15660 | 2018-10-25 | 2019-02-14
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1927110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2148656 | Completed | 15660 | 15684 | 2018-10-24 | 2019-07-29
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/1927312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3451037 | Completed | 15660 | 15678 | 2018-10-24 | 2019-08-17
NEEMUCH / MANASA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/243607 — Construction of IAY House -IAY REG. NO. MP1640709 | Completed | 15030 | 15240 | 2017-02-01 | 2018-08-08
NEEMUCH / MANASA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/247889 — Construction of IAY House -IAY REG. NO. MP1786110 | Completed | 15030 | 15008 | 2017-02-16 | 2018-04-06
NEEMUCH / MANASA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/248767 — Construction of IAY House -IAY REG. NO. MP1828015 | Completed | 15030 | 15330 | 2017-02-16 | 2018-04-06
NEEMUCH / MANASA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/259851 — Construction of IAY House -IAY REG. NO. MP2356547 | Completed | 15030 | 15008 | 2017-02-01 | 2018-04-06
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3810149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118488096 | Completed | 18360 | 17136 | 2022-06-15 | 2024-02-08
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3816550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119349317 | Completed | 18360 | 18343 | 2022-06-16 | 2024-02-08
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3816554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119351192 | Completed | 18360 | 18241 | 2022-09-22 | 2024-02-08
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3822075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119872806 | Completed | 18360 | 18241 | 2022-06-15 | 2024-02-08
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3823392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123380256 | Completed | 18360 | 18241 | 2022-06-15 | 2024-02-08
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3837333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123827564 | Completed | 18360 | 18324 | 2022-06-16 | 2024-05-22
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3848913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127465784 | Completed | 18360 | 18207 | 2022-07-19 | 2024-02-08
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3854486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126787904 | Completed | 18360 | 18360 | 2022-08-10 | 2022-10-15
NEEMUCH / MANASA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3854678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126804936 | Completed | 18360 | 15912 | 2023-06-23 | 2024-06-11
NEEMUCH / MANASA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3876742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126142355 | Completed | 18360 | 15912 | 2023-04-15 | 2024-06-11
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3876755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126143487 | Completed | 18360 | 18224 | 2022-06-16 | 2024-02-08
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3876764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126144461 | Completed | 18360 | 18241 | 2022-06-16 | 2024-02-08
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3888893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126179125 | Completed | 18360 | 18241 | 2022-06-16 | 2024-02-08
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3888910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126180813 | Completed | 18360 | 18309 | 2022-06-16 | 2024-02-08
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3888944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126183859 | Completed | 18360 | 18309 | 2022-10-14 | 2023-08-03
NEEMUCH / MANASA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3911728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150718597 | Completed | 18360 | 17901 | 2023-05-26 | 2023-07-22
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/3918599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127326163 | Completed | 18360 | 18360 | 2022-09-29 | 2023-01-30
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4194974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123170214 | Completed | 18360 | 18343 | 2022-07-19 | 2024-02-08
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4195943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124179018 | Completed | 18360 | 17952 | 2022-07-19 | 2023-08-03
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4197004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125883341 | Completed | 18360 | 17136 | 2022-07-31 | 2024-06-11
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4199429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126185689 | Completed | 18360 | 18360 | 2022-07-19 | 2022-11-10
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4216931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150718246 | Completed | 18360 | 14346 | 2022-07-31 | 2025-01-15
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4366946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150705732 | Completed | 18360 | 18360 | 2022-12-06 | 2023-02-15
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4603219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123758393 | Completed | 21870 | 21870 | 2024-10-29 | 2025-01-09
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4603899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124438509 | Completed | 21870 | 21870 | 2024-11-26 | 2025-02-08
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4614151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126182198 | Completed | 21870 | 21870 | 2024-11-26 | 2025-02-08
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4619948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126146083 | Completed | 21870 | 21870 | 2024-11-12 | 2025-02-08
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4620154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126176018 | Completed | 23490 | 21825 | 2024-11-12 | 2025-04-13
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4622244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126789265 | Completed | 21870 | 21870 | 2024-12-25 | 2025-02-27
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4622291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126796121 | Completed | 23490 | 21828 | 2024-10-29 | 2025-04-28
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4628449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127463787 | Completed | 23490 | 22122 | 2025-02-11 | 2025-09-29
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4629028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127476888 | Completed | 23490 | 21690 | 2024-12-25 | 2025-05-06
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4666430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150708024 | Completed | 21870 | 21870 | 2024-11-26 | 2025-02-08
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/4666464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150718834 | Completed | 21870 | 21870 | 2024-10-29 | 2025-02-08
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/487546 — Construction of IAY House -IAY REG. NO. MP2104465 | Completed | 17100 | 17916 | 2017-10-27 | 2020-12-04
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/487548 — Construction of IAY House -IAY REG. NO. MP2104493 | Completed | 15030 | 15612 | 2017-10-25 | 2018-12-22
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/5012491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123759028 | Completed | 23490 | 21924 | 2025-08-13 | 2026-03-19
NEEMUCH / MANASA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/505286 — Construction of IAY House -IAY REG. NO. MP2326573 | Completed | 15030 | 14868 | 2017-02-05 | 2018-12-21
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/506190 — Construction of IAY House -IAY REG. NO. MP2337783 | Completed | 15030 | 15018 | 2017-07-13 | 2018-05-19
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/5083034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126193043 | Completed | 23490 | 22968 | 2025-08-13 | 2025-09-29
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/5083051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126201163 | Completed | 23490 | 22968 | 2025-05-02 | 2025-07-31
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/5083243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126499294 | Completed | 23490 | 23490 | 2025-04-03 | 2025-08-11
NEEMUCH / MANASA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/508365 — Construction of IAY House -IAY REG. NO. MP2360692 | Completed | 17100 | 5010 | 2017-02-05 | 2022-04-01
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/5085596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127473010 | Completed | 23490 | 22707 | 2025-07-01 | 2025-09-30
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/512531 — Construction of IAY House -IAY REG. NO. MP2405497 | Completed | 15030 | 15136 | 2017-05-30 | 2018-04-06
NEEMUCH / MANASA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/518472 — Construction of IAY House -IAY REG. NO. MP2518166 | Completed | 15030 | 15450 | 2017-02-05 | 2019-03-22
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/518964 — Construction of IAY House -IAY REG. NO. MP2528876 | Completed | 15030 | 15136 | 2017-10-27 | 2018-04-25
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/596160 — Construction of IAY House -IAY REG. NO. MP1640719 | Completed | 15030 | 15480 | 2017-05-30 | 2018-04-06
NEEMUCH / MANASA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003049/IF/IAY/82948 — Construction of IAY House -IAY REG. NO. MP-41-003-049-002/4 | Completed | 14310 | 15030 | 2016-02-16 | 2017-04-06
NEEMUCH / MANASA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/Ts.No-13 — नन्‍दन फलोघान प्रहलाद खीमा Ts.No-13 ( पालडा) | Completed | 157000 | 12661 | 2011-09-08 | 2015-03-02
NEEMUCH / MANASA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/Ts.no-14 — नन्‍दन फलोघान कैलाश नाथु Ts.No.14 (पालडा) | Completed | 157000 | 14503 | 2011-09-06 | 2015-03-02
NEEMUCH / MANASA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/Ts.No-6 — नन्‍दन फलोघान पन्‍नालाल छोगा Ts.No.6 (पालडा) | Completed | 157000 | 15943 | 2011-09-09 | 2015-03-02
NEEMUCH / MANASA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/Ts.No-7 — नन्‍दन फलोघान गोवि‍न्‍द कन्‍हैयालाल Ts.No-7 ( पालडा) | Completed | 157000 | 15571 | 2011-09-08 | 2015-03-02
NEEMUCH / MANASA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/Ts.no-8 — नन्‍दन फलोघान नरवोत्‍म नन्‍दा Ts.No.8 (पालडा) | Completed | 157000 | 17967 | 2011-09-07 | 2015-03-02
NEEMUCH / MANASA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003049/IF/Ts.No-9 — नन्‍दन फलोघान रामलाल भोलू Ts.No.9 (पालडा) | Completed | 157000 | 16982 | 2011-09-08 | 2015-03-02
NEEMUCH / MANASA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/कपि‍लधारा अमरसि‍ह चुन्‍नीलाल डोरि‍या — कपि‍लधारा अमरसि‍ह चुन्‍नीलाल डोरि‍याखेडी (पालडा) | Completed | 187000 | 22910 | 2010-02-04 | 2015-02-12
NEEMUCH / MANASA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/कपि‍लधारा कारूलाल मांगीलाल कराडि‍या — कपि‍लधारा कारूलाल मांगीलाल कराडि‍या (पालडा) | Completed | 187000 | 149962 | 2010-03-17 | 2015-02-12
NEEMUCH / MANASA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/कपि‍लधारा पन्‍नालाल छोगा (पालडा) — कपि‍लधारा पन्‍नालाल छोगा (पालडा) | Completed | 187000 | 105729 | 2010-03-09 | 2015-02-12
NEEMUCH / MANASA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/कपि‍लधारा भागीरथ मगन (पालडा) — कपि‍लधारा भागीरथ मगन (पालडा) | Completed | 187000 | 118274 | 2010-03-07 | 2015-02-12
NEEMUCH / MANASA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/कपि‍लधारा मुलचंद देवीलाल (पालडा) — कपि‍लधारा मुलचंद देवीलाल (पालडा) | Completed | 187000 | 101419 | 2010-04-05 | 2015-02-12
NEEMUCH / MANASA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/कपि‍लधारा रंगलाल केशुराम कराडि‍या (प — कपि‍लधारा रंगलाल केशुराम कराडि‍या (पालडा) | Completed | 187000 | 176313 | 2010-02-19 | 2015-02-12
NEEMUCH / MANASA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/कपि‍लधारा राधेश्‍याम रतनलाल (पालडा) — कपि‍लधारा राधेश्‍याम रतनलाल (पालडा) | Completed | 187000 | 137750 | 2010-04-05 | 2015-02-12
NEEMUCH / MANASA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003049/IF/कपि‍लधारा सुखलाल मोहनलाल सि‍घाडि‍या — कपि‍लधारा सुखलाल मोहनलाल सि‍घाडि‍या (पालडा) | Completed | 187000 | 190743 | 2010-02-20 | 2015-02-12
NEEMUCH / MANASA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1741003049/LD/22012034238150 — खैल मैदान कार्य माध्‍यमिक विधालय ts no 409 पिपल्‍यासिंघाडिया | Completed | 592000 | 314100 | 2015-12-06 | 2016-08-05
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1741003049/LD/22012034306171 — शांतिधाम टीन शेड निर्माण पिपलियासिंघाडीया टीएस 12445 | Completed | 180000 | 179399.93 | 2017-03-18 | 2018-07-16
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1741003049/LD/22012034306253 — SHANTI DHAM TEEN SHED NIRMAN SINGHADIYA PIPLIYA TS 12445 | Completed | 180000 | 172027.23 | 2017-08-30 | 2018-07-16
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1741003049/LD/22012034358352 — SHANTI DHAM TEEN SHED NIRMAN KARADIYA PALADA | Completed | 180000 | 187413.26 | 2017-08-18 | 2018-07-16
NEEMUCH / MANASA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1741003049/LD/Ts 17 — खेल मैदान कार्य Ts 17 (पालडा) | Completed | 447000 | 154135 | 2011-06-18 | 2015-03-02
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1741003049/PG/9425895455 — खैल मैदान निर्माण कार्य सिंगघाडीया पिपलिया टीएस 12443 | Completed | 353000 | 6012 | 2017-03-19 | 2017-04-01
NEEMUCH / MANASA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/166 — पंचपरमेश्‍वर आंतरि‍क पथ सी सी मार्ग Ts 166 EE (पालडा) | Completed | 118000 | 46356 | 2012-04-03 | 2015-03-02
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034168777 — पंचपरमेश्‍वर आंतरिक पथ सी सी मार्ग बंशीलाल के मकान | Completed | 72310 | 65660.6 | 2013-05-31 | 2015-03-02
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034173567 — ग्राम कराडिया मे सी सी रोड निर्माण मंदिर से बद्रील | Completed | 60000 | 59311 | 2013-07-05 | 2014-12-11
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034183373 — आंतरिक पथ सी सी रोड पंचपरमेश्‍वर हनुमान मंदिर से | Completed | 58200 | 58145.8 | 2013-09-20 | 2015-03-02
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034183380 — आंतरिक पथ सी सी रोड पंचपरमेश्‍वर प्रभुलाल के मकान | Completed | 43300 | 34460 | 2013-09-20 | 2016-09-12
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034189777 — आंतरि‍क पथ सी सी रोड जेतराम के मकान से भेरू रावत क | Completed | 74000 | 72811.3 | 2013-10-11 | 2014-12-11
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034195231 — आंतरिक पथ सी सी रोड रामेश्‍वर रावत के मकान से अमरस | Completed | 59300 | 70811.8 | 2013-12-23 | 2014-12-11
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003049/RC/22012034208360 — खेत सडक योजना अंतर्गत पंचायत भवन से बंजारा बस्‍ती | Completed | 1452000 | 539213.93 | 2014-02-26 | 2017-02-28
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003049/RC/22012034208365 — खेत सडक योजना अंतर्गत रामचन्‍द्र के खेत से बगदीराम उंकार के खेत तक सडक कराडिया | Completed | 1500000 | 4380 | 2014-02-27 | 2015-10-18
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003049/RC/22012034212278 — खेत सडक योजना अंतर्गत स्‍कुल से शमशान घाट तक सडक प | Completed | 1482000 | 1195047 | 2014-03-06 | 2016-09-12
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034213108 — आंतरिक पथ सी सी रोड निर्माण रामेश्‍वर रावत के मकान | Completed | 34300 | 18635 | 2014-03-09 | 2015-02-12
NEEMUCH / MANASA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034231808 — सी सी रोड केशर लाल के बाड़े से नंदलाल ओड़ के मकान तक ग्राम कराडिया पलड़ा | Completed | 53200 | 49030 | 2014-10-30 | 2015-10-18
NEEMUCH / MANASA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034231809 — सी सी रोड सीताराम के मकान से मूलचंद के मकान तक डोरियाखेड़ी पलड़ा | Completed | 34200 | 34009.99 | 2014-10-30 | 2015-10-18
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034289296 — आंतरिक पथ सी सी रोड निर्माण श्री हनुमान मंदिर परिसर ts no 621 | Completed | 27000 | 26400 | 2015-11-19 | 2016-01-28
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003049/RC/22012034289299 — खेत सडक योजनान्‍तर्गत डोरियाखेडी से नाले की ओर 0 से 700 मी तक ts no 406 | Completed | 1139000 | 250079.9 | 2016-05-10 | 2017-02-28
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003049/RC/22012034295483 — खेत सडक योजनान्‍तर्गत पालडा चौराया से रमेश मेहतर के खेत की ओर 0 से 700 मी ts no 1391 | Completed | 1240000 | 590290 | 2016-01-07 | 2017-02-28
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034297920 — आंतरिक पथ सी सी रोड निर्माण हेण्‍डपंप से गोर्वधनलाल धनगर के मकान की ओर ts no 1488 | Completed | 23700 | 22706 | 2016-02-16 | 2016-08-05
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034327583 — आंतरिक पथ्‍ा सी सी रोड निर्माण मंदिर चौक टीएस 251 डोरियाखेडी | Completed | 52800 | 47513 | 2017-03-07 | 2017-03-26
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034327590 — आंतरिक पथ सी सी रोड निर्माण मंदिर चौक डोरियाखेडी टीएस 65 | Completed | 25700 | 23484 | 2017-03-21 | 2017-04-01
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034330594 — आंतरिक पथ सी सी रोड निर्माण मंदिर से प्राथमिक विधालय तक न्‍यु डीपीआर डोरियाखेडी | Completed | 216000 | 90366 | 2017-03-11 | 2019-10-18
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003049/RC/22012034339841 — सुदुर ग्राम सडक निर्माण सिंघाडिया से डोरियाखेडी तक टीएस 112 | Completed | 2483000 | 2301471.71 | 2017-06-07 | 2019-10-05
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034365667 — आंतरिक पथ सी सी रोड निर्माण अमरलाल बंजारा के मकान से विनोद बंजारा के मकान तक टीएस 194 | Completed | 21500 | 18539 | 2017-10-31 | 2018-07-13
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034374844 — न्‍यु डीपीआर सी सी रोड निर्माण पन्‍नालाल के मकान से राधेश्‍याम रावत के मकान तक कराडिया | Completed | 74400 | 31992 | 2018-01-07 | 2019-08-16
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034396224 — डीपीआर सी सी रोड निर्माण हनुमान मंदिर चौक से शेशराम रावत के मकान तक सिंघ्‍ााडीया पिपलिया | Completed | 93225 | 92256 | 2018-11-30 | 2019-08-16
NEEMUCH / MANASA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034504792 — DPR CC ROAD NIRMAN ( MOHAN LAL JAGNNATH KAI MAKAN SEY JAGDISH PATIDAR K MAKAN TAK ) PIPLYA SINGHDIYA | Completed | 4200 | 3872 | 2019-11-09 | 2019-12-22
NEEMUCH / MANASA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034504793 — DPR CC ROAD NIRMAN ( RUP SINGH RAWAT K BADEY SEY BANSHI LAL MEGHWAL K MAKAN TAK ) SINGHDIYA PIPLYA | Completed | 84100 | 84480 | 2019-11-09 | 2020-01-10
NEEMUCH / MANASA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034504983 — DPR CC ROAD NIRMAN ( BAGDIRAM KAI MAKAN SEY VARDI CHAND RAWAT KAI MAKAN TAK ) DORIYAKHEDI | Completed | 27900 | 12672 | 2019-11-09 | 2020-03-20
NEEMUCH / MANASA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034504986 — DPR CC ROAD NIRMAN ( PANNA LAL RAWAT KAI MAKAN SEY RAMCHANDR RAWAT KAI MAKAN TAK ) KARADIYA | Completed | 17700 | 16896 | 2020-02-08 | 2020-06-20
NEEMUCH / MANASA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034504989 — DPR CC ROAD NIRMAN ( KARU LAL BANJARA KAI MAKAN SEY LAXMAN BANJARA KAI MAKAN TAK ) PALADA | Completed | 35600 | 34848 | 2019-11-09 | 2020-01-20
NEEMUCH / MANASA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034504992 — DPR CC ROAD NIRMAN ( HEERA LAL PATIDAR KAI MAKAN SEY GOPAL BALAI KAI MAKAN TAK ) PALADA | Completed | 42300 | 41184 | 2019-11-09 | 2020-02-15
NEEMUCH / MANASA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034504994 — DPR CC ROAD NIRMAN ( DAYARAM KAI MAKAN SEY JAGDISH BANJARA KAI MAKAN TAK ) PALADA | Completed | 33100 | 33060 | 2020-07-19 | 2020-08-18
NEEMUCH / MANASA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034504996 — DPR CC ROAD NIRMAN ( LAL BAI MATA JI CHOUK ) PALADA | Completed | 7700 | 6336 | 2019-11-09 | 2020-02-25
NEEMUCH / MANASA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034528662 — CC ROAD NIRMAN ( BANSHILAL MEGHWAL KAI MAKAN SY BHERU BAWAJI KI OR ) SINGHADIAYA PIPLIYA | Completed | 24860 | 23940 | 2020-07-08 | 2020-08-18
NEEMUCH / MANASA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034528663 — CC ROAD NIRMAN ( KACHRU LAL BAGRI KAI MAKAN SY VISHNU PATIDAR KAI MAKAN KI OR ) PALADA | Completed | 76500 | 76380 | 2020-07-08 | 2020-12-23
NEEMUCH / MANASA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034528664 — CC ROAD NIRMAN ( BAGDIRAM MEGHWAL KAI MAKAN SY RAMGOPAL PATIDAR KAI MAKAN TAK ) PIPLYA SINGHDIYA | Completed | 15618 | 11400 | 2020-08-23 | 2021-02-26
NEEMUCH / MANASA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034548060 — CC ROAD NIRMAN ( MEN ROAD SY BHAWARLAL GUJRATI KAI MAKAN TAK ) PALADA | Completed | 46100 | 44928 | 2020-11-12 | 2025-03-20
NEEMUCH / MANASA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034548061 — CC ROAD NIRMAN ( MEN ROAD SY RAKESH PATIDAR KAI MAKANTAK ) PALADA | Completed | 44800 | 43770 | 2020-11-12 | 2025-03-20
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034574029 — NALI NIRMAN ( SHIVNARAYAN PATIDAR KAI MAKAN SY GRAM PANCHYAT KI OR ) PALADA | Completed | 22500 | 20844 | 2021-06-19 | 2021-06-25
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034579228 — CC ROAD NIRMAN ( SCHOL SY SAMRATH PORWAL KAI MAKAN KI OR ) KARADIYA | Completed | 96000 | 71989 | 2021-09-10 | 2025-03-20
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034598266 — CC ROAD NIRMAN ( SCHOL KAI SAMNEY ) KARADIYA | Completed | 30000 | 26634 | 2021-12-07 | 2022-03-12
NEEMUCH / MANASA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034623818 — CC ROAD NIRMAN ( MATAJI MANDIR KE SAMNE) PALDA | Completed | 22000 | 19890 | 2023-08-10 | 2024-11-23
NEEMUCH / MANASA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003049/RC/22012034634501 — SUDUR SADAK NIRMAN ( PALDA SE BANJARA BASTI BHAMESAR KI OR ) PALDA | Completed | 1348340.65 | 1013770.83 | 2023-06-03 | 2026-01-29
NEEMUCH / MANASA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034649582 — CC ROAD NIRMAN ( RAMKARAN PATIDAR KE MAKAN SE RAJESH MEHATA KE MAKAN TAK ) PA LDA | Completed | 46000 | 45684 | 2024-09-14 | 2026-01-29
NEEMUCH / MANASA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/22012034662728 — C C ROAD NIRMAN ( GOPAL RAWAT KE MAKAN SE KESHARIMAL KE BADE KI AUR ) PALDA | Completed | 70000 | 68040 | 2024-08-15 | 2026-01-29
NEEMUCH / MANASA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003049/RC/289 — पचपरमेश्‍वर आतरि‍क पथ कराडि‍या Ts 289 (पालडा) | Completed | 62000 | 55438 | 2012-06-30 | 2015-02-12
NEEMUCH / MANASA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1741003049/RC/सडक नि‍र्माण डोरीयाखेडी से सि‍गाडीया — सडक नि‍र्माण डोरीयाखेडी से सि‍गाडीया (पालडा) | Completed | 433000 | 219012 | 2008-06-17 | 2015-02-12
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741003049/RS/22012034288405 — SHOCHALAY GOPAL KANEHYALAL TS NO 1741003049/01EE/11 | Completed | 5400 | 4980 | 2015-10-16 | 2016-05-30
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741003049/RS/22012034288407 — SHOCHLAY PURALAL RODILAL TS NO 1741003049/01EE/94 | Completed | 5400 | 4980 | 2015-10-16 | 2016-05-30
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741003049/RS/22012034288421 — SHOCHALAY SATYNARYAN BHAWARDAS TS NO 1741003049/01EE/89 | Completed | 5400 | 4980 | 2015-10-16 | 2016-05-30
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741003049/RS/22012034288423 — SHOCHALAY BHAIRULAL NATHU TS NO 1741003049/01EE/19 | Completed | 5400 | 4980 | 2015-10-16 | 2016-05-30
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741003049/RS/22012034288426 — SHOCHALAY GOPAL GHASI TS NO 1741003049/01EE/13 | Completed | 5400 | 4980 | 2015-10-16 | 2016-05-30
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741003049/RS/22012034409482 — SHOCHALAY NIRAMAN SHYAMLAL BAPULAL DORIYAKHEDI | Completed | 12000 | 10908 | 2018-08-04 | 2021-03-31
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741003049/RS/22012034409483 — SHOCHALAY NIRAMAN LALSING BHAGIRATH KARADIYA | Completed | 12000 | 10908 | 2018-08-04 | 2020-06-01
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741003049/RS/22012034409485 — SHOCHALAY NIRAMAN RODILAL GIRDHARI PIPLIYA SINGHADIYA | Completed | 12000 | 10908 | 2018-08-04 | 2021-03-31
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741003049/RS/22012034409488 — SHOCHALAY NIRAMAN LILA BAI RAMNARAYAN SINGHADIYA PIPLYA | Completed | 12000 | 11134.65 | 2018-08-04 | 2020-06-01
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1741003049/RS/22012034533308 — SAMUDAYIK SWACHHTA PARISAR NIRMAN ( JAGDISH PATIDAR K KUWE K PAS) PIPLIYA | Completed | 43700 | 37828 | 2021-12-07 | 2025-03-20
NEEMUCH / MANASA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003049/WC/22012034447107 — PEROCATION TANK NIRMAN(singhadiya pipliya) | Completed | 304945.19 | 162436.5 | 2019-06-13 | 2023-10-05
NEEMUCH / MANASA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1741003049/WC/22012034553608 — TALAB RESACTIONING OR PITCTING NIRMAN ( TALAB ) PALDA | Completed | 327194.37 | 209742 | 2020-05-26 | 2021-02-06
NEEMUCH / MANASA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1741003049/WC/22012034553609 — TALAB RESACTIONING OR PITCTING NIRMN (TALAB) DORIYAKHDI | Completed | 295718.56 | 147528 | 2020-07-01 | 2021-06-06
NEEMUCH / MANASA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003049/WC/22012034571822 — PARCOLATION TANK NIRMAN ( SCHOOL KAI PICHY ) PALDA | Completed | 771257.49 | 264822.8 | 2020-07-29 | 2020-12-23
NEEMUCH / MANASA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003049/WC/22012034588095 — PARCOLATION TANK NIRMAN ( BANJARA BASTI KAI AAGEY ) PALADA | Completed | 759644.07 | 737851.38 | 2020-11-18 | 2021-07-08
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003049/WC/22012034660944 — CTR PARCOLATION TANK NIRMAN ( BAGDIRAM DHANGAR KAI KHET KAI PAAS ) SINGHADIYA PIPLIYA | Completed | 771447.52 | 434226.82 | 2021-05-28 | 2024-07-03
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003049/WC/22012034660952 — CTR PARCOLATION TANK NIRMAN ( RAJARAM KAI KHET KAI PAAS ) KARADIYA | Completed | 771447.52 | 365730.5 | 2021-08-16 | 2025-03-20
NEEMUCH / MANASA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1741003049/WC/22012034887817 — TALAB JIRNODHAR NIRMAN GRAM PALDA | Completed | 306735 | 265120.46 | 2022-04-09 | 2025-05-20
NEEMUCH / MANASA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1741003049/WC/22012034887821 — STOP DAM JIRNODHAR NIRMAN ( HEERALAL KE KHET KE PAS ) DORIYAKHEDI | Completed | 260289.27 | 245735.79 | 2022-04-16 | 2024-07-03
NEEMUCH / MANASA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1741003049/WC/22012034950575 — STOP DAM NIRMAN (BALCHAN PATIDAR KE KHET KE PAAS PIPLIYA SINGADA ) PALDA | Completed | 847896.41 | 572916.4 | 2022-04-25 | 2025-04-29
NEEMUCH / MANASA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003049/WC/22012034962460 — PARCOLATION TANK NIRMAN (KARULAL BANJARA KE KHET KE PASS ) PALDA | Completed | 493288.43 | 430123.24 | 2022-05-16 | 2026-01-24
NEEMUCH / MANASA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1741003049/WC/22012035006751 — AMRIT SAROVER DUG OUT POND NIRMAN PALDA | Completed | 1470049.04 | 959836 | 2023-05-16 | 2026-01-24
NEEMUCH / MANASA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1741003049/WC/472 — कंटूर टेच Ts no 357 पालडा | Completed | 436000 | 28512 | 2013-03-13 | 2015-03-21
NEEMUCH / MANASA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003049/WC/9993643882 — परकोलेशन टेंक निर्माण ts no 112 पालडा | Completed | 304000 | 284521 | 2014-01-28 | 2017-02-22
NEEMUCH / MANASA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003049/WC/9993647301 — परकोलेशन टेंक ts no 111 पालडा | Completed | 304000 | 279037 | 2014-02-26 | 2017-02-22
NEEMUCH / MANASA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1741003049/WC/9993659460 — निर्मल नीर कुप निर्माण कार्य ts no 408 पिपलियासिंघाडिया | Completed | 594000 | 566201.9 | 2015-12-27 | 2016-08-05
NEEMUCH / MANASA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003049/WC/Ts.no 101 — परकोलेशन टेंक कराडीया Ts.No 101 (पालडा) | Completed | 200000 | 163168 | 2011-07-18 | 2015-02-12
NEEMUCH / MANASA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741/WC/9993625908 — MICRO WHATER SHED PALDA | Completed | 109000 | 69696 | 2012-09-13 | 2015-03-21