## Work List
Exported on: 2026-10-21 12:28:28
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: CHUKNI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1741003082/AV/22012034401288 — PANCHAYAT BHAWAN NIRMAN CHUKNI | Completed | 1000000 | 999537.75 | 2019-03-09 | 2020-06-16
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1741003082/AV/22012034577115 — DAINING HAAL NIRMAN ( SCHOOL ) CHUKNI | Closed | 16093.2 | 0 | 2021-04-01
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1741003082/AV/22012034583376 — DAINING HAAL NIRMAN ( PRIMARY SCHOOL ) CHUKNI | Closed | 0 | 0 | 2021-04-01
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1741003082/AV/7685 — आगनवाडी भवन निर्माण टीएस 12 चुकनी खेडा | Completed | 180000 | 179704 | 2017-02-16 | 2017-12-24
NEEMUCH / MANASA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003082/DP/22012034444800 — NIRMAL NIR KUP NIRMAN ( SHAMSHAN K PAAS ) CHUKNI KHEDA | Suspended | 535032.26 | 174 | 2019-03-09
NEEMUCH / MANASA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003082/DP/22012034526749 — NIRMAL NIR KUP NIRMAN ( TALAB KAI PAAS ) CHUKNI | Closed | 0 | 0 | 2021-04-01
NEEMUCH / MANASA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1741003082/DP/22012034567394 — VRAKSHA ROPAN KARYA (SHAMSHAN GHAT PARISAR ME CHUKNIKHEDA ) CHUKNI | Ongoing | 408007.29 | 214478.5 | 2022-09-28
NEEMUCH / MANASA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1741003082/DP/22012034603830 — VASUDHA VANDAN PLANTATION WORK (MERI MATI MERA DESH) CHUKNI | Closed | 55847.4 | 0 | 2023-04-14
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1741003082/DP/22012034614409 — nirmal nir kup nirman | New | 0 | 0 | 2024-04-01
NEEMUCH / MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1741003082/DP/22012034625994 — VRAKSHA ROPAN KARYA ( PRATHAMIK SCHOOL PARISAR CHUKNI KHEDA ) CHUKNI | Ongoing | 309689.07 | 72144.5 | 2024-09-06
NEEMUCH / MANASA | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1741003082/DP/9993627864 — व़क्षा रोपण कार्य tsno. 110 चुकनी | Deleted | 256000 | 0 | 2014-04-26
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003082/FP/22012034314553 — नाले मे सपोर्टवाल निर्माण उदयराम के बाडे से सुभाष के मकान की ओर टीएस 10 | Completed | 1062200 | 1040469.97 | 2017-05-21 | 2017-12-24
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003082/FP/22012034360042 — नाला निर्माण MANGILAL K MAKAN SE | Completed | 814000 | 788114.94 | 2017-10-06 | 2018-05-29
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003082/FP/22012034360111 — नाला निर्माण कार्य किशोर सेन के बाडे से पुलिया व प्रभुलाल के बाडे नाले टीएस 145 | Completed | 1478000 | 1473971.6 | 2017-10-30 | 2018-10-10
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Intermediate and Link Drains / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003082/FP/22012034360598 — पुलिया निर्माण कार्य चुकनी से ढाकनी रास्‍ता पर बेण्‍डया खाल पर टीएस 142 | Completed | 472000 | 470369.22 | 2018-02-13 | 2018-10-09
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003082/FP/22012034360702 — पुलिया निर्माण कार्य प्रधानमंत्री सडक से शेषपुर मार्ग पर टीएस 552 चुकनी | Completed | 570000 | 566897.44 | 2018-05-03 | 2019-07-12
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003082/FP/22012034361435 — नाला निर्माण कार्य बद्रीलाल शिवलाल के मकान से पेमा बालु के मकान तक टीएस 510 | Completed | 1291500 | 1135490.82 | 2019-01-25 | 2025-03-20
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003082/FP/22012034361436 — नाला निर्माण कार्य ओमप्रकाश पाटीदार के मकान से कंवरलाल सेन के मकान से नाले तक टीएस 124 | Completed | 1150000 | 720877.99 | 2019-01-25 | 2022-02-01
NEEMUCH / MANASA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003082/FP/22012034366475 — RITERNING WALL NIRMAN ( SHAMSHAN KAI PAAS ) CHUKNI | Completed | 1671681.7 | 1669896.8 | 2020-07-24 | 2022-02-01
NEEMUCH / MANASA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1741003082/FP/22012034367445 — PULIYA NIRMAN ( CHUKNI KHEDA RASTEY PAR) CHUKNI | Completed | 139000 | 139270 | 2020-09-23 | 2022-02-01
NEEMUCH / MANASA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003082/FP/22012034632208 — NALA DRAINAIGE CHAINEL NIRMAN (RAJU BHANVAJSING KE MAKAN SE SHYAMA TEJA KE MAKAN KE SAMNE) CHUKNI | Completed | 277500 | 275385 | 2023-04-17 | 2024-07-23
NEEMUCH / MANASA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1741003082/FP/22012034633678 — NALA NIRMAN ( PANCHYAT BHAVAN KE PICHE SE SHANKAR LAL JI KE BADE TAK ) CHUKNI | Ongoing | 204000 | 203909 | 2024-03-13
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1741003082/IF/22012034351966 — VRKSHA ROPAN MOKASH PARISAR CHUKNI | Completed | 335000 | 333827 | 2017-06-22 | 2024-08-12
NEEMUCH / MANASA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741003082/IF/22012034559982 — KHET TALAB NIRMAN ( KANKU BAI JEEVAN ) CHUKNI | Completed | 332572.21 | 159043 | 2020-05-28 | 2022-02-01
NEEMUCH / MANASA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741003082/IF/22012034576590 — KHET TALAB NIRMAN () | Closed | 332572.21 | 0 | 2020-04-01
NEEMUCH / MANASA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1741003082/IF/22012034683600 — KHET TALAB NIRMAN(SONABAI BHURALA)CHUKNI | Deleted | 0 | 0 | 2020-04-01
NEEMUCH / MANASA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741003082/IF/22012034770378 — CTR KHET TALAB NIRMAN ( CHAGANLAL SHIVLAL ) CHUKNI | Completed | 110516.06 | 108809.6 | 2021-06-09 | 2023-05-04
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741003082/IF/22012034980999 — KHET TALAB NIRMAN ( GOPAL BHAWSINGH BANJARA) CHUKNI | Completed | 113188.46 | 77793.72 | 2022-05-21 | 2023-07-14
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741003082/IF/22012034991405 — CTR KHET TALAB NIRMAN ( PRAKASH CHATRA BANJARA CHUKNI KHEDA) CHUKNI | Completed | 192388.69 | 113910.4 | 2022-05-27 | 2023-07-14
NEEMUCH / MANASA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003082/IF/22012035091082 — KAPIL DHARA KOOP NIRMAAN (RAHUL SURAJMAL BANJARA CHUKNI KHEDA ) CHUKNI | Completed | 272594.96 | 260247.09 | 2023-05-18 | 2024-07-19
NEEMUCH / MANASA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741003082/IF/22012035112288 — KHET TALAB NIRMAN ( GUDDI BAI SHYAMLAL BANJARA CHUKNI KHEDA ) CHUKNI | Completed | 197939.35 | 192044 | 2023-06-18 | 2025-03-09
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741003082/IF/22012035440137 — KHET TALAB NIRMAN ( MANABAI SATYNARAYAN ) CHUKNI | Physically Completed | 450885.64 | 250701 | 2025-05-07 | 2026-05-16
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003082/IF/22012035457080 — DUG WELL RECHARGE PIT INDIVIDUAL ( KANKUBAI JIVAN BANJAARA ) CHUKANI | Completed | 25899.46 | 25324.2 | 2025-05-07 | 2026-01-11
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003082/IF/22012035457106 — DUG WELL RECHARGE PIT INDIVIDUAL ( SHANTILAL SHALIGRAM PATIDAR ) CHUKANI | Completed | 25899.46 | 24019.2 | 2025-05-07 | 2026-03-31
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1741003082/IF/22012035457126 — DUG WELL RECHARGE PIT INDIVIDUAL ( KANHAIYALAL HIRALAL PATIDAR ) CHUKANI | Physically Completed | 25899.46 | 23758.2 | 2025-05-13 | 2026-04-09
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1741003082/IF/22012035558414 — KHET TALAB NIRMAN ( RAJMAL BHAVSINGH CHUKNI KHEDA ) CHUKNI | Physically Completed | 147621.16 | 140904 | 2025-06-14 | 2026-04-16
NEEMUCH / MANASA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003082/IF/9993690495 — कपिलधारा कुप निर्माण निर्मल कुमार विनोद कुमार पिता रतनलाल कुल्‍मी ts no 671 | Completed | 382000 | 381727 | 2015-12-01 | 2016-09-29
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/3675348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116340902 | Completed | 18360 | 18360 | 2022-06-20 | 2022-10-07
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/3675352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116341223 | Completed | 18360 | 18360 | 2022-06-20 | 2022-10-07
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/3842027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117032301 | Completed | 18360 | 18360 | 2022-06-20 | 2022-10-07
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/411753 — Construction of IAY House -IAY REG. NO. MP1279883 | Completed | 15030 | 14964 | 2017-04-08 | 2017-11-28
NEEMUCH / MANASA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/4166926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117639888 | Completed | 18360 | 18360 | 2022-06-22 | 2022-10-07
NEEMUCH / MANASA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/439891 — Construction of IAY House -IAY REG. NO. MP1465634 | Completed | 15030 | 14986 | 2017-03-10 | 2017-06-19
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/4571252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117040961 | Completed | 23490 | 22122 | 2025-01-11 | 2025-05-09
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/4974154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119981661 | Completed | 23490 | 23490 | 2025-05-13 | 2025-07-04
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/4998003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116299109 | Completed | 23490 | 23490 | 2025-06-19 | 2025-08-26
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/4998069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116319528 | Approved | 23490 | 0 | 2025-02-19
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/4998073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116319850 | Approved | 23490 | 0 | 2025-02-19
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/4998902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116352116 | Completed | 23490 | 23490 | 2026-01-16 | 2026-03-26
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/4999988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117031830 | Completed | 23490 | 23490 | 2025-05-13 | 2025-07-04
NEEMUCH / MANASA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/4999994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117040545 | Approved | 23490 | 0 | 2025-02-19
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5008217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119686742 | Completed | 23490 | 23229 | 2025-06-04 | 2025-10-31
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5008219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119687346 | Completed | 23490 | 23490 | 2025-05-13 | 2025-09-29
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5008220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119687607 | Completed | 23490 | 23490 | 2025-05-25 | 2025-07-04
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5010272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119692543 | Completed | 23490 | 23490 | 2025-06-19 | 2026-02-26
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5083757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126844384 | Completed | 23490 | 23490 | 2025-05-13 | 2025-07-04
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5687941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122125951 | Completed | 23490 | 22968 | 2025-08-03 | 2025-10-31
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5687949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116319727 | Approved | 23490 | 0 | 2025-05-17
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5687960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116319312 | Completed | 23490 | 23490 | 2025-08-03 | 2026-02-26
NEEMUCH / MANASA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5687961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119692296 | Completed | 23490 | 23490 | 2025-09-05 | 2026-03-26
NEEMUCH / MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5918893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116351837 | Ongoing | 23490 | 4698 | 2026-06-03
NEEMUCH / MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5920248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119691958 | Ongoing | 23490 | 9396 | 2026-05-20
NEEMUCH / MANASA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/5931742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126839967 | Ongoing | 23490 | 4698 | 2026-06-03
NEEMUCH / MANASA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/59992 — Construction of IAY House -IAY REG. NO. MP-41-003-082-001/31 | Completed | 14310 | 14143 | 2016-04-06 | 2017-06-21
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/857525 — Construction of IAY House -IAY REG. NO. MP1581736 | Completed | 15480 | 14964 | 2017-09-10 | 2017-12-12
NEEMUCH / MANASA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1741003082/IF/IAY/978807 — Construction of IAY House -IAY REG. NO. MP3832873 | Completed | 15480 | 14964 | 2017-09-10 | 2017-12-12
NEEMUCH / MANASA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003082/IF/Ts.No-619 — कपि‍ल धारा कंवरलाल पन्‍नालाल Ts.no 619 (चुकनी) | Completed | 193000 | 200651 | 2011-06-04 | 2012-06-15
NEEMUCH / MANASA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1741003082/IF/कपि‍लधारा घीसालाल भावसि‍ह बंजारा बस् — कपि‍लधारा घीसालाल भावसि‍ह बंजारा बस्‍ती (चुकनी) | Completed | 187000 | 187000 | 2010-02-04 | 2010-05-05
NEEMUCH / MANASA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1741003082/LD/22012034228931 — शांतिधाम विकास कार्य बाउन्‍डरीवाल निर्माण ts no 211 चुकनी | Completed | 658000 | 657821.9 | 2015-09-23 | 2016-09-29
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1741003082/LD/22012034238161 — शांतिधाम विकास बाउन्‍डरीवाल निर्माण ts no 661 चुकनी | Completed | 145000 | 132536 | 2015-12-13 | 2017-04-11
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1741003082/LD/22012034303246 — शांतिधाम विकास टीन शेड निर्माण चुकनी खेडा टीएस 563 | Completed | 180000 | 172871.13 | 2017-04-03 | 2017-12-20
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1741003082/LD/22012034358413 — शांतिधाम टीन शेड निर्माण चुकनी | Completed | 180000 | 174974.11 | 2017-08-30 | 2017-12-20
NEEMUCH / MANASA | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1741003082/LD/3799433836 — मुक्‍ितधाम परिसर समतलीकरण कार्य ts no 195 चुकनी | Completed | 200000 | 198186 | 2014-09-23 | 2015-03-25
NEEMUCH / MANASA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/135 — पंचमरमेश्‍वर आंतरि‍क पथ सी सी रोड Ts 135 EE चुकनी | Completed | 147000 | 147320 | 2012-10-15 | 2013-10-11
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034171409 — पंचपरमेश्‍वर आंतरिक पथ सीसी रोड पशु ओषधालय से देवक | Completed | 11500 | 11282 | 2013-06-18 | 2013-10-10
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034187348 — आंतरिक पथ सी सी रोड देवकिशन कुम्‍हार के मकान से दे | Completed | 19800 | 19366 | 2013-09-30 | 2013-10-10
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034187356 — आंतरिक पथ सी सी रोड चुकनीखेडा ग्राम के मेड से पानी | Completed | 167000 | 166756 | 2013-10-01 | 2015-06-12
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034212248 — आंतरिक पथ सी सी रोड निर्माण सुरेश सेन के मकान से ब | Completed | 51300 | 51124 | 2014-03-06 | 2014-06-12
NEEMUCH / MANASA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003082/RC/22012034212837 — ख्‍ेात सडक योजना अंतर्गत रामप्रसाद तुलसीराम के खेत से गणेशराम गेंदमल के खेत कि और सडक चुकनी | Deleted | 1395000 | 0 | 2014-07-08
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034289681 — आंतरिक पथ सी सी रोड निर्माण कचरूलाल के मकान से मांगीलाल पाटीदार के मकान की ओर ts no 662 | Completed | 121000 | 120628 | 2016-05-30 | 2017-07-18
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003082/RC/22012034289683 — खेत सडक योजनान्‍तर्गत शांतिलाल बंजारा के खेत से चतराजी बंजारा के खेत तक ts no 620 | Completed | 1374000 | 169755 | 2015-12-26 | 2017-02-17
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003082/RC/22012034289685 — खेत सडक योजनान्‍तर्गत प्‍यारचंद पाटीदार के खेत से शांतिलाल बंजारा के खेत तक ts no 619 | Completed | 425000 | 127808 | 2015-12-27 | 2017-02-17
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034301616 — आंतरिक पथ सी सी रोड निर्माण | Deleted | 0 | 0 | 2016-04-01
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034322484 — आंतरीक पथ सी सी रोड मांगीलाल रतनलाल के मकान से विष्‍णु कुमार रामप्रसाद के मकान तक | Deleted | 0 | 0 | 2016-10-02
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034329889 — आंतरिक पथ सी सी रोड निर्माण घनश्‍याम के मकान से दुध डैयरी की ओर टीएस 331 | Completed | 49206 | 49012.98 | 2017-10-30 | 2018-03-16
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034330596 — आंतरिक पथ सी सी रोड निर्माण न्‍युडीपीआर चुकनी | Completed | 533984 | 176038 | 2017-03-29 | 2019-07-29
NEEMUCH / MANASA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034365490 — आंतरिक पथ सी सी रोड निर्माण घनश्‍याम के मकान से दुध डेयरी की ओर टीएस 331 | Deleted | 49206 | 0 | 2016-10-02
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034372738 — CC ROAD NIRMAN | Closed | 0 | 0 | 2017-04-15
NEEMUCH / MANASA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003082/RC/22012034382348 — सुदुर ग्राम सडक निर्माण कार्य चुकनी से चुकनी खेडा तक टीएस 118 | Closed | 1785000 | 0 | 2017-04-15
NEEMUCH / MANASA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034435111 — CC ROAD NIRMAN | Closed | 0 | 0 | 2019-04-01
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034435413 — डीपीआर सी सी रोड मांगुदास जी के मकान से मांगीलाल छगनलालजी के मकान तक चुकनी | Completed | 37990 | 37308 | 2019-03-09 | 2020-02-16
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034444228 — DPR CC ROAD ( BADRI LAL BHWAR LAL KAI MAKAN SEY GAV WALEY HANMAN MANDIR TAK ) CHUKNI | Completed | 11850 | 11788 | 2019-03-09 | 2020-11-25
NEEMUCH / MANASA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034444230 — DPR CC ROAD ( HEDPUMP SEY GOPAL MANGI LAL KAI MAKAN TAK ) CHUKNI | Completed | 23250 | 23054 | 2019-03-09 | 2020-02-16
NEEMUCH / MANASA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034543198 — CC ROAD NIRMAN ( PURALAL PATIDAR KAI MAKAN SY SURESH CARPENTAR KAI MAKAN TAK ) CHUKNI | Completed | 62000 | 61560 | 2020-11-05 | 2021-12-01
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034594477 — CC ROAD NIRMAN ( MOHANLAL RATHOR KAI MAKAN SY RAMKRISHN PATIDAR KAI MAKAN TAK ) CHUKNI | Completed | 11000 | 10808 | 2021-11-17 | 2022-02-23
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034594479 — CC ROAD NIRMAN ( SHYAM SUTAR KAI MAKAN SY PULIYA TK OR DEVKISHAN K MAKAN SY HEERALAL K MAKAN TK ) | Completed | 7500 | 7334 | 2021-11-21 | 2022-02-23
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034595227 — NALI NIRMAN ( PATIDAR DHARMSHALA SY SUBHASH KAI MAKAN TAK ) CHUKNI | Ongoing | 70000 | 16959 | 2021-12-06
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034604573 — CC ROD V NALI NIRAMN (DASHARTH KE MAKAN SE BALLA CHANDA KE MAKAN TAK ) CHUKNI KHEDA | Completed | 14000 | 13996 | 2022-02-14 | 2022-04-02
NEEMUCH / MANASA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1741003082/RC/22012034634482 — SUDUR SADAK NIRMAN ( CHUKNI SE PALESHWAR MHADEV TAK ) CHUKNI | Ongoing | 1135520.58 | 1070901.8 | 2023-05-25
NEEMUCH / MANASA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034641506 — CC ROAD NIRMAN ( GOMA BANJARA KE MAKAN SE JAGDISH BIHARI KE MAKAN TAK CHUKNI KHEDA ) CHUKNI | Completed | 120000 | 117612 | 2024-09-27 | 2025-03-20
NEEMUCH / MANASA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034823660 — CC ROAD NIRMAN ( PWD ROAD SE RAJU BHAVSINGH KE MAKAN KI OR ) CHUKNI | Completed | 50500 | 47871 | 2024-11-12 | 2025-03-20
NEEMUCH / MANASA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034825142 — CC ROAD NIRMAN ( KARAN SINGH KE MAKAN SE JORSING KE MAKAN KI OR ) CHUKNI | Completed | 24000 | 22599 | 2024-12-26 | 2025-03-20
NEEMUCH / MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034835417 — CC ROAD NIRMAN MLA ( PM ROAD SE KESHARIMAL KE MAKAN TAK OR KACHRULAL KE MAKAN SE SATYNARAYAN) CHUKNI | Ongoing | 191000 | 91350 | 2025-05-09
NEEMUCH / MANASA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034835775 — CC ROAD NIRMAN 5 VA VITTY ( BANSHILAL GURJAR KE MAKNA SE PARMANAND KE MAKAN KI OR) BANDA | Approved | 96000 | 0 | 2025-01-26
NEEMUCH / MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034835870 — CC ROAD NIRMAN 15 VITTY (NAGJI RAM KE MAKAN SE BALU KE MAKAN TAK) CHUKNI | Completed | 24000 | 23943.15 | 2025-05-16 | 2025-09-06
NEEMUCH / MANASA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/22012034848366 — CC ROAD NIRMAN 5 VITT (BAGDIRAM SE PRABHULAL KE MAKAN OR MANALAL KE MAKAN KI OR DINESH KE M ) CHUKNI | Approved | 22000 | 0 | 2025-06-14
NEEMUCH / MANASA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1741003082/RC/615 — पंचपरमेश्‍वर आंतरि‍क पथ प्रा स्‍कुल से भुरालाल के मकान तक Ts.no. 534 चुकनी | Completed | 110663 | 95804 | 2012-12-24 | 2013-03-06
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741003082/RS/22012034290435 — SHOCHALAY MUKUND NAGJIRAM TS NO 492/01 | Completed | 3180 | 3180 | 2015-10-27 | 2015-11-08
NEEMUCH / MANASA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1741003082/RS/22012034290437 — SHOCHALAY MANOHAR GANESHRAM TS NO 492/02 | Completed | 3180 | 3180 | 2015-10-27 | 2015-11-08
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1741003082/RS/22012034607135 — C.C. NALI NIRMAN (PATIDAR DHARMSHALA SE SUBHASH KE MAKAN TAK) | Closed | 0 | 0 | 2021-08-16
NEEMUCH / MANASA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1741003082/SK/1226 — Bharat Nirman Rajeev Gandhi Sewa Kendra,CHUKNI | Deleted | 1285000 | 0 | 2013-10-05
NEEMUCH / MANASA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003082/WC/22012034446496 — SOCH PIT NIRMAN ( RAJU BAPULAL K MAKAN K PAS HANPUMP K PAS 01 ) CHUKNIKHEDA | Suspended | 13304.93 | 174 | 2019-03-09
NEEMUCH / MANASA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003082/WC/22012034446497 — SOCH PIT NIRMAN ( GOPAL PARTHA K MAKAN K PAS HANDPUPM K PAS 02 ) CHUKNIKHEDA | Suspended | 13304.93 | 174 | 2019-03-09
NEEMUCH / MANASA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034521662 — SOCH PIT NIRMAN ( SCHOL PRISAR KAI PAAS) CHUKNIKHEDA | Completed | 13427.24 | 13141.93 | 2020-02-06 | 2020-08-28
NEEMUCH / MANASA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034521663 — SOCH PIT NIRMAN ( AAGANWADI BHAWAN KAI PAS) CHUKNI | Completed | 13427.24 | 13141.93 | 2020-01-29 | 2020-08-28
NEEMUCH / MANASA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1741003082/WC/22012034551470 — TALAB KI PAAL RESACTIONING NIRMAN ( CHUKNI KHEDA ROAD PAR ) CHUKNI | Completed | 81240.54 | 79592.29 | 2020-05-22 | 2022-04-11
NEEMUCH / MANASA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1741003082/WC/22012034688823 — CTR NALA TRENCHING NIRMAN ( CHUKNI ) | Completed | 205277.78 | 203220.87 | 2021-05-17 | 2022-04-11
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034824117 — CTR/SLWM SOAK PIT NIRMAN(GRAM PANCHAYAT CHUKNI01) | Completed | 14467.3 | 13896 | 2021-09-16 | 2022-02-23
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034824121 — CTR/SLWM SOAK PIT NIRMAN(GRAM PANCHAYAT CHUKNI02) | Completed | 14467.3 | 13896 | 2021-09-16 | 2022-02-23
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034824132 — CTR/SLWM SOAK PIT NIRMAN(GRAM PANCHAYAT CHUKNI03) | Completed | 14467.3 | 13896 | 2021-09-16 | 2022-02-23
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034824136 — CTR/SLWM SOAK PIT NIRMAN(GRAM PANCHAYAT CHUKNI04) | Deleted | 14467.3 | 193 | 2021-09-16
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034824138 — CTR/SLWM SOAK PIT NIRMAN(GRAM PANCHAYAT CHUKNI05) | Completed | 14467.3 | 13896 | 2021-09-16 | 2022-02-23
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034824251 — CTR/SLWM SOAK PIT NIRMAN(GRAM PANCHAYAT CHUKNI06) | Deleted | 14467.3 | 193 | 2021-09-16
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034824252 — CTR/SLWM SOAK PIT NIRMAN(GRAM PANCHAYAT CHUKNI07) | Closed | 14467.3 | 0 | 2021-04-01
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034824253 — CTR/SLWM SOAK PIT NIRMAN(GRAM PANCHAYAT CHUKNI08) | Closed | 14467.3 | 0 | 2021-04-01
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034824254 — CTR/SLWM SOAK PIT NIRMAN(GRAM PANCHAYAT CHUKNI09) | Closed | 14467.3 | 0 | 2021-04-01
NEEMUCH / MANASA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1741003082/WC/22012034824255 — CTR/SLWM SOAK PIT NIRMAN(GRAM PANCHAYAT CHUKNI10) | Closed | 14467.3 | 0 | 2021-04-01
NEEMUCH / MANASA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1741003082/WC/22012034982972 — CTR NALA TRENCHING NIRMAN ( PURQNMAL PATIDAR KE KHET KE PASS) CHUKNI | Closed | 0 | 0 | 2022-04-14
NEEMUCH / MANASA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1741003082/WC/22012035118216 — ROOF TOP RAIN WATER HARVESTING STRUCTURE ( PANCHAYAT CHUKANI) CHUKANI | Closed | 34981.84 | 0 | 2023-08-16
NEEMUCH / MANASA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1741003082/WC/22012035145574 — RFR NALA (DRENEJ CHENAL NIRMAN BAPULAL BANJARA KE MAKAN SE CHHOTU BANJARA KE MAKAN TAK CHUKNIKHEDA | Completed | 370000 | 363422.01 | 2024-03-13 | 2025-03-20
NEEMUCH / MANASA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1741003082/WC/22012035173274 — PARCOLATION TANK NIRMAN | New | 0 | 0 | 2024-04-01
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1741003082/WC/22012035294879 — DUG WELL RECHARGE PIT ( SHASHKIY KUP KE PAS KHEDA CHUKANI ) CHUKANI | Approved | 25899.46 | 0 | 2025-04-24
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1741003082/WC/22012035294893 — DUG WELL RECHARGE PIT ( SHASHKIY KUP KE PAS ) CHUKANI | New | 0 | 0 | 2025-04-24
NEEMUCH / MANASA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1741003082/WC/22012035294908 — DUG WELL RECHARGE PIT ( SHASHKIY KUP KE PAS) CHUKANI | Approved | 25899.46 | 0 | 2025-04-24
NEEMUCH / MANASA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1741003082/WC/9993663997 — निर्मल नीर कुप निर्माण शांतिधाम परिसर ts no 1310 | Completed | 540000 | 539469.9 | 2016-01-12 | 2017-07-18
NEEMUCH / MANASA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1741003082/WH/22012034439358 — TALAB REPARINING NIRMAN ( CHUKNI KA KHEDA RASTEY PAR ) CHUKNI | Closed | 0 | 0 | 2019-01-26
NEEMUCH / MANASA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1741003/IF/22012034592398 — nijikhet vraksharopan pema bala banjara | Physically Completed | 289800 | 114162.5 | 2020-09-19 | 2026-06-10