## Work List
Exported on: 2026-10-16 17:16:09
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BHANDARDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BARWANI / BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Sericulture-Comm / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1742001010/DP/22012034561842 — वृक्षारोपण कार्य अमृत सरोवर तालाब स्थल भेंडा बयड़ा धामोडी | Ongoing | 713000 | 0 | 2022-10-13
BARWANI / BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Sericulture-Comm / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1742001010/DP/22012034561865 — वृक्षारोपण कार्य अमृत सरोवर तालाब के पास जडाखाऊ भंडारादा | Ongoing | 713000 | 0 | 2022-10-13
BARWANI / BARWANI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742001010/IF/22012034514697 — KAPIL DHARA SURMA BAI BALIRAM | Ongoing | 234458.62 | 12600 | 2020-02-11
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742001010/IF/22012035294682 — Kapil dhara kup Nirman Kary Lakhan Bhangi gram Jadakhau | New | 0 | 0 | 2024-10-02
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1742001010/IF/22012035319840 — Khet Talab Nirman kary Haresing Bamniya | New | 0 | 0 | 2025-04-01
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035590670 — एक बगिया माँ के नाम गड़ावटी हवलसिंग जड़ाखाऊ भंडारदा | Ongoing | 271689.33 | 8700 | 2025-09-07
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035590674 — एक बगिया माँ के नाम कविता बाई तकलिया भंडारदा | Ongoing | 277565.33 | 2400 | 2025-09-07
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035590680 — एक बगिया माँ के नाम राली दुवालसिंग भंडारदा | Ongoing | 277565.33 | 2400 | 2025-09-07
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035593344 — एक बगिया माँ के नाम गीता बाई अनिल जमरे जड़ाखाऊ भंडारदा | Ongoing | 277565.33 | 7500 | 2025-09-07
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035609285 — ek bagiya maa ke naam 54095 khurpi bai bhandarda | Ongoing | 178816.67 | 300 | 2025-09-07
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035609312 — ek bagiya maa ke naam 54335 rela bai alave jadakhau | Ongoing | 277565.33 | 4800 | 2025-09-07
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035611326 — ek bagiya maa k naam sayda bai bhandarda 28330 | Approved | 277565.33 | 0 | 2025-08-15
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035620559 — ek bagiya maa ke naam baati bai bhandarda 79663 | New | 0 | 0 | 2025-08-15
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035620697 — ek bagiya maa k naam baati bai tadoli bhandarda 79663 | New | 0 | 0 | 2025-08-15
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035620701 — ek bagiya maa k naam baati bai tadoli bhandarda 79663 | New | 0 | 0 | 2025-08-15
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035629225 — ek bagiya maa k naam jhumki bai bhandarda 39702 | New | 0 | 0 | 2025-08-15
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035635523 — ek bagiya maa k naam mukhali bai bhandarda 28330 | New | 0 | 0 | 2025-08-15
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001010/IF/22012035653846 — एक बगिया माँ के नाम मुखली बाई भंडारदा | New | 0 | 0 | 2025-04-14
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/4587799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120265694 | Physically Completed | 27000 | 0 | 2024-10-09 | 2026-09-10
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/4825032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122391949 | Ongoing | 27000 | 0 | 2025-02-20
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/4828583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129471497 | Ongoing | 27000 | 0 | 2024-11-09
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/4832208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145387152 | Ongoing | 27000 | 0 | 2025-01-26
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/4832659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146843358 | Physically Completed | 27000 | 0 | 2024-11-09 | 2026-09-10
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/4834520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150713469 | Physically Completed | 23490 | 0 | 2024-11-24 | 2026-07-19
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/4860397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129456862 | Physically Completed | 27000 | 0 | 2024-12-31 | 2026-09-10
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5457226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129527310 | Physically Completed | 27000 | 15600 | 2025-06-18 | 2026-09-22
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5457738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125762619 | Ongoing | 27000 | 0 | 2025-06-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5457740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125766755 | Physically Completed | 27000 | 0 | 2025-06-18 | 2026-09-22
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5458378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129762695 | Ongoing | 27000 | 0 | 2025-06-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5458584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126213186 | Physically Completed | 23490 | 0 | 2025-04-24 | 2026-08-23
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5458868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129693805 | Physically Completed | 27000 | 0 | 2025-04-24 | 2026-09-10
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5460243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118096899 | Ongoing | 27000 | 0 | 2025-04-24
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5460292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129674614 | Ongoing | 27000 | 1827 | 2025-04-24
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5461473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126837165 | Ongoing | 27000 | 0 | 2025-04-24
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5461696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120081892 | Ongoing | 27000 | 0 | 2025-04-24
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5463239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125845768 | Physically Completed | 23490 | 0 | 2025-04-24 | 2026-07-26
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5464946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125842559 | Physically Completed | 23490 | 0 | 2025-04-24 | 2026-08-23
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5465240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126820066 | Ongoing | 27000 | 0 | 2025-04-24
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5465531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120054449 | Ongoing | 27000 | 0 | 2025-04-24
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5565111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125848003 | Ongoing | 27000 | 0 | 2025-06-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5593205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129723062 | Ongoing | 27000 | 0 | 2025-05-12
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5593254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129750635 | Physically Completed | 23490 | 0 | 2025-06-18 | 2026-08-09
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5593423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129459762 | Physically Completed | 23490 | 3850 | 2025-05-12 | 2026-08-09
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5595042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129540158 | Ongoing | 27000 | 1827 | 2025-05-12
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5595311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119865939 | Physically Completed | 27000 | 0 | 2025-05-12 | 2026-09-10
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5595390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126852225 | Physically Completed | 27000 | 0 | 2025-05-12 | 2026-09-10
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5595566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129518586 | Physically Completed | 23490 | 1827 | 2025-05-12 | 2026-07-26
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5638847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129678553 | Physically Completed | 23490 | 0 | 2025-06-18 | 2026-08-16
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5638850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129757659 | Ongoing | 27000 | 0 | 2025-07-30
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5639328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129572899 | Ongoing | 27000 | 0 | 2025-06-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5640477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126856979 | Ongoing | 27000 | 0 | 2025-06-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5641350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129743476 | Ongoing | 27000 | 1827 | 2025-06-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5641501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129547766 | Physically Completed | 27000 | 0 | 2025-06-18 | 2026-09-11
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5641534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129532943 | Physically Completed | 23490 | 0 | 2025-06-18 | 2026-07-12
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5642623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127583255 | Physically Completed | 23490 | 0 | 2025-06-18 | 2026-07-12
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5643205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130118895 | Physically Completed | 27000 | 1827 | 2025-06-18 | 2026-09-22
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5643206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150652070 | Ongoing | 27000 | 0 | 2025-06-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5643207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126816057 | Physically Completed | 23490 | 0 | 2025-06-18 | 2026-07-19
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5643208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129672669 | Ongoing | 27000 | 2100 | 2025-06-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5643785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126845695 | Physically Completed | 27000 | 0 | 2025-06-18 | 2026-09-11
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5643951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126730934 | Physically Completed | 27000 | 0 | 2025-06-18 | 2026-09-11
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5711640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125786506 | Physically Completed | 23490 | 0 | 2025-07-30 | 2026-08-23
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5711780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125784419 | Ongoing | 27000 | 0 | 2025-07-26
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5711848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126672060 | Physically Completed | 23490 | 0 | 2025-07-26 | 2026-07-19
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5712227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130105062 | Physically Completed | 23490 | 2100 | 2025-07-26 | 2026-07-19
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5731621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126831036 | Physically Completed | 27000 | 0 | 2025-08-13 | 2026-09-13
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5733194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129545710 | Physically Completed | 27000 | 780 | 2025-08-13 | 2026-09-11
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126806601 | Ongoing | 27000 | 0 | 2025-12-31
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126293775 | Physically Completed | 27000 | 0 | 2025-09-29 | 2026-10-04
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120922998 | Physically Completed | 27000 | 0 | 2025-09-29 | 2026-09-11
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129558894 | Physically Completed | 23490 | 0 | 2025-10-14 | 2026-08-23
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129695541 | Physically Completed | 23490 | 0 | 2025-10-01 | 2026-07-12
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129721749 | Ongoing | 27000 | 1827 | 2025-10-14
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129739298 | Physically Completed | 23490 | 0 | 2025-10-01 | 2026-07-12
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126833154 | Physically Completed | 27000 | 0 | 2025-10-14 | 2026-09-11
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129517608 | Ongoing | 27000 | 0 | 2025-12-31
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150651682 | Physically Completed | 27000 | 0 | 2025-10-19 | 2026-09-13
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150651836 | Ongoing | 27000 | 9000 | 2025-12-31
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126212338 | Physically Completed | 23490 | 0 | 2025-10-31 | 2026-07-05
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124538071 | Physically Completed | 23490 | 2100 | 2025-10-14 | 2026-07-12
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129705307 | Approved | 27000 | 0 | 2025-03-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130103519 | Physically Completed | 23490 | 0 | 2025-10-19 | 2026-07-19
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130118947 | Physically Completed | 27000 | 0 | 2025-10-01 | 2026-09-16
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129661354 | Physically Completed | 23490 | 0 | 2025-09-29 | 2026-07-19
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129733457 | Ongoing | 27000 | 0 | 2025-10-14
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129753036 | Ongoing | 27000 | 17400 | 2025-10-01
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120081441 | Ongoing | 27000 | 0 | 2025-11-06
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126803428 | Physically Completed | 23490 | 0 | 2025-10-14 | 2026-08-23
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125844952 | Ongoing | 27000 | 0 | 2025-10-19
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129736865 | Ongoing | 27000 | 0 | 2025-09-29
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129745924 | Ongoing | 27000 | 0 | 2025-09-29
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124876424 | Ongoing | 27000 | 0 | 2025-11-06
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5820991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129574044 | Ongoing | 27000 | 0 | 2025-11-06
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5861947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124658201 | Ongoing | 27000 | 0 | 2025-12-31
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/5970007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129566844 | Ongoing | 27000 | 0 | 2026-03-18
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6122718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119871457 | Physically Completed | 27000 | 10480 | 2026-05-18 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6125819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126800758 | Ongoing | 27000 | 6600 | 2026-06-02
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6126891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120021966 | Ongoing | 27000 | 14100 | 2026-04-15
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6131056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130118251 | Physically Completed | 27000 | 7266 | 2026-04-15 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6131057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130118344 | Physically Completed | 27000 | 8532 | 2026-04-15 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6131058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130118972 | Physically Completed | 27000 | 2400 | 2026-04-15 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6131059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130119013 | Physically Completed | 27000 | 6000 | 2026-04-15 | 2026-09-16
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6136030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125278854 | Ongoing | 27000 | 14232 | 2026-05-03
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6147074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119814931 | Approved | 27000 | 0 | 2026-01-20
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6147075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119814964 | Physically Completed | 27000 | 1200 | 2026-04-15 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6147078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119815432 | Physically Completed | 27000 | 7266 | 2026-04-15 | 2026-09-16
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6149130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130103772 | Physically Completed | 27000 | 7266 | 2026-04-15 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6149185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120021646 | Physically Completed | 27000 | 8832 | 2026-04-15 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6149347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125765287 | Physically Completed | 27000 | 13032 | 2026-04-15 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6150220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119577513 | Physically Completed | 23490 | 7632 | 2026-04-15 | 2026-08-16
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6151380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132243470 | Physically Completed | 27000 | 1200 | 2026-04-15 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6153475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150651235 | Ongoing | 27000 | 4500 | 2026-05-03
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6153501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119576888 | Ongoing | 27000 | 21900 | 2026-07-22
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6156794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130118654 | Physically Completed | 27000 | 7266 | 2026-04-15 | 2026-09-22
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6156795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130118785 | Physically Completed | 27000 | 7266 | 2026-04-15 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6156997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120022863 | Physically Completed | 27000 | 12666 | 2026-05-03 | 2026-09-16
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6157495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119576037 | Physically Completed | 27000 | 10032 | 2026-05-03 | 2026-09-13
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6161958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119815135 | Physically Completed | 23490 | 6066 | 2026-04-15 | 2026-08-09
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6161959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119815148 | Physically Completed | 23490 | 7632 | 2026-04-15 | 2026-08-09
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6161960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119815190 | Physically Completed | 27000 | 2766 | 2026-04-15 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6162734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120081362 | Physically Completed | 27000 | 10932 | 2026-04-15 | 2026-09-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6163845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120794148 | Ongoing | 27000 | 20100 | 2026-05-03
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6164258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126825331 | Ongoing | 27000 | 2400 | 2026-04-15
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6164263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119872293 | Physically Completed | 23490 | 0 | 2026-04-15 | 2026-08-02
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6257561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120255269 | Ongoing | 27000 | 0 | 2026-10-10
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6269308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129552801 | Approved | 27000 | 0 | 2025-05-30
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6280495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124463099 | Approved | 27000 | 0 | 2026-02-10
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6292142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145395890 | Approved | 27000 | 0 | 2024-09-27
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6301269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129553789 | Approved | 27000 | 0 | 2025-02-24
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6307487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120265966 | Approved | 27000 | 0 | 2026-02-10
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6308212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119866100 | Ongoing | 27000 | 0 | 2026-10-10
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6308219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130118696 | Approved | 27000 | 0 | 2026-03-29
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6308220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130118832 | Ongoing | 27000 | 0 | 2026-10-10
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6318793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129522920 | Ongoing | 27000 | 0 | 2026-10-10
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6318928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129543098 | Ongoing | 27000 | 0 | 2026-10-10
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6319593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129477972 | Ongoing | 27000 | 0 | 2026-10-10
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6319703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129573105 | Ongoing | 27000 | 0 | 2026-10-10
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6332543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125847286 | Ongoing | 27000 | 0 | 2026-10-10
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6335777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120023793 | Approved | 27000 | 0 | 2025-03-03
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6346743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132243488 | Ongoing | 27000 | 0 | 2026-10-10
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001010/IF/IAY/6403159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120080717 | Approved | 27000 | 0 | 2026-02-10
BARWANI / BARWANI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1742001010/WC/22012035031640 — सामुदायिक पोषण वाटीका निर्माण कार्य मायना बायडा हजारिया गरदन के घर के पास धमोड़ी | Ongoing | 1013295.22 | 0 | 2023-02-15
BARWANI / BARWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Horticulture -Community / Line Plantation of Horticulture Trees for Community | Plantation | 1742001010/WC/22012035093260 — पोषण वाटिका निर्माण कार्य प्रेमसिंह गानसिया के खेत पास Bhandarda | Ongoing | 979948.19 | 0 | 2023-08-07
BARWANI / BARWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1742001010/WC/22012035137462 — SCT&CPT NIRMAN KARYA JADAKHAU GP BHANDARDA | Ongoing | 812784.93 | 87900 | 2023-10-08