## Work List
Exported on: 2026-10-05 15:11:57
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BORI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BARWANI / BARWANI | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1742001016/AV/22012034625344 — पंचायत भवन निर्माण बोरी | Physically Completed | 482000 | 0 | 2023-03-02 | 2026-07-29
BARWANI / BARWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1742001016/DP/22012034617613 — वृक्षारोपण कार्य माता मंदिर पास बोरी | Ongoing | 422466.87 | 0 | 2024-07-05
BARWANI / BARWANI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742001016/IF/22012034632515 — Kapil Dhara Koop Nirman Kary Narag Miyya Bori | Ongoing | 246126.86 | 0 | 2021-06-30
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1742001016/IF/22012035576546 — FRA GOAT SHELTER NIRMAN SURSIYA RAJAN BORI | Approved | 60089.99 | 0 | 2025-04-01
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1742001016/IF/22012035576548 — FRA GOAT SHELTER NIRMAN PARSIYA GYANSING BORI | Approved | 60089.99 | 0 | 2025-04-01
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1742001016/IF/22012035576551 — FRA CATTLE SHELTER NIRMAN BALA BHAYA BORI | Approved | 132146.51 | 0 | 2025-04-01
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001016/IF/22012035588969 — Ek Bagiya Maa ke name SAVATI CHIMA MP-42-001-016-001/237 BORI | Approved | 277244.92 | 0 | 2025-08-01
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001016/IF/22012035588985 — Ek Bagiya Maa ke name SIKHARI SHANTILALA MP-42-001-016-001/191-A BORI | Approved | 277565.33 | 0 | 2025-08-01
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001016/IF/22012035612504 — ek bagiya maa k naam shantu bai bori 318056 | Ongoing | 277565.33 | 0 | 2025-09-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001016/IF/22012035615753 — ek bagiya maa k naam gina barela bori 61947 | Ongoing | 277565.33 | 4500 | 2025-09-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742001016/IF/22012035618576 — ek bagiya maa k naam kamalibai bori 73505 | Ongoing | 277565.33 | 4500 | 2025-09-18
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742001016/IF/22012035630232 — FRA Kapil Dhara Kup Nirman Kary Ranchhod Gutiya Bori | Approved | 0 | 0 | 2025-10-02
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742001016/IF/22012035630241 — FRA Kapil Dhara Kup Nirman Kary Kalariya Kishan Bori | Approved | 0 | 0 | 2025-10-02
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742001016/IF/22012035630255 — FRA Kapil Dhara Kup Nirman Kary Santa Chandrasingh Bori | Approved | 0 | 0 | 2025-10-02
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742001016/IF/22012035630259 — FRA Kapil Dhara Kup Nirman Kary Supariya Damjya Bori | Approved | 0 | 0 | 2025-10-02
BARWANI / BARWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001016/IF/IAY/4891779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129770571 | Ongoing | 27000 | 0 | 2025-03-11
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001016/IF/IAY/5456829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127845813 | Ongoing | 27000 | 0 | 2026-06-03
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001016/IF/IAY/5461477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127851891 | Physically Completed | 27000 | 4200 | 2026-02-24 | 2026-09-07
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001016/IF/IAY/5462428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131986420 | Physically Completed | 27000 | 8700 | 2025-04-26 | 2026-09-21
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001016/IF/IAY/5463081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127824268 | Ongoing | 27000 | 0 | 2026-05-12
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001016/IF/IAY/5595334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125671712 | Physically Completed | 23490 | 0 | 2025-12-09 | 2026-07-31
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001016/IF/IAY/5641498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131988910 | Physically Completed | 27000 | 7000 | 2026-02-24 | 2026-08-31
BARWANI / BARWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001016/IF/IAY/5735281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129764231 | Physically Completed | 27000 | 2800 | 2026-01-16 | 2026-08-31
BARWANI / BARWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742001016/IF/IAY/6136249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128380621 | Ongoing | 27000 | 7830 | 2026-06-03
BARWANI / BARWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1742001016/WC/22012035249041 — Bolder check dam nirman kary khaydiya faliya pahadi par bori | Approved | 488647.25 | 0 | 2025-01-26