## Work List
Exported on: 2026-10-23 19:36:18
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: AAWLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BARWANI / PATI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742002001/IF/22012034694450 — Hiteshi Kup Nirman Karya Mahangya ganja Aawali | Ongoing | 250732.62 | 0 | 2021-10-05
BARWANI / PATI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742002001/IF/22012034694457 — Hiteshi Kup Nirman Karya Chatarsing Tatya Aawali | Ongoing | 247839.67 | 0 | 2021-06-30
BARWANI / PATI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1742002001/IF/22012034864740 — Hiteshi Kup Nirman Kary Punibai Mohansing awali | Ongoing | 250732.62 | 0 | 2021-10-05
BARWANI / PATI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742002001/IF/22012035384519 — JGSA 2025 Recharge Structure Kapildhara Koop Gangaram Hirasingh Gram Awali | New | 0 | 0 | 2025-04-14
BARWANI / PATI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742002001/IF/22012035434604 — JGSA 2025 RECHARGE STRUCTURE KAPILDHARA GANGARAM HIRA AAWALI | Approved | 0 | 0 | 2025-04-14
BARWANI / PATI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742002001/IF/22012035435291 — JGSA 2025 RECHARGE STRUCTURE KAPILDHARA CHATARSINGH TATYA AAWALI | New | 0 | 0 | 2025-04-14
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1742002001/IF/22012035526777 — Construction Of Farm Ponds For Begam Kashiram Gp Aawli | Approved | 0 | 0 | 2025-04-14
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742002001/IF/22012035597175 — Ek Bagiya Maa Ke Nam Gurliya Bai Ganga SHG GP Awli | Ongoing | 284196.18 | 0 | 2025-08-29
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742002001/IF/22012035618630 — Ek Bagiya Maa Ke Name Rupli Bai Laxmee SHG GP Awali | Ongoing | 263510.03 | 0 | 2025-10-09
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742002001/IF/22012035618637 — Ek Bagiya Maa Ke Name Khiyali Laxmee SHG GP Awali | Ongoing | 263510.03 | 0 | 2025-10-09
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742002001/IF/22012035618643 — Ek Bagiya Maa Ke Name Nanti Bai Barela Laxmee SHG GP Awali | Ongoing | 263510.03 | 0 | 2025-10-17
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742002001/IF/22012035618650 — Ek Bagiya Maa Ke Name Shivani Ita SHG GP Awali | Ongoing | 263510.03 | 0 | 2025-10-01
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742002001/IF/22012035631347 — Ek Bagiya Maa Ke Nam RUPLI BAI LAXMEE SHG GP AAWLI | New | 0 | 0 | 2025-08-15
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742002001/IF/22012035631361 — Ek Bagiya Maa Ke Nam RUPALI BAI WASKALE MAA DURGA DEV SHG GP AAWLI | Ongoing | 271690.7 | 0 | 2025-10-22
BARWANI / PATI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/4020366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128082282 | Physically Completed | 23490 | 0 | 2023-11-23 | 2026-07-19
BARWANI / PATI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/4703856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120559080 | Completed | 23490 | 0 | 2024-11-05 | 2026-08-03
BARWANI / PATI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/4715942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129896884 | Ongoing | 27000 | 0 | 2024-11-20
BARWANI / PATI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/4715945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129898946 | Physically Completed | 27000 | 0 | 2024-11-20 | 2026-10-04
BARWANI / PATI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/4717130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129436826 | Ongoing | 27000 | 0 | 2024-12-23
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5514542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128079233 | Completed | 23490 | 1566 | 2025-05-19 | 2026-08-23
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5514915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129496428 | Physically Completed | 27000 | 3600 | 2025-05-19 | 2026-09-01
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5515169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129901111 | Physically Completed | 27000 | 0 | 2025-05-18 | 2026-09-21
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5515172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129905904 | Completed | 23490 | 1566 | 2025-05-19 | 2026-08-23
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5515327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119904461 | Ongoing | 27000 | 0 | 2025-05-19
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5515408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120558822 | Completed | 23490 | 0 | 2025-05-19 | 2026-08-03
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5515459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129493447 | Completed | 23490 | 0 | 2025-05-19 | 2026-08-03
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5515954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119621996 | Physically Completed | 27000 | 6000 | 2026-02-23 | 2026-09-21
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5530343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120567261 | Physically Completed | 27000 | 1800 | 2025-05-19 | 2026-09-13
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5582177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129907847 | Physically Completed | 27000 | 0 | 2026-02-10 | 2026-09-06
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5582497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129907733 | Completed | 23490 | 0 | 2026-02-10 | 2026-08-03
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5612306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131404761 | Physically Completed | 27000 | 2610 | 2026-02-10 | 2026-09-21
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5612880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129910327 | Ongoing | 27000 | 2610 | 2026-02-10
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5613316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129897819 | Physically Completed | 27000 | 2871 | 2026-02-10 | 2026-09-21
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5613838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129900560 | Physically Completed | 27000 | 0 | 2026-02-11 | 2026-09-21
BARWANI / PATI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5645650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129905140 | Ongoing | 27000 | 0 | 2026-05-19
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5715475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129905781 | Physically Completed | 27000 | 0 | 2026-02-18 | 2026-09-21
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5715476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129906282 | Physically Completed | 27000 | 2871 | 2026-02-11 | 2026-09-21
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5715480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129910840 | Physically Completed | 27000 | 0 | 2026-02-11 | 2026-09-21
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/5732953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129595775 | Completed | 23490 | 1827 | 2026-02-11 | 2026-08-23
BARWANI / PATI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/6180885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129902481 | Physically Completed | 27000 | 3654 | 2026-04-21 | 2026-10-11
BARWANI / PATI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/6270583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129521935 | Ongoing | 27000 | 8400 | 2026-10-08
BARWANI / PATI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/6270612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129908980 | Approved | 27000 | 0 | 2025-03-17
BARWANI / PATI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/6303020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121955235 | Ongoing | 27000 | 8400 | 2026-10-08
BARWANI / PATI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/6303022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124493354 | Ongoing | 27000 | 8400 | 2026-10-08
BARWANI / PATI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/6355667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125474573 | Approved | 27000 | 0 | 2026-05-02
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742002001/IF/IAY/6356079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129606968 | Approved | 27000 | 0 | 2025-07-08
BARWANI / PATI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1742002001/WC/22012034443310 — Nirmal Neer UPYojana Payjal kup Nirman Handi Baidi Gram Awali (4.45) | Ongoing | 445000 | 0 | 2019-03-02
BARWANI / PATI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1742002001/WC/22012034596221 — Community Farm Pond Work Misriya-Fulsingh Ke Ghar pass, GP Aawali | Physically Completed | 332962.02 | 0 | 2020-12-25 | 2026-08-18
BARWANI / PATI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1742002001/WC/22012034596222 — Community Farm Pond Work Revsingh Munna Ke Khet pass, GP Aawali | Physically Completed | 332962.02 | 0 | 2020-12-25 | 2026-07-28
BARWANI / PATI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair & Maintenance of Percolation Tank for Community | Repair & maint of Percolation Tank | 1742002001/WC/22012034968837 — TALAB RENOVATION WARTI FALYA AWALI (1.88) | Ongoing | 109000 | 0 | 2022-05-13
BARWANI / PATI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1742002001/WC/22012035172344 — Galy Plug Nirman Karya GP Aawali | New | 0 | 0 | 2024-01-27
BARWANI / PATI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1742002001/WC/22012035233849 — Sct/cpt Nirman Karya Dufariya Nana ke ghar pas Aawali | Approved | 486446.84 | 0 | 2024-11-15
BARWANI / PATI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1742002001/WC/22012035317642 — Gullyi Plug Nirman Kary Ratiya Gelsingh Ghar Pass Aawali | Approved | 0 | 0 | 2025-04-24
BARWANI / PATI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1742002001/WC/22012035317643 — Gullyi Plug Nirman Kary Ratiya Gelsingh Ghar Pass Aawali | Approved | 473711.37 | 0 | 2025-04-24
BARWANI / PATI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1742002001/WC/22012035317645 — Gali Plug Nirman Kary RunaBai Khet Pass Aawali | Approved | 485118.89 | 0 | 2025-04-24
BARWANI / PATI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1742002001/WC/VB/22012035335536 — Loose Boulder check dam Fapa dalsingh k ghar k pass awali | Ongoing | 486876.42 | 375000 | 2026-09-25
BARWANI / PATI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1742002001/WC/VB/22012035335537 — Loose Boulder Check Dam Chichali bai k ghar k pass Awali | Ongoing | 445763.53 | 0 | 2026-10-01
BARWANI / PATI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1742002001/WC/VB/YD/22012035333975 — Construction of Staggered Trench mangliya Dalsingh k ghar k pass Awali | Ongoing | 491921.05 | 426913.41 | 2026-08-31
BARWANI / PATI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742002029/IF/22012035596287 — Ek Bagiya Maa Ke Nam Siyani Bai Durga SHG GP Awli | Ongoing | 284196.18 | 10800 | 2025-08-29