## Work List
Exported on: 2026-10-10 08:07:49
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: AVALI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BARWANI / THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Cyclone shelter for Community / Construction of Cyclone shelter for Community | Construction of Other Community Building/Assets | 1742003002/AV/22012034568485 — santi dham avali | Closed | 196981.11 | 0 | 2021-04-29
BARWANI / THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1742003002/AV/22012034568487 — baundriwall pani ki tanki se panchayat tak | Closed | 0 | 0 | 2021-04-29
BARWANI / THIKRI | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1742003002/AV/4396 — अन्गंवाडी भवन गोलाटा (अवली) | Completed | 283000 | 283056.25 | 2016-01-25 | 2018-12-24
BARWANI / THIKRI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1742003002/DP/1 — वृक्षारोपण (राजस्‍व भूमि) आवली | Completed | 200000 | 55229 | 2008-08-19 | 2010-08-17
BARWANI / THIKRI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1742003002/DP/2 — वृक्षारोपण (पूर्नवास स्‍थल) आवली | Completed | 200000 | 65113 | 2008-07-01 | 2010-07-17
BARWANI / THIKRI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1742003002/DP/22012034236209 — narmda prikrama path par wraksharopan golata | Completed | 732000 | 252532 | 2016-10-03 | 2019-07-21
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/DP/22012034240802 — vraksharopan golata phadi par | Completed | 535000 | 33800 | 2017-05-13 | 2019-07-21
BARWANI / THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov building Block Plantation-Farm Forestry-Comm / Block Plantation of Farm Forestry Trees in Government building premises for Community | Plantation | 1742003002/DP/22012034433161 — podharopan school parishar avali punrawash | Closed | 33500000000 | 0 | 2018-08-31
BARWANI / THIKRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1742003002/DP/22012034533475 — vraksharopan kabristhan golata | Closed | 169537.13 | 0 | 2021-04-14
BARWANI / THIKRI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1742003002/DP/22012034562483 — maa ki bagiya golata avali | Closed | 0 | 0 | 2022-07-25
BARWANI / THIKRI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1742003002/DP/22012034601554 — amrit vatika panchayat parisar | Closed | 55847.4 | 0 | 2023-04-14
BARWANI / THIKRI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1742003002/DP/3 — वृक्षारोपण (श्रीराम मंदिर केम्‍पस गोलाटा) आवली | Completed | 200000 | 59395 | 2008-06-25 | 2010-08-17
BARWANI / THIKRI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1742003002/DP/84 — नर्मदा परिक्रमा पथ (4.90 गोलाटा से छोटा बडदा मार्ग तक) आवली | Completed | 490000 | 192060 | 2013-03-05 | 2013-06-26
BARWANI / THIKRI | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1742003002/DP/9926699145 — नर्मदा परिक्रमा पथ गोलाटा से छोटा बडदा मार्ग आवली | Completed | 490000 | 148869.7 | 2013-03-24 | 2014-03-12
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034351292 — vraksaropan narmeda parikrema path | Completed | 335000 | 24408 | 2017-06-16 | 2019-07-21
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034351301 — vraksaropan hanuman mandir punerwas | Completed | 168000 | 117870 | 2017-06-16 | 2019-07-21
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034358708 — फलोद्यान परियोजना जीतेन्द्र हीरालाल + अन्नपूर्ण हीरालाल गोलाटा | Completed | 1046250 | 139399 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034358719 — फलोद्यान परियोजना साकिर बालू गोलाटा | Completed | 795847 | 117656 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034358722 — फलोद्यान परियोजना राजेंद्र हीरालाल गोलाटा | Completed | 551955 | 78192 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034358726 — फलोद्यान परियोजना महेश नानुराम गोलाटा | Completed | 290625 | 46376 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034358743 — फलोद्यान परियोजना कल्याण चन्दर गोलाटा | Completed | 145080 | 24064 | 2017-08-25 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034358746 — फलोद्यान परियोजना भीमसिंह रामसिंह गोलाटा | Completed | 348750 | 55726 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034358753 — फलोद्यान परियोजना जीतेन्द्र टन्टूसिंह गोलाटा | Completed | 251082 | 49464 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034358758 — फलोद्यान परियोजना प्रताप जट्टूसिंह गोलाटा | Completed | 436170 | 67304 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034358768 — फलोद्यान परियोजना अमृता बादामसिंह गोलाटा | Completed | 436170 | 69338 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034358772 — फलोद्यान परियोजना रामचंद्र हरेसिंह गोलाटा | Completed | 494295 | 81138.8 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034373949 — फलोद्यान परियोजना लीलाबाई गिरधारी + गिरधारी नथिया संदेवा (आंवली) | Completed | 435705 | 69652 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034373954 — फलोद्यान परियोजना प्रकाश गिरधारी | Completed | 232500 | 38572 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034373956 — फलोद्यान परियोजना राधेश्याम ओंकार संदेवा | Completed | 377580 | 60266 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034373958 — फलोद्यान परियोजना हिम्मतसिंह नत्थुसिंह संदेवा | Completed | 523125 | 83610 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034373961 — फलोद्यान परियोजना अंतरसिंह नत्थुसिंह संदेवा | Completed | 523125 | 78216 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034373962 — फलोद्यान परियोजना प्रह्लादसिंह नत्थुसिंह संदेवा | Completed | 523125 | 83634 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034374422 — फलोद्यान परियोजना बलराम कालूसिंह आंवली | Completed | 465000 | 60832 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003002/IF/22012034374424 — फलोद्यान परियोजना प्रह्लाद कालूसिंह आंवली | Completed | 465000 | 79450 | 2017-06-26 | 2020-09-25
BARWANI / THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1742003002/IF/22012034431976 — Plantation Work Khet Ki Med Par Prahlad Nattu Avali | Closed | 188000 | 0 | 2018-07-05
BARWANI / THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1742003002/IF/22012034431978 — plantation work khet Med Laxman khema Avali | Closed | 188000 | 0 | 2018-07-05
BARWANI / THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1742003002/IF/22012034431979 — plantation work Khet Ki Med Manoj Bhagawan Avali | Closed | 188000 | 0 | 2018-07-05
BARWANI / THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1742003002/IF/22012034431980 — plantation work Khet Ki Med Uma Tejgiri Avali | Closed | 188000 | 0 | 2018-07-05
BARWANI / THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1742003002/IF/22012034431981 — plantation work Neeji Khet par Jeevan bai Bhagawan Avali | Closed | 150800 | 0 | 2018-07-05
BARWANI / THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1742003002/IF/22012034433150 — plantation work Niji Khet Babulal Motilal Avali | Closed | 150800 | 0 | 2018-07-05
BARWANI / THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1742003002/IF/22012034433152 — plantation work Nijin Khet Par Lila Girdhar Avali | Closed | 150800 | 0 | 2018-07-05
BARWANI / THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1742003002/IF/22012034433154 — plantation work Niji Khet Durga radheshyam Avali | Closed | 150800 | 0 | 2018-07-05
BARWANI / THIKRI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1742003002/IF/22012034435289 — Plantaion Work Khet Ki Med par Jitendra Thunthu Golatha | Closed | 188000 | 0 | 2018-07-05
BARWANI / THIKRI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1742003002/IF/22012034439440 — podharopan med par budesingh sobhagsing | Closed | 188000 | 0 | 2018-08-15
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742003002/IF/22012034450265 — nadeb nirman amrsingh ratansingh golata | Completed | 41000 | 42394 | 2019-01-11 | 2020-09-23
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742003002/IF/22012034450270 — nadep nirman budesingh chohan golata | Completed | 41000 | 44152 | 2019-01-11 | 2020-09-23
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742003002/IF/22012034450271 — nadep nirman vikram juvansingh golata | Closed | 41000 | 0 | 2018-12-28
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742003002/IF/22012034450272 — nadep nirman mangilal rolji golata | Completed | 41000 | 25992 | 2019-01-11 | 2020-09-23
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742003002/IF/22012034450273 — nadep nirman ganesh shankar golata | Completed | 41000 | 35182 | 2019-01-11 | 2020-09-23
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742003002/IF/22012034450274 — nadep nirman lakhan rukhadiya | Closed | 41000 | 0 | 2018-12-28
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742003002/IF/22012034450275 — nadep nirman baliram anarsingh avali | Closed | 41000 | 0 | 2018-12-28
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742003002/IF/22012034450276 — nadep nirman devandr vishvkrma | Closed | 41000 | 0 | 2018-12-28
BARWANI / THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/22012034527120 — farm pond (khet talanb) balu najir kha | Completed | 39992.3 | 33672 | 2020-02-06 | 2020-10-08
BARWANI / THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/22012034527122 — farm pond (khet talanb) hiralal ghisaji | Completed | 39327.06 | 29904 | 2020-02-06 | 2020-10-08
BARWANI / THIKRI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/22012034527123 — farm pond (khet talanb) baghsingh gopal | Closed | 0 | 0 | 2019-12-20
BARWANI / THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003002/IF/22012034594115 — PASHU SHEET LAKHAN RUKHADIYA | Closed | 0 | 0 | 2020-07-17
BARWANI / THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003002/IF/22012034594121 — PASHU SHEET BALIRAM ANARSINGH | Closed | 0 | 0 | 2020-07-17
BARWANI / THIKRI | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742003002/IF/22012034594123 — NADEP NIRMAN DEVCHAND GANPAT | Closed | 0 | 0 | 2020-07-17
BARWANI / THIKRI | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742003002/IF/22012034594127 — NADEEP NIRMAN TUKARAM BALA | Closed | 0 | 0 | 2020-07-17
BARWANI / THIKRI | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742003002/IF/22012034594129 — NADEEP NIRMAN ANANSINGH | Closed | 0 | 0 | 2020-07-17
BARWANI / THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003002/IF/22012034645582 — pashu sheed vidhya bai budesingh | Deleted | 0 | 0 | 2020-10-21
BARWANI / THIKRI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003002/IF/22012034823641 — pashusheed vidhya bai | Deleted | 0 | 0 | 2021-04-14
BARWANI / THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1742003002/IF/22012034902974 — slwm shokpit | Closed | 0 | 0 | 2021-08-15
BARWANI / THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1742003002/IF/22012034902989 — shok pith | Closed | 0 | 0 | 2021-08-15
BARWANI / THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1742003002/IF/22012034903001 — shok pith | Deleted | 0 | 0 | 2021-08-15
BARWANI / THIKRI | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1742003002/IF/22012034990335 — shok pith tukarambala | Closed | 0 | 0 | 2022-04-14
BARWANI / THIKRI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Shelter Belt Trees for Individuals | Plantation | 1742003002/IF/22012035167953 — pashu sheed vidhya bai golata | Completed | 72618.65 | 58430 | 2023-10-09 | 2025-04-18
BARWANI / THIKRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1742003002/IF/22012035236362 — Plantation work sobhag singh gangaram golata | Ongoing | 145050.83 | 62480.88 | 2024-07-17
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/22012035421279 — Farm pond nanuram mangilal golata | Physically Completed | 55865.38 | 46885.49 | 2025-04-30 | 2026-02-11
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1742003002/IF/22012035421343 — Farm pond gajrajsingh | Approved | 147621.16 | 0 | 2025-04-14
BARWANI / THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003002/IF/9926709143 — pashu sheet (shobagh shingh ji golata 0.80) manreg | Completed | 80000 | 80249.88 | 2014-02-27 | 2014-08-08
BARWANI / THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003002/IF/9926709165 — pashu sheet(juwan shingh rayshingh golata 0.80) av | Completed | 80000 | 74026 | 2014-02-27 | 2014-09-21
BARWANI / THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003002/IF/9926709175 — pashu sheed (govind narayan kewat golata 0.80) ava | Completed | 80000 | 64403 | 2014-02-27 | 2014-09-21
BARWANI / THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003002/IF/9926709182 — pashu sheed (rajesh amarshingh golata 0.80) avali | Completed | 80000 | 73717.62 | 2014-02-27 | 2014-06-18
BARWANI / THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Poultry Shelter / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1742003002/IF/9926709248 — POULTRIY SHELTER(chandra shingh rama golata ) 0.47 | Completed | 47000 | 41114 | 2014-02-27 | 2014-08-01
BARWANI / THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Poultry Shelter / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1742003002/IF/9926709255 — poultriy shelter(bhiku mona golata 047) avali | Completed | 47000 | 43857.65 | 2014-02-27 | 2014-05-29
BARWANI / THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1742003002/IF/9926709260 — goat shelter(mangilal rolji golata 0.45) | Completed | 45700 | 41042.91 | 2014-02-27 | 2014-05-29
BARWANI / THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1742003002/IF/9926709267 — goat shelter(ramesh shomariya 045)golata | Completed | 45700 | 43582.58 | 2014-02-27 | 2014-06-28
BARWANI / THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1742003002/IF/9926709274 — goat shelter(Ravji bhavsgingh 045)golata | Completed | 45700 | 43532.36 | 2014-02-27 | 2014-08-06
BARWANI / THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1742003002/IF/9926709278 — goat shelter(Amarshingh ratnshingh golata 0.45) | Completed | 45700 | 37520.46 | 2014-02-27 | 2014-05-29
BARWANI / THIKRI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Poultry Shelter / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1742003002/IF/9926709284 — poultreey shelter(shengha hasiya) golat 0.47 | Completed | 47000 | 44247.56 | 2014-02-27 | 2015-07-24
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003002/IF/9993692078 — ganesh shankar pashushet golata avali | Completed | 97000 | 97768.61 | 2015-12-03 | 2016-05-25
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1742003002/IF/9993719036 — मेढ़ बंधान | Deleted | 0 | 0 | 2015-08-02
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/9993722922 — medh bandhhan avali parwari bai budha | Deleted | 0 | 0 | 2016-01-26
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/9993722930 — med bandhan nirmala santilal parmar | Deleted | 0 | 0 | 2016-01-26
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/9993722933 — med bandhan nirmala mahesh shankar parmar | Deleted | 0 | 0 | 2016-01-26
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/9993722935 — med bandhan nirmala prkash parmar | Deleted | 0 | 0 | 2016-01-26
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003002/IF/9993722936 — pashusheet manishankar pathak | Deleted | 0 | 0 | 2016-01-26
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1742003002/IF/9993722941 — bakri sheet bhurla | Deleted | 0 | 0 | 2016-01-26
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/9993722943 — med bandhan nirmala raju | Deleted | 0 | 0 | 2016-01-26
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/9993722945 — med bandhan nirmala gaju | Deleted | 0 | 0 | 2016-01-26
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/9993722946 — med bandhan nirmala | Deleted | 0 | 0 | 2016-01-26
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/9993722949 — med bandhan nirmala | Deleted | 0 | 0 | 2016-01-26
BARWANI / THIKRI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1742003002/IF/9993722950 — med bandhan nirmala | Deleted | 0 | 0 | 2016-01-26
BARWANI / THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742003002/IF/9993731300 — pashu sheed ajit kaliyansingh golata | Completed | 97000 | 96335.11 | 2016-04-05 | 2016-10-14
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/1122881 — Construction of IAY House -IAY REG. NO. MP1637973 | Completed | 17100 | 11340 | 2017-11-21 | 2021-01-18
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/1147169 — Construction of IAY House -IAY REG. NO. MP1680050 | Deleted | 15480 | 0 | 2017-12-28
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/1147312 — Construction of IAY House -IAY REG. NO. MP1694469 | Deleted | 15480 | 0 | 2017-12-28
BARWANI / THIKRI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/1773957 — Construction of IAY House -IAY REG. NO. MP3229363 | Completed | 15660 | 14616 | 2018-11-01 | 2019-01-01
BARWANI / THIKRI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/1774312 — Construction of IAY House -IAY REG. NO. MP3359950 | Completed | 15660 | 15360 | 2018-11-01 | 2018-12-18
BARWANI / THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/2488969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4198644 | Completed | 17100 | 17100 | 2020-06-02 | 2020-09-23
BARWANI / THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/2728455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3293428 | Completed | 17100 | 11894 | 2021-03-16 | 2022-07-25
BARWANI / THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/2728460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3294252 | Completed | 17100 | 13220 | 2021-03-16 | 2022-07-25
BARWANI / THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/2729599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1692640 | Completed | 17100 | 12143 | 2021-03-16 | 2024-04-16
BARWANI / THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/2729764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1644922 | Completed | 17100 | 14321 | 2021-03-16 | 2022-04-15
BARWANI / THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/2730301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4184666 | Completed | 17100 | 11341 | 2021-03-16 | 2024-04-16
BARWANI / THIKRI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/2744861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1405067 | Completed | 17100 | 16215 | 2021-03-16 | 2023-11-21
BARWANI / THIKRI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3103275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3254648 | Completed | 17370 | 13776 | 2021-06-17 | 2024-04-16
BARWANI / THIKRI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3236729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3266562 | Physically Completed | 17370 | 9922 | 2021-10-28 | 2024-11-21
BARWANI / THIKRI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3237397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3254591 | Physically Completed | 17370 | 8034 | 2021-10-28 | 2024-11-21
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003002/IF/IAY/3755419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127168618 | Approved | 27000 | 0 | 2022-05-01
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3770386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130305683 | Completed | 18360 | 17340 | 2022-06-19 | 2023-01-06
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3770388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130305725 | Completed | 18360 | 17794 | 2022-08-02 | 2023-07-19
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3770390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130305762 | Completed | 18360 | 17876.6 | 2022-11-09 | 2023-09-05
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3770394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306268 | Completed | 18360 | 17340 | 2022-06-19 | 2023-05-18
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3770396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306487 | Completed | 18360 | 17136 | 2022-08-02 | 2023-02-19
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3770397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306521 | Completed | 18360 | 17136 | 2022-08-02 | 2023-03-16
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3770398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306548 | Completed | 18360 | 18145 | 2022-06-19 | 2023-11-21
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3770399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306568 | Completed | 18360 | 17136 | 2022-08-02 | 2023-02-05
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003002/IF/IAY/3770402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306912 | Approved | 27000 | 0 | 2022-05-01
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003002/IF/IAY/3774038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126610768 | Ongoing | 27000 | 6936 | 2022-08-23
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003002/IF/IAY/3774048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126611895 | Ongoing | 27000 | 2856 | 2023-01-12
BARWANI / THIKRI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3776193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125797629 | Completed | 18360 | 16601 | 2023-06-14 | 2025-02-17
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3780291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125079381 | Completed | 18360 | 18156 | 2022-07-23 | 2023-02-25
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3780296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125079928 | Completed | 18360 | 18097.8 | 2022-08-23 | 2023-07-06
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3782334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125840783 | Completed | 18360 | 17367 | 2022-11-03 | 2023-09-05
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3782839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125109651 | Completed | 18360 | 17632 | 2022-07-23 | 2023-05-20
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003002/IF/IAY/3782852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125111342 | Ongoing | 27000 | 0 | 2023-01-14
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3782871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125114027 | Completed | 18360 | 18291 | 2022-11-17 | 2023-07-06
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3843313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124145254 | Completed | 18360 | 18179 | 2022-11-24 | 2023-07-06
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3843454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124156016 | Completed | 18360 | 15008 | 2023-03-10 | 2024-04-16
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3844113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124169295 | Completed | 18360 | 16505 | 2022-07-23 | 2024-05-07
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3844122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124169991 | Completed | 18360 | 18179 | 2022-11-17 | 2023-10-26
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3844135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124170611 | Completed | 18360 | 18360 | 2022-07-23 | 2023-01-09
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3844680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125299894 | Completed | 18360 | 18228 | 2022-09-10 | 2024-06-18
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3866612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126103106 | Completed | 18360 | 18116 | 2022-08-23 | 2023-11-21
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3946111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130305541 | Completed | 18360 | 18130 | 2023-01-14 | 2023-10-26
BARWANI / THIKRI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3946112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130305585 | Completed | 18360 | 17970 | 2023-06-14 | 2024-06-12
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/3946113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130305624 | Completed | 18360 | 17081 | 2022-06-19 | 2023-07-06
BARWANI / THIKRI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4011423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126105405 | Completed | 18360 | 17991 | 2023-06-14 | 2024-06-18
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4251837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125837165 | Completed | 18360 | 18053 | 2022-09-10 | 2023-11-21
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003002/IF/IAY/4252112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126615741 | Ongoing | 27000 | 1428 | 2023-01-14
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003002/IF/IAY/4252113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126618648 | Approved | 27000 | 0 | 2022-06-19
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4256145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306462 | Completed | 18360 | 15976.8 | 2022-08-02 | 2023-12-06
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4350119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125549000 | Completed | 18360 | 17872 | 2022-11-17 | 2023-11-21
BARWANI / THIKRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003002/IF/IAY/4352664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128179632 | Ongoing | 27000 | 0 | 2022-07-18
BARWANI / THIKRI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4354144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306806 | Completed | 18360 | 15309 | 2023-08-30 | 2024-11-09
BARWANI / THIKRI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4372529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306303 | Completed | 18360 | 12314 | 2023-06-14 | 2025-05-06
BARWANI / THIKRI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4379775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130305450 | Completed | 18360 | 17430 | 2023-06-14 | 2024-05-02
BARWANI / THIKRI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4382396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306425 | Completed | 18360 | 14350 | 2023-06-14 | 2025-05-06
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003002/IF/IAY/4385642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124199946 | Approved | 27000 | 0 | 2022-07-18
BARWANI / THIKRI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4401328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123516720 | Closed | 19890 | 0 | 2023-07-08
BARWANI / THIKRI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4405610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306329 | Closed | 19890 | 0 | 2023-07-08
BARWANI / THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/455591 — Construction of IAY House -IAY REG. NO. MP1635508 | Deleted | 15030 | 0 | 2017-01-27
BARWANI / THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/455863 — Construction of IAY House -IAY REG. NO. MP1638038 | Deleted | 15030 | 0 | 2017-01-27
BARWANI / THIKRI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/457075 — Construction of IAY House -IAY REG. NO. MP1651768 | Deleted | 15030 | 0 | 2017-01-27
BARWANI / THIKRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4606224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124831758 | Completed | 21870 | 21627 | 2024-12-01 | 2025-03-17
BARWANI / THIKRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/4633431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306752 | Completed | 23490 | 22862 | 2024-12-01 | 2025-07-07
BARWANI / THIKRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003002/IF/IAY/4826983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125565479 | Approved | 27000 | 0 | 2024-10-18
BARWANI / THIKRI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/789464 — Construction of IAY House -IAY REG. NO. MP1757723 | Completed | 15480 | 13398 | 2018-11-01 | 2019-01-01
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/813630 — Construction of IAY House -IAY REG. NO. MP1672864 | Deleted | 15480 | 0 | 2018-01-04
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/940442 — Construction of IAY House -IAY REG. NO. MP1652186 | Deleted | 15480 | 0 | 2018-01-01
BARWANI / THIKRI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/940443 — Construction of IAY House -IAY REG. NO. MP1652767 | Completed | 17100 | 9744 | 2018-11-01 | 2020-09-23
BARWANI / THIKRI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/940459 — Construction of IAY House -IAY REG. NO. MP1700994 | Completed | 15480 | 14790 | 2018-11-01 | 2019-02-03
BARWANI / THIKRI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1742003002/IF/IAY/989099 — Construction of IAY House -IAY REG. NO. MP1652012 | Approved | 27000 | 0 | 2017-04-25
BARWANI / THIKRI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742003002/IF/IAY/989270 — Construction of IAY House -IAY REG. NO. MP1702317 | Completed | 15480 | 13416 | 2018-10-24 | 2020-02-01
BARWANI / THIKRI | 2015-2016 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1742003002/LD/22012034235075 — khel medan avali (punarvash anganwadi ke pash) avali | Completed | 359000 | 351234.51 | 2015-10-27 | 2018-02-15
BARWANI / THIKRI | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1742003002/LD/22012034235076 — khel medan avali(avali punarwash anganwadi ke pash) | Deleted | 0 | 0 | 2015-08-15
BARWANI / THIKRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1742003002/LD/22012034576006 — baubdriwall | Closed | 0 | 0 | 2022-01-25
BARWANI / THIKRI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1742003002/LD/3799419180 — khail maidan g. s.v. golata | Deleted | 0 | 0 | 2013-09-29
BARWANI / THIKRI | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1742003002/LD/3799419181 — khail maidan g. s.v. golata | Completed | 282000 | 190048.43 | 2014-01-09 | 2015-08-01
BARWANI / THIKRI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1742003002/LD/3799428687 — manreg(santi dham golata) avali | Completed | 270000 | 209461.25 | 2014-02-27 | 2015-08-04
BARWANI / THIKRI | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/ — पुलिया निर्माण आवली | Completed | 490960 | 296230.2 | 2006-07-28 | 2007-01-03
BARWANI / THIKRI | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/01 — नाली निर्माण गोलाटा आंवली | Completed | 100000 | 89280 | 2008-06-25 | 2010-08-17
BARWANI / THIKRI | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1742003002/RC/161 — जीएसबी मार्ग (5.00 आवली से गोया) आवली | Completed | 500000 | 424498 | 2009-08-30 | 2008-01-26
BARWANI / THIKRI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034171088 — आंतरिक मार्ग निर्माण पंचपरमेश्‍वर + मनरेगा आंवली | Completed | 131000 | 41298 | 2013-06-13 | 2013-10-19
BARWANI / THIKRI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034194887 — panchparmeswar cc road ( 3.90 shelji ke makan se m | Completed | 135000 | 121948.5 | 2013-12-02 | 2014-03-13
BARWANI / THIKRI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1742003002/RC/22012034197050 — नर्मदा परिक्रमा पथ (4.90 गोलाटा से छोटा बडदा मार्ग | Deleted | 490000 | 0 | 2012-04-14
BARWANI / THIKRI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034206523 — panchaparmeshvar+ marega c.c.rod prtapsingh kemkan | Completed | 109000 | 92340 | 2014-02-20 | 2014-04-10
BARWANI / THIKRI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034221173 — c.c. ROd Dhannalal ke makan se manya ke mkan tk (g | Completed | 95000 | 99110 | 2014-06-12 | 2014-09-19
BARWANI / THIKRI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034226781 — C C dren niraman golata (avali)1.80(panchapar | Completed | 155000 | 93248 | 2014-08-07 | 2015-09-30
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034321918 — C C Road adhivashi mohalla golata | Deleted | 4320000000 | 0 | 2017-01-27
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034324682 — सीसीरोड निर्माण नानुराम के मकान से बुधन के मकान तक गोलाटा | Completed | 62000 | 61300 | 2018-12-13 | 2019-11-18
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034368826 — C C Road nirman school parishar avali | Completed | 300000 | 49068 | 2019-03-08 | 2019-11-18
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034434723 — c c road nirman raju ke makan se budesingh ke mkan tk golata | Closed | 0 | 0 | 2018-12-28
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034435410 — c c road nirman avali trilok ke mkan se dadamsingh ke mkan tk | Closed | 0 | 0 | 2018-12-28
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034435552 — c c road avali | Closed | 0 | 0 | 2018-12-28
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034435553 — c c road avali | Closed | 0 | 0 | 2018-12-28
BARWANI / THIKRI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034445954 — c c road vijayke makan se mohaN ke mkan tk tadvi mohalla golata | Completed | 65000 | 70740 | 2019-03-08 | 2019-11-18
BARWANI / THIKRI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034480168 — C.C. road maniya ke makan se ramesh sommariya ke makan tk golata | Completed | 60000 | 60980 | 2019-10-10 | 2020-02-15
BARWANI / THIKRI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034516078 — rapat nirman mohan ke ghar ke pass golata | Closed | 65400 | 0 | 2019-08-15
BARWANI / THIKRI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034529170 — सी सी रोड निर्माण शा. उत्कृष्ट बालक प्राथमिक विद्यालय अवली बसाहट | Completed | 73000 | 62940 | 2020-07-18 | 2021-01-04
BARWANI / THIKRI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034544267 — c c road nirman halav se santi dham tak | Completed | 40800 | 49860 | 2020-10-22 | 2021-05-10
BARWANI / THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034568494 — c c road prathmik school atirikt bhavan | Completed | 41000 | 44460 | 2021-05-20 | 2022-06-20
BARWANI / THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034582030 — c c road rammandir ke pass golata | Completed | 51000 | 50208 | 2021-11-09 | 2022-04-15
BARWANI / THIKRI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034614737 — nali nirman golata ram mandir ke pass | Deleted | 0 | 0 | 2022-04-14
BARWANI / THIKRI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034614738 — nali nirman golata ram mandir ke pass | Physically Completed | 56000 | 24438.88 | 2022-09-21 | 2026-08-06
BARWANI / THIKRI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034667504 — C c Road ramandir ke pass golata | Completed | 45000 | 8255 | 2024-04-30 | 2025-03-26
BARWANI / THIKRI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034684008 — puliya nirman avali | Closed | 300000 | 0 | 2024-01-05
BARWANI / THIKRI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742003002/RC/22012034839370 — Puliya nirman golata | Completed | 100000 | 99778.78 | 2025-04-23 | 2025-12-02
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034323926 — shochaly nirman sati bai chagan avali | Completed | 12000 | 11806 | 2017-02-08 | 2017-06-14
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034323937 — shochaly nirman nanuram rama avali | Completed | 12000 | 13810 | 2017-02-08 | 2017-06-14
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034323940 — shochaly nirman keshar bai heralal avali | Completed | 12000 | 11806 | 2017-02-08 | 2017-06-14
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034323942 — shochaly nirman ranjit nathu avali | Completed | 12000 | 11806 | 2017-02-08 | 2018-02-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034323946 — shochaly nirman ramsingh amrsingh avali | Completed | 12000 | 11806 | 2017-02-08 | 2017-06-14
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034326587 — shochaly nirman sadhana bai nirmal ban avali | Completed | 12000 | 10804 | 2017-02-23 | 2017-06-14
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034328069 — shochaly nirman devendra balusingh avali | Completed | 12000 | 11806 | 2017-03-04 | 2017-04-13
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034328071 — shochaly nirman tukaram bala avali | Completed | 12000 | 11806 | 2017-03-04 | 2018-02-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034328073 — shochaly nirman chandrashekhar vishvkarma avali | Completed | 12000 | 11806 | 2017-03-04 | 2017-04-09
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034328074 — shochaly nirman sumangir avali | Completed | 12000 | 11806 | 2017-03-04 | 2017-06-14
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334535 — shochaly nirman devendra vishvkarma avali | Completed | 12000 | 11806 | 2017-03-25 | 2017-06-14
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334906 — shochaly nirman bhagvan kishor golata | Completed | 12000 | 11806 | 2017-03-25 | 2018-02-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334914 — shochaly nirman manohar kishor golata | Completed | 12000 | 11806 | 2017-03-25 | 2018-02-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334916 — shochaly nirman mansingh kishor golata | Completed | 12000 | 9802 | 2017-03-25 | 2018-10-21
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334918 — shochaly nirman ranjit kishor golata | Completed | 12000 | 10822 | 2017-03-25 | 2020-06-13
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334921 — shochaly nirman gajraj haresingh golata | Completed | 12000 | 11806 | 2017-03-25 | 2018-02-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334922 — shochaly nirman dipak bhimsingh golata | Completed | 12000 | 10822 | 2017-03-25 | 2020-06-13
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334923 — shochaly nirman jitendra tantusingh golata | Completed | 12000 | 3006 | 2017-03-25 | 2025-02-17
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334928 — shochaly nirman mahendra karnsingh golata | Completed | 12000 | 11806 | 2017-03-25 | 2020-06-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334929 — shochaly nirmanbaju bai ggolata | Completed | 12000 | 11806 | 2017-03-25 | 2018-02-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334935 — shochaly nirman budesingh golata | Completed | 12000 | 11806 | 2017-03-25 | 2018-02-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034334936 — shochaly nirman ajit kaliyan golata | Completed | 12000 | 10822 | 2017-03-25 | 2020-06-13
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034335049 — shochaly nirman shekhar hemchand golata | Completed | 12000 | 9802 | 2017-03-25 | 2018-10-21
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034335050 — shochaly nirman ballu mangilal | Completed | 12000 | 10822 | 2017-03-25 | 2020-06-14
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034335051 — shochaly nirman rajendra hiralal golata | Completed | 12000 | 11806 | 2017-03-25 | 2018-10-21
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034335053 — shochaly nirman baghsingh golata | Completed | 12000 | 11806 | 2017-03-25 | 2018-02-01
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034335054 — shochaly nirman radheshyam golata | Completed | 1200000000 | 2022 | 2017-03-25 | 2020-07-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034335056 — shochaly nirman kaliyan chandar golata | Completed | 12000 | 11806 | 2017-03-25 | 2018-02-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034335058 — shochaly nirman harish sharma golata | Completed | 12000 | 11806 | 2017-03-25 | 2018-02-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034335059 — shochaly nirman mahesh nanuram golata | Completed | 12000 | 9802 | 2017-03-25 | 2018-02-21
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034335945 — shochaly nirman pavan sitaram avali | Completed | 12000 | 11802 | 2017-03-26 | 2017-04-15
BARWANI / THIKRI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1742003002/RS/22012034335947 — shochaly nirman motilal champalal avali | Completed | 12000 | 11802 | 2017-03-01 | 2017-04-23
BARWANI / THIKRI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1742003002/RS/22012034624436 — samudaik swachta parishar (sochaly nirman ) awali | Completed | 43000 | 39847.2 | 2022-02-20 | 2023-06-27
BARWANI / THIKRI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1742003002/RS/22012035137931 — nali nirman pani ki tanki ke pass se puliya tak golata | Physically Completed | 73000 | 61541.4 | 2025-06-11 | 2026-02-20
BARWANI / THIKRI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003002/WC/ — वाटरपोण्‍ड न. 2 आंवली | Completed | 473350 | 24840 | 2008-01-22 | 2008-07-08
BARWANI / THIKRI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003002/WC/02 — वाटरपोण्‍ड न. 1 आवंली | Completed | 214727 | 214727 | 2007-04-17 | 2008-03-31
BARWANI / THIKRI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003002/WC/1 — बोरी बंधान Aawli | Completed | 11000 | 2340 | 2007-01-16 | 2007-04-15
BARWANI / THIKRI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003002/WC/2 — बोरी बंधान आंवली (V) | Completed | 9900 | 2340 | 2007-01-16 | 2007-04-15
BARWANI / THIKRI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003002/WC/22012034504907 — WATER POND RAMESH SOMMARIYA KE GHAR KE NICHE GOLATA | Completed | 310385.56 | 254280 | 2019-12-12 | 2020-11-09
BARWANI / THIKRI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1742003002/WC/22012034517018 — samudayek khettalab mangilal ke ghar ke niche golata | Closed | 0 | 0 | 2019-10-02
BARWANI / THIKRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742003002/WC/22012034599983 — samudaik foram pond nirman shanti dham ke pass golata | Completed | 91951.04 | 60600 | 2020-12-28 | 2023-06-27
BARWANI / THIKRI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742003002/WC/22012034599985 — samudaik forampond nirman adiwashi mohalla pass golata | Completed | 95451.04 | 50822 | 2020-12-28 | 2023-06-27
BARWANI / THIKRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1742003002/WC/22012034714082 — CTR_GIS_RUF TOP HARVASTING AAVALI | Closed | 22173.14 | 0 | 2021-05-05
BARWANI / THIKRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1742003002/WC/22012034762716 — CTR_GIS_gully plug golata Aavali | Closed | 0 | 0 | 2021-05-05
BARWANI / THIKRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1742003002/WC/22012034908226 — samudaik forampond nirmant | Closed | 0 | 0 | 2022-01-25
BARWANI / THIKRI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1742003002/WC/22012034908231 — samudaik forampond nirmant | Closed | 0 | 0 | 2022-01-25
BARWANI / THIKRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742003002/WC/22012035138364 — Samudaik farm pond aawali | Completed | 150140.04 | 71940.61 | 2024-06-22 | 2025-06-13
BARWANI / THIKRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1742003002/WC/22012035172388 — farm pond golata | New | 0 | 0 | 2024-04-14
BARWANI / THIKRI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1742003002/WC/22012035175396 — Samudaik farm pond aawali | New | 0 | 0 | 2024-01-26
BARWANI / THIKRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1742003002/WC/22012035200940 — Roof top water harvesting for samudaik sochalay awali | Approved | 37072.16 | 0 | 2024-04-14
BARWANI / THIKRI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1742003002/WC/22012035257994 — sct work golata | Approved | 0 | 0 | 2025-04-05
BARWANI / THIKRI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1742003002/WC/430 — वाटर पौण्‍ड (4.76 गोलाटा) आंवली | Completed | 476000 | 194000 | 2010-07-11 | 2010-07-11
BARWANI / THIKRI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1742003002/WC/539 — वाटर पौण्‍ड (4.55 गोलाटा ) आंवली | Completed | 455000 | 145546 | 2011-07-06 | 2012-05-06
BARWANI / THIKRI | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1742003002/WC/6 — बोरी बंधान आवली (VI) | Completed | 9500 | 1940 | 2007-01-16 | 2007-01-21
BARWANI / THIKRI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1742003002/WC/634 — वाटर पोण्‍ड निर्माण (बुधा कालु के खेत के पास (3.57 | Completed | 357000 | 267424 | 2012-01-22 | 2012-09-08
BARWANI / THIKRI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1742003002/WC/9993670724 — सी.सी.टी | Deleted | 0 | 0 | 2016-04-01
BARWANI / THIKRI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1742003/IF/22012034397401 — फलोद्यान परियोजना बालीबाई बाला संदेवा (आंवली) | Physically Completed | 552420 | 88236 | 2018-04-07 | 2026-06-12
BARWANI / THIKRI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1742/WC/9993622007 — R/W निर्माण आवली रोड् से भवती हनुमान (49.96)RES | Completed | 4996000 | 4451542.2 | 2010-06-15 | 2014-02-26