## Work List
Exported on: 2026-10-03 16:15:46
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: CHHAPRI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BARWANI / THIKRI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Cyclone shelter for Community / Construction of Cyclone Shelter for Community | Construction of Other Community Building/Assets | 1742003013/AV/22012034657670 — pashu sedh mamta bai pavan | New | 0 | 0 | 2024-05-10
BARWANI / THIKRI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742003013/IF/22012035172838 — Kapildhara Haaru ratan | Physically Completed | 232656.75 | 0 | 2024-03-14 | 2026-08-03
BARWANI / THIKRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742003013/IF/22012035273853 — Kapildhara lalya nihala | Approved | 0 | 0 | 2024-11-15
BARWANI / THIKRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1742003013/IF/22012035297179 — Pashu shed gajra Bai kamal | Approved | 0 | 0 | 2025-01-26
BARWANI / THIKRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1742003013/IF/22012035297538 — Pashu shed Suman Bai kishor | Approved | 0 | 0 | 2025-01-26
BARWANI / THIKRI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/4249209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123742754 | Ongoing | 27000 | 0 | 2023-03-09
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/4402772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123470288 | Completed | 23490 | 0 | 2026-02-20 | 2026-07-26
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/4824282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118380525 | Completed | 23490 | 0 | 2025-04-13 | 2026-07-26
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/4854567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122512497 | Ongoing | 27000 | 0 | 2025-07-10
BARWANI / THIKRI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/4866627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127940291 | Physically Completed | 23490 | 0 | 2025-03-12 | 2026-08-04
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5435340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116432550 | Ongoing | 27000 | 0 | 2026-02-20
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5598321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123754954 | Physically Completed | 23490 | 150 | 2025-05-11 | 2026-08-04
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5598768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122372201 | Completed | 23490 | 0 | 2025-05-11 | 2026-07-26
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5598782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127974896 | Ongoing | 27000 | 3000 | 2025-07-10
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5679473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127964401 | Physically Completed | 23490 | 500 | 2026-01-29 | 2026-08-04
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5679508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120794454 | Ongoing | 27000 | 0 | 2025-12-10
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5679608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128082853 | Physically Completed | 23490 | 0 | 2025-07-10 | 2026-08-20
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5719497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127932843 | Completed | 23490 | 0 | 2025-08-23 | 2026-07-26
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5803759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116318882 | Completed | 23490 | 2100 | 2025-09-24 | 2026-07-26
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5835746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119557441 | Completed | 23490 | 0 | 2025-12-03 | 2026-07-26
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5835804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123740933 | Ongoing | 27000 | 9900 | 2026-01-29
BARWANI / THIKRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5875326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117131529 | Ongoing | 27000 | 13500 | 2026-05-05
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5875501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128092792 | Physically Completed | 23490 | 6600 | 2026-02-04 | 2026-08-04
BARWANI / THIKRI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5889290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136639062 | Ongoing | 27000 | 0 | 2026-06-05
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5934581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127950858 | Ongoing | 27000 | 0 | 2026-03-06
BARWANI / THIKRI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742003013/IF/IAY/5935213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121632189 | Ongoing | 27000 | 0 | 2026-03-06
BARWANI / THIKRI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1742003013/RC/22012034679156 — Cc road khedapura | New | 0 | 0 | 2024-04-14
BARWANI / THIKRI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1742003013/WC/22012035200516 — Gali plug 1 chhapri | Approved | 0 | 0 | 2024-05-18
BARWANI / THIKRI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1742003013/WC/VB/22012035333757 — Contour Trench Nirman Khwaja Baba Pahadi k pass | Ongoing | 201335.8 | 0 | 2026-09-03