## Work List
Exported on: 2026-08-15 09:38:00
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: LIMBAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BARWANI / RAJPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742004031/IF/22012034591567 — GKRA नाड़ेप निर्माण कार्य (0.12) सीताराम मांगिलाल लिम्बई | Ongoing | 12412.41 | 0 | 2020-10-28
BARWANI / RAJPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Vermi Compost structure for Individual / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1742004031/IF/22012034591570 — GKRA वर्मी कोंपोस्ट निर्माण कार्य (0.15) सखाराम बाल्या लिम्बई रेवजा | Ongoing | 15467.4 | 0 | 2020-10-28
BARWANI / RAJPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742004031/IF/22012034860123 — पशु शेड निर्माण कार्य मंशाराम बाउ लिम्‍बई | Ongoing | 102645.51 | 0 | 2021-11-16
BARWANI / RAJPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742004031/IF/22012034860410 — PASU SEHT NIRMAN PRAMANAND DEPLA | Ongoing | 102645.51 | 0 | 2021-11-16
BARWANI / RAJPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742004031/IF/22012035105156 — pashu shed kary kavita mansharam limbai | Ongoing | 124546.98 | 0 | 2023-08-31
BARWANI / RAJPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742004031/IF/22012035105160 — pashu shed kary deepika jitendra limbai | Ongoing | 125693.61 | 0 | 2023-07-15
BARWANI / RAJPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742004031/IF/22012035105163 — pashu shed kary shila sukya limbai | Ongoing | 125546.98 | 0 | 2023-07-15
BARWANI / RAJPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742004031/IF/22012035105165 — pashu shed kary vaijanti hiralal limbai | Ongoing | 125546.98 | 0 | 2023-07-15
BARWANI / RAJPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1742004031/IF/22012035144837 — pashu shed nirman kary laxmi gangaram limbai | Ongoing | 122697.73 | 0 | 2023-10-06
BARWANI / RAJPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742004031/IF/22012035352845 — JGSA 2025 Recharge Structure Rajaram Ballu Limbai | Approved | 25899.46 | 0 | 2025-04-14
BARWANI / RAJPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1742004031/IF/22012035352873 — JGSA 2025 Recharge Structure Ashok Tumdiya | Approved | 25899.46 | 0 | 2025-04-14
BARWANI / RAJPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1742004031/IF/22012035475693 — dagwel recharg galiya mangiya | New | 0 | 0 | 2025-04-14
BARWANI / RAJPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1742004031/IF/22012035475775 — dagwel recharg kup sanjay jagnnath | New | 0 | 0 | 2025-04-14
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742004031/IF/22012035481825 — JGSA 2025 KHET TALAB NIRMAN KARY SAKHRAM BALIYA | New | 0 | 0 | 2025-04-16
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742004031/IF/22012035481828 — JGSA 2025 KHET TALAB NIRMAN KARY SAMAD MANSURI | New | 0 | 0 | 2025-04-16
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742004031/IF/22012035481863 — JGSA 2025 KHET TALAB NIRMAN KARY SAKHRAM BALIYA | New | 0 | 0 | 2025-04-14
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742004031/IF/22012035481866 — JGSA 2025 KHET TALAB NIRMAN KARY SAMAD MANSURI | New | 0 | 0 | 2025-04-14
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1742004031/IF/22012035595573 — EK baghiya maa ke name basan bai jamre limbai | Ongoing | 272192.24 | 0 | 2025-09-11
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742004031/IF/22012035595587 — EK baghiya maa ke name sonu bai nigwal limbai | Ongoing | 269386.03 | 0 | 2025-09-09
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742004031/IF/22012035595974 — EK bagiya maa ke name sangita bai | Ongoing | 269386.03 | 0 | 2025-09-09
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742004031/IF/22012035613792 — EK bagiya maa ke name AVITA BAI LIMBAI | Ongoing | 278467.15 | 0 | 2025-09-30
BARWANI / RAJPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/2948644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4783530 | Approved | 23490 | 0 | 2021-01-08
BARWANI / RAJPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/3278391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5533781 | Approved | 23490 | 0 | 2021-06-10
BARWANI / RAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/4831584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133594016 | Ongoing | 23490 | 0 | 2025-03-11
BARWANI / RAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/4831850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131707049 | Ongoing | 23490 | 0 | 2025-01-17
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/4850620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133589415 | Ongoing | 23490 | 0 | 2025-04-09
BARWANI / RAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/4850622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133595519 | Physically Completed | 23490 | 0 | 2025-02-19 | 2026-08-09
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5506552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133594472 | Ongoing | 23490 | 0 | 2025-05-11
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5506713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133595124 | Ongoing | 23490 | 0 | 2025-05-11
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5511686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131849122 | Ongoing | 23490 | 0 | 2025-05-11
BARWANI / RAJPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5620512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133589385 | Ongoing | 23490 | 0 | 2026-05-13
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5620740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133587940 | Ongoing | 23490 | 0 | 2025-07-19
BARWANI / RAJPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5709777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133592971 | Ongoing | 23490 | 0 | 2026-04-16
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5814984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133593728 | Physically Completed | 23490 | 0 | 2025-10-11 | 2026-07-26
BARWANI / RAJPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5814985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133594798 | Physically Completed | 23490 | 0 | 2026-04-16 | 2026-08-09
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5815056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133593645 | Ongoing | 23490 | 0 | 2025-10-11
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5815057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133593663 | Ongoing | 23490 | 0 | 2026-02-19
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5815511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133447724 | Ongoing | 23490 | 0 | 2025-10-11
BARWANI / RAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742004031/IF/IAY/5815944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133588258 | Ongoing | 23490 | 0 | 2025-10-11
BARWANI / RAJPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742004031/RC/22012034834623 — cc road nirman (4.24) sheru bawara ke ghar se jamniyapura road limbai | Approved | 64000 | 0 | 2024-08-17
BARWANI / RAJPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742004031/RC/22012034836519 — cc road nirman (5.89) Prakash bharat ke ghar se Lattu ke khet ki or Jamniyapura limbai | Ongoing | 89000 | 0 | 2025-03-05
BARWANI / RAJPUR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1742004031/RC/22012034847098 — cc road nirman (3.71) Main Road puliya se Lattu ke Khet tak Jamaniya falya Limbai | Ongoing | 56000 | 14818.29 | 2026-06-13