## Work List
Exported on: 2026-09-26 15:19:46
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MANKUI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BARWANI / PANSEMAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742005024/IF/22012035029809 — PLANTEION MADAN RUMALSHING | Ongoing | 153560.72 | 29232 | 2023-01-10
BARWANI / PANSEMAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742005024/IF/22012035324755 — कपिल धारा कूप निर्माण भाटा काल्या ग्राम पंचायत मनकुई | Ongoing | 322434.5 | 0 | 2026-08-12
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742005024/IF/22012035324801 — कपिल धारा कूप निर्माण दयासिंग पिदा ग्राम पंचायत मनकुई | Ongoing | 322434.5 | 0 | 2025-05-22
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742005024/IF/22012035324816 — कपिल धारा कूप निर्माण तेलसिंग अतरसिंह | Ongoing | 322434.5 | 0 | 2025-05-22
BARWANI / PANSEMAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742005024/IF/22012035324832 — कपिल धारा कूप निर्माण भायदास कनसिंह ग्राम पंचायत मनकुई | Ongoing | 322434.5 | 0 | 2026-04-01
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742005024/IF/22012035324839 — कपिल धारा कूप निर्माण चांदनी गणपत ग्राम पंचायत मनकुई | Approved | 322434.5 | 0 | 2025-04-01
BARWANI / PANSEMAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742005024/IF/22012035324861 — कपिल धारा कूप निर्माण सुखलाल गुलसिंग ग्राम पंचायत मनकुई | Ongoing | 322434.5 | 0 | 2026-04-01
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742005024/IF/22012035324886 — कपिल धारा कूप निर्माण बिलरसिंग गुला | Ongoing | 322434.5 | 0 | 2025-05-22
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1742005024/IF/22012035324899 — कपिल धारा कूप निर्माण गंगाराम बनसिंह ग्राम पंचायत मनकुई | Ongoing | 322434.5 | 0 | 2025-05-22
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1742005024/IF/22012035486074 — खेत तालाब निर्माण मकाराम रुपसिंह के खेल के पास ग्राम पंचायत मनकुई | Approved | 147621.16 | 0 | 2025-04-01
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742005024/IF/22012035610770 — Plantation work Juni bai ke khet me Mankui | New | 0 | 0 | 2025-08-15
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742005024/IF/22012035610773 — Plantation work Mina bai ke khet me Mankui | Ongoing | 268315.94 | 16704 | 2025-09-15
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742005024/IF/22012035610774 — Plantation work Mangla bai ke khet me Mankui | Ongoing | 269386.03 | 0 | 2025-09-07
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742005024/IF/22012035610776 — Plantation work Emla bai ke khet me Mankui | Ongoing | 269386.03 | 0 | 2025-09-07
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742005024/IF/22012035625508 — Plantation work Chahali bai khedkar ke khet me mankui | Ongoing | 199319.34 | 0 | 2025-10-07
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742005024/IF/22012035632675 — Plantation work Mamta bai ke khet me Mankui | Approved | 269386.03 | 0 | 2025-08-15
BARWANI / PANSEMAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/1984243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2566535 | Physically Completed | 23490 | 0 | 2026-05-14 | 2026-07-25
BARWANI / PANSEMAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/4603903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124439207 | Ongoing | 27000 | 0 | 2024-11-05
BARWANI / PANSEMAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/4642333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137369255 | Physically Completed | 27000 | 9600 | 2024-11-05 | 2026-09-25
BARWANI / PANSEMAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/4820887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115407328 | Physically Completed | 23490 | 0 | 2024-11-18 | 2026-07-25
BARWANI / PANSEMAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/4829312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127297317 | Physically Completed | 23490 | 0 | 2025-01-31 | 2026-07-25
BARWANI / PANSEMAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/4886635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138635431 | Physically Completed | 23490 | 4800 | 2025-01-31 | 2026-08-09
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5387681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148909046 | Physically Completed | 23490 | 0 | 2025-07-26 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5390820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138635170 | Physically Completed | 27000 | 0 | 2025-05-15 | 2026-09-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5390954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138004641 | Physically Completed | 23490 | 0 | 2025-05-15 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5396475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124259036 | Physically Completed | 23490 | 0 | 2025-05-15 | 2026-07-19
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5403347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125588980 | Physically Completed | 23490 | 0 | 2025-05-15 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5403845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128712878 | Physically Completed | 23490 | 0 | 2025-07-26 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5405938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127516247 | Ongoing | 27000 | 0 | 2025-07-26
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5406183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124949305 | Ongoing | 27000 | 0 | 2025-05-15
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5408225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134885794 | Physically Completed | 23490 | 0 | 2025-05-15 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5408227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134885836 | Physically Completed | 23490 | 4800 | 2025-07-26 | 2026-08-19
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5423924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124944761 | Physically Completed | 27000 | 0 | 2025-05-15 | 2026-09-06
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5427185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141832651 | Physically Completed | 23490 | 0 | 2025-05-15 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5428349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127915385 | Physically Completed | 23490 | 4800 | 2025-05-15 | 2026-08-19
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5429089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134474260 | Physically Completed | 23490 | 0 | 2025-05-15 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5434172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128721742 | Physically Completed | 23490 | 0 | 2025-05-15 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5435150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124879704 | Physically Completed | 23490 | 0 | 2025-05-15 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5435695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133483953 | Ongoing | 27000 | 0 | 2025-07-26
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5436904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137368957 | Physically Completed | 23490 | 0 | 2025-07-26 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5437788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137369187 | Physically Completed | 23490 | 0 | 2025-07-26 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5438618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127908575 | Physically Completed | 23490 | 0 | 2025-05-15 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5439051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138004807 | Physically Completed | 23490 | 0 | 2025-05-15 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5587313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137369236 | Physically Completed | 23490 | 0 | 2025-07-26 | 2026-08-19
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5655040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127125374 | Physically Completed | 23490 | 0 | 2025-11-28 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5805344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141832672 | Physically Completed | 23490 | 0 | 2025-11-28 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5851659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134886084 | Completed | 23490 | 0 | 2025-11-28 | 2026-07-13
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5852013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125819601 | Physically Completed | 23490 | 0 | 2025-11-28 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5852137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127511496 | Physically Completed | 23490 | 0 | 2025-11-28 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5852224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127124829 | Physically Completed | 23490 | 0 | 2025-11-28 | 2026-07-25
BARWANI / PANSEMAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5852286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134831932 | Physically Completed | 23490 | 0 | 2025-11-28 | 2026-07-19
BARWANI / PANSEMAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5874263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127123837 | Ongoing | 27000 | 0 | 2026-05-14
BARWANI / PANSEMAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5874321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125844071 | Physically Completed | 23490 | 0 | 2026-04-08 | 2026-07-25
BARWANI / PANSEMAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/5880844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137369058 | Physically Completed | 27000 | 0 | 2026-05-14 | 2026-09-10
BARWANI / PANSEMAL | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1742005024/IF/IAY/85661 — Construction of IAY House -IAY REG. NO. MP-42-005-024-001/152P | Approved | 27000 | 0 | 2016-01-12
BARWANI / PANSEMAL | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742005024/WC/22012035248340 — निस्तार तालाब निर्माण दिनेश रायसिंग के खेत के पास ग्राम पंचयात मनकुई | Approved | 0 | 0 | 2025-01-24
BARWANI / PANSEMAL | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742005024/WC/22012035300142 — खेत तालाब निर्माण नवलसिंह रत्ना खेत के पास ग्राम पंचायत मनकुई | New | 0 | 0 | 2025-04-01
BARWANI / PANSEMAL | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742005024/WC/VB/22012035329832 — NISTAR TALAB NIRMAND BHAYDASH KANSING KE KHET PASS MANKUI | Approved | 0 | 0 | 2026-07-30
BARWANI / PANSEMAL | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Tanka (Water Storage Structure) / Construction of Tanka (Water Storage Structure) |  | 1742005024/WC/VB/22012035329848 — KHET TALAB NIRMAN SERSINGH KE KHET KE PASS MANKUI | Approved | 0 | 0 | 2026-07-30
BARWANI / PANSEMAL | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742005024/WC/VB/22012035329853 — KHET TALAB NIRMAN FIRTILAL PRADHAN KE KHET PASS MANKUI | Approved | 0 | 0 | 2026-07-30
BARWANI / PANSEMAL | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742005024/WC/VB/22012035329874 — लुज बोल्डर निर्माण अतर्सिंग सुरमल के खेत के पास मनकुई | Approved | 0 | 0 | 2026-07-30
BARWANI / PANSEMAL | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742005024/WC/VB/22012035329878 — लुज बोल्डर निर्माण भाटा काल्या के खेत के पास मनकुई | Approved | 0 | 0 | 2026-07-30
BARWANI / PANSEMAL | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742005024/WC/VB/22012035329888 — लुज बोल्डर निर्माण शेरसिंग हुन्या के खेल के पास मनकुई | Approved | 0 | 0 | 2026-07-30
BARWANI / PANSEMAL | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1742005024/WC/VB/22012035329894 — निस्तार तालाब निर्माण खुमसिंग संकर के खेत के पास मनकुई | Approved | 0 | 0 | 2026-07-30
BARWANI / PANSEMAL | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1742005024/WC/VB/22012035330586 — कंटूर ट्रेंच निर्माण ओंकार पारसी के खेत वाली पहाड़ी पर मनकुई | Approved | 0 | 0 | 2026-08-01
BARWANI / PANSEMAL | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1742/DP/22012034558212 — Bas Ropan karya C.N. No 774 MANKUI | Ongoing | 1962000 | 0 | 2022-07-14