## Work List
Exported on: 2026-10-21 09:20:08
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: DHANORA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BARWANI / SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1742007023/AV/22012034593726 — Goshala Nirman Karya Dhanora | Ongoing | 3833066.41 | 0 | 2022-12-03
BARWANI / SENDHAWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1742007023/DP/22012034621907 — Samudayik Varsha Ropan Kary Goshala Ke Pas Gram Panchayat Dhanora | Approved | 0 | 0 | 2024-06-13
BARWANI / SENDHAWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1742007023/IF/22012034612067 — पशु शेड निर्माण हित-अमास्या जतन्या ग्राम पंचायत धनोरा | Ongoing | 101804.91 | 0 | 2021-09-13
BARWANI / SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012034612721 — पोधा रोपण कार्य हित-दारासिंग सदाशिव ग्राम पंचायत धनोरा | Ongoing | 142446.41 | 0 | 2022-12-15
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012034612801 — पोधा रोपण कार्य हित-लकडिया भली ग्राम पंचायत धनोरा | Ongoing | 142446.41 | 0 | 2024-06-24
BARWANI / SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012034612808 — पोधा रोपण कार्य हित-भायराम सीताराम ग्राम पंचायत धनोरा | Ongoing | 142446.41 | 0 | 2022-05-24
BARWANI / SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742007023/IF/22012034620159 — कपिल धारा कूप निर्माण कार्य हित-प्रकाश गंगाराम धनोरा | Ongoing | 246126.86 | 0 | 2022-05-27
BARWANI / SENDHAWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1742007023/IF/22012034633403 — पशु शेड निर्माण हित-नूरीबाई शोभाराम ग्राम पंचायत धनोरा | Ongoing | 101804.91 | 0 | 2021-07-04
BARWANI / SENDHAWA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1742007023/IF/22012035079265 — Khet Talab Nirman Hit. Premsingh Latu Gram Panchayat Dhanora | Ongoing | 126762.84 | 0 | 2023-11-01
BARWANI / SENDHAWA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1742007023/IF/22012035079266 — Khet Talab Nirman Hit.Kuwarsingh Premsingh Gram Dhanora | Ongoing | 126762.84 | 0 | 2023-11-01
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1742007023/IF/22012035220489 — खेत तालाब निर्माण हित. गेदराम सुरला चारदड ग्राम पंचायत धनोरा | Ongoing | 385261.22 | 0 | 2024-06-14
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1742007023/IF/22012035220514 — खेत तालाब निर्माण हित. भावसिग मुवासिया चारदड ग्राम पंचायत धनोरा | Ongoing | 385261.22 | 0 | 2024-06-14
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1742007023/IF/22012035220524 — खेत तालाब निर्माण हित.नारसिंह शंकर चारदड ग्राम पंचायत धनोरा | Ongoing | 385261.22 | 0 | 2024-12-15
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1742007023/IF/22012035220532 — खेत तालाब निर्माण हित. काहरिया गुलाब चारदड ग्राम पंचायत धनोरा | Ongoing | 385261.22 | 0 | 2024-12-15
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1742007023/IF/22012035220536 — खेत तालाब निर्माण हित. रतन भीमसिंग चारदड ग्राम पंचायत धनोरा | Ongoing | 385261.22 | 0 | 2025-01-31
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1742007023/IF/22012035220538 — खेत तालाब निर्माण हित. थावलीबाई आनु चारदड ग्राम पंचायत धनोरा | Ongoing | 385261.22 | 0 | 2024-12-01
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1742007023/IF/22012035221388 — खेत तालाब निर्माण कार्य हित. भारसिंह डोगरसिंग चारदड ग्राम पंचायत धनोरा | Ongoing | 385261.22 | 0 | 2024-12-24
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035242773 — पौधा रोपड़ कार्य हित. हरी जगन ग्राम पंचायत धनोरा | Approved | 145050.83 | 0 | 2024-06-13
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035242776 — पौधा रोपड़ कार्य हित. पैना ननज्या ग्राम पंचायत धनोरा | Approved | 145050.83 | 0 | 2024-06-13
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035242779 — पौधा रोपड़ कार्य हित. शोभाराम फूलसिंह ग्राम पंचायत धनोरा | Ongoing | 145050.83 | 0 | 2024-12-15
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035242784 — पौधा रोपड़ कार्य हित. जाडिया रेमाल ग्राम पंचायत धनोरा | Approved | 145050.83 | 0 | 2024-06-13
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035242792 — पौधा रोपड़ कार्य हित. शांतिराम जगलिया ग्राम पंचायत धनोरा | Ongoing | 145050.83 | 0 | 2025-01-18
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035242797 — पौधा रोपड़ कार्य हित. छतरसिंह मुवासिया ग्राम पंचायत धनोरा | Ongoing | 145050.83 | 0 | 2025-01-18
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035242799 — पौधा रोपड़ कार्य हित. बद्री आनु ग्राम पंचायत धनोरा | Approved | 145050.83 | 0 | 2024-06-13
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035258082 — पोधा रोपण कार्य हित शंकर श्यामा ग्राम पंचायत धनोरा | Approved | 0 | 0 | 2024-08-16
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035258083 — पोधा रोपण कार्य हित सीताराम मिचरा ग्राम पंचायत धनोरा | Approved | 0 | 0 | 2024-08-16
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035258084 — पोधा रोपण कार्य हित जेमाल हरदा ग्राम पंचायत धनोरा | Approved | 145122.1 | 0 | 2024-08-16
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035258085 — पोधा रोपण कार्य हित तिलस्या भावसिंग ग्राम पंचायत धनोरा | Approved | 145122.1 | 0 | 2024-08-16
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035258086 — पोधा रोपण कार्य हित रावल्या मुवास्या ग्राम पंचायत धनोरा | Approved | 145122.1 | 0 | 2024-08-16
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035258088 — पोधा रोपण कार्य हित रायदा रूपसिंग ग्राम पंचायत धनोरा | Approved | 145122.1 | 0 | 2024-08-16
BARWANI / SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742007023/IF/22012035400979 — कूप रिचार्ज पिट हित- जाडिया रेमाल ग्राम पंचायत धनोरा | Approved | 0 | 0 | 2025-04-14
BARWANI / SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742007023/IF/22012035401009 — कूप रिचार्ज पिट हित- आतरसिंह नानसिंह ग्राम पंचायत धनोरा | Approved | 0 | 0 | 2025-04-14
BARWANI / SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742007023/IF/22012035401040 — कूप रिचार्ज पिट हित- कमल भारसिंह ग्राम पंचायत धनोरा | Approved | 0 | 0 | 2025-04-14
BARWANI / SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742007023/IF/22012035401072 — कूप रिचार्ज पिट हित- छतरसिंह मुवासिया ग्राम पंचायत धनोरा | Approved | 0 | 0 | 2025-04-14
BARWANI / SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742007023/IF/22012035401096 — कूप रिचार्ज पिट हित- भावला जिरभान ग्राम पंचायत धनोरा | Approved | 0 | 0 | 2025-04-14
BARWANI / SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742007023/IF/22012035401112 — कूप रिचार्ज पिट हित- जारसिया गाठिया ग्राम पंचायत धनोरा | Approved | 0 | 0 | 2025-04-14
BARWANI / SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742007023/IF/22012035401147 — कूप रिचार्ज पिट हित- पंडित लच्छा ग्राम पंचायत धनोरा | Approved | 0 | 0 | 2025-04-14
BARWANI / SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742007023/IF/22012035401161 — कूप रिचार्ज पिट हित- कर्मा डुलजी ग्राम पंचायत धनोरा | Approved | 0 | 0 | 2025-04-14
BARWANI / SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742007023/IF/22012035420338 — कूप रिचार्ज पिट हित- कालिया नरसिंह ग्राम पंचायत धनोरा | Approved | 25899.46 | 0 | 2025-04-14
BARWANI / SENDHAWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1742007023/IF/22012035421824 — कूप रिचार्ज पिट हित - चंपालाल भावसिंग ग्राम पंचायत धनोरा | Approved | 25899.46 | 0 | 2025-04-14
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1742007023/IF/22012035618978 — EK BAGIYA MAA KE NAAM DWARKI BRAHAMANE SHG DHANORA ADHE SACHIVA DHANORA | Ongoing | 283754.05 | 0 | 2025-09-21
BARWANI / SENDHAWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/1966636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2036791 | Ongoing | 27000 | 0 | 2020-01-18
BARWANI / SENDHAWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/3163911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5136546 | Physically Completed | 27000 | 0 | 2021-09-04 | 2026-09-11
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/3186322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5722132 | Physically Completed | 27000 | 0 | 2025-01-04 | 2026-09-11
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/3218164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4648624 | Physically Completed | 27000 | 0 | 2025-01-04 | 2026-09-11
BARWANI / SENDHAWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/3218238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4534628 | Ongoing | 27000 | 0 | 2021-09-03
BARWANI / SENDHAWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/3227871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4635741 | Completed | 27000 | 0 | 2021-12-13 | 2026-08-31
BARWANI / SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4176128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116582302 | Approved | 27000 | 0 | 2022-05-26
BARWANI / SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4177562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113996211 | Approved | 27000 | 0 | 2022-05-26
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4225466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117422147 | Completed | 27000 | 0 | 2025-06-29 | 2026-08-31
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4231624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125560520 | Ongoing | 27000 | 7830 | 2026-07-22
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4233585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127391115 | Completed | 27000 | 0 | 2025-06-29 | 2026-08-31
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4234204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128285905 | Completed | 27000 | 0 | 2026-04-16 | 2026-08-31
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4346028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118322447 | Completed | 27000 | 0 | 2026-04-16 | 2026-08-31
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4350378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127350394 | Completed | 27000 | 0 | 2026-06-15 | 2026-08-31
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4352633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128120443 | Completed | 27000 | 0 | 2025-06-29 | 2026-08-31
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4398768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117318283 | Ongoing | 27000 | 0 | 2026-06-15
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4398949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116312855 | Completed | 27000 | 0 | 2026-05-19 | 2026-08-31
BARWANI / SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4400100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117422121 | Approved | 27000 | 0 | 2022-05-25
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4400102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117422139 | Completed | 27000 | 0 | 2026-05-19 | 2026-08-31
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4401281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121979748 | Ongoing | 27000 | 0 | 2026-05-19
BARWANI / SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4405339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128287124 | Approved | 27000 | 0 | 2022-06-15
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4405452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127952954 | Completed | 27000 | 0 | 2025-06-29 | 2026-08-31
BARWANI / SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4405945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127848321 | Approved | 27000 | 0 | 2022-06-18
BARWANI / SENDHAWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4406468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127155711 | Approved | 27000 | 0 | 2022-11-04
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4820199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114055968 | Ongoing | 27000 | 0 | 2025-06-09
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4821002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116218516 | Physically Completed | 27000 | 0 | 2025-04-07 | 2026-09-11
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4821005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116218586 | Ongoing | 27000 | 0 | 2025-10-06
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4821006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116218602 | Physically Completed | 27000 | 0 | 2025-06-09 | 2026-09-11
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4824230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118321471 | Ongoing | 27000 | 0 | 2025-12-02
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4824404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123535180 | Approved | 27000 | 0 | 2024-09-23
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4825335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122755436 | Ongoing | 27000 | 0 | 2025-10-06
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4826167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125127884 | Physically Completed | 27000 | 0 | 2025-06-09 | 2026-09-11
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4827704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127850938 | Completed | 27000 | 0 | 2025-06-09 | 2026-08-31
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4827705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127853383 | Approved | 27000 | 0 | 2024-09-23
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4827982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128241471 | Approved | 27000 | 0 | 2024-09-26
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4828043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125222560 | Ongoing | 27000 | 0 | 2025-09-01
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4828832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128918642 | Completed | 27000 | 0 | 2025-06-09 | 2026-08-31
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4829348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127352791 | Approved | 27000 | 0 | 2024-10-09
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4829780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128300394 | Physically Completed | 27000 | 0 | 2025-06-09 | 2026-09-11
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4849117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123858909 | Physically Completed | 27000 | 0 | 2025-06-09 | 2026-09-11
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4854285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118322275 | Physically Completed | 27000 | 0 | 2025-07-19 | 2026-09-11
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4855258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127952527 | Ongoing | 27000 | 11745 | 2026-07-22
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4855931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125225864 | Approved | 27000 | 0 | 2024-11-04
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4856473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127357176 | Approved | 27000 | 0 | 2024-11-04
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4858640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128245071 | Completed | 27000 | 0 | 2025-06-09 | 2026-08-31
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4859132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127849978 | Ongoing | 27000 | 0 | 2025-06-06
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4889560 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127852648 | Approved | 27000 | 0 | 2024-11-04
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/4890130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127354284 | Approved | 27000 | 0 | 2024-09-26
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5456832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127855126 | Ongoing | 27000 | 0 | 2026-06-06
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5456833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127855480 | Ongoing | 27000 | 15660 | 2026-07-22
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5457263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125252283 | Approved | 27000 | 0 | 2025-03-24
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5459025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125827020 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5461415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127366159 | Physically Completed | 23490 | 0 | 2026-02-19 | 2026-08-09
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5461478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127851963 | Approved | 27000 | 0 | 2025-03-24
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5464256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129954878 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5465986 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127856672 | Ongoing | 27000 | 7830 | 2026-07-22
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5517550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128301526 | Ongoing | 27000 | 0 | 2026-07-06
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5517576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128276020 | Approved | 27000 | 0 | 2025-03-24
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5517577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128278452 | Approved | 27000 | 0 | 2025-03-24
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5517643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127862954 | Approved | 27000 | 0 | 2025-04-04
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5517819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127971367 | Physically Completed | 27000 | 0 | 2025-06-06 | 2026-09-11
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5519332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122765857 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5519376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127161200 | Ongoing | 27000 | 12330 | 2026-07-22
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5520733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126377140 | Approved | 27000 | 0 | 2025-04-04
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5524473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125817617 | Physically Completed | 23490 | 0 | 2025-09-01 | 2026-08-16
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5526439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128280325 | Approved | 27000 | 0 | 2025-04-16
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5529177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127352071 | Physically Completed | 27000 | 0 | 2025-07-19 | 2026-09-11
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5531322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127154883 | Physically Completed | 27000 | 16830 | 2026-07-09 | 2026-10-18
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5601081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125237390 | Ongoing | 27000 | 15660 | 2026-07-22
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5622896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125261411 | Physically Completed | 27000 | 0 | 2025-07-19 | 2026-09-11
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5624319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125320083 | Ongoing | 27000 | 8415 | 2026-07-22
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5653502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128915043 | Approved | 27000 | 0 | 2025-05-23
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5655159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125396927 | Approved | 27000 | 0 | 2025-04-04
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5698237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127971867 | Approved | 27000 | 0 | 2025-06-30
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5699874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118124334 | Ongoing | 27000 | 15660 | 2026-07-22
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5829816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129954777 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5829832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122761275 | Approved | 27000 | 0 | 2025-03-08
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5829848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123517522 | Approved | 27000 | 0 | 2025-03-08
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5829854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116218418 | Ongoing | 27000 | 15660 | 2026-08-13
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5829904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127864868 | Approved | 27000 | 0 | 2025-04-28
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5829964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121981139 | Physically Completed | 23490 | 0 | 2025-12-02 | 2026-08-09
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116582108 | Ongoing | 27000 | 0 | 2025-12-02
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128920593 | Approved | 27000 | 0 | 2024-11-07
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117422098 | Approved | 27000 | 0 | 2025-04-28
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128238552 | Ongoing | 27000 | 0 | 2025-10-10
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128240646 | Approved | 27000 | 0 | 2025-04-19
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128302685 | Approved | 27000 | 0 | 2025-04-04
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128303737 | Approved | 27000 | 0 | 2025-04-04
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128304925 | Approved | 27000 | 0 | 2025-04-06
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105855061 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123526742 | Approved | 27000 | 0 | 2025-05-02
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125110604 | Approved | 27000 | 0 | 2025-03-24
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106283229 | Physically Completed | 23490 | 0 | 2025-12-02 | 2026-08-09
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106402847 | Ongoing | 27000 | 0 | 2025-12-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125220461 | Approved | 27000 | 0 | 2025-04-29
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127921234 | Approved | 27000 | 0 | 2025-03-24
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127355751 | Approved | 27000 | 0 | 2025-03-10
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123525781 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113800918 | Ongoing | 27000 | 0 | 2025-12-02
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113691894 | Approved | 27000 | 0 | 2025-03-07
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127356466 | Approved | 27000 | 0 | 2024-11-04
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128277852 | Approved | 27000 | 0 | 2025-04-28
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118645135 | Approved | 27000 | 0 | 2025-03-07
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125225262 | Completed | 23490 | 0 | 2026-01-28 | 2026-09-02
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124980377 | Physically Completed | 23490 | 0 | 2025-03-24 | 2026-08-09
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125843222 | Approved | 27000 | 0 | 2025-03-08
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116218529 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116218567 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116218579 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127858286 | Approved | 27000 | 0 | 2025-04-06
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128139802 | Approved | 27000 | 0 | 2025-03-07
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125223171 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128245599 | Approved | 27000 | 0 | 2025-05-05
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129233176 | Approved | 27000 | 0 | 2025-03-24
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129233384 | Approved | 27000 | 0 | 2025-03-08
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129233569 | Approved | 27000 | 0 | 2025-03-24
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125235306 | Approved | 27000 | 0 | 2025-04-24
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131045880 | Physically Completed | 23490 | 8415 | 2026-07-14 | 2026-08-09
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122756007 | Approved | 27000 | 0 | 2025-05-05
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128273531 | Approved | 27000 | 0 | 2025-03-21
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128279072 | Ongoing | 27000 | 0 | 2025-10-06
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106053946 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125264058 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118322624 | Physically Completed | 27000 | 0 | 2025-10-06 | 2026-09-11
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128921544 | Approved | 27000 | 0 | 2025-03-24
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128244564 | Approved | 27000 | 0 | 2025-03-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118124360 | Approved | 27000 | 0 | 2025-05-13
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128532578 | Approved | 27000 | 0 | 2025-03-08
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5830990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125122453 | Approved | 27000 | 0 | 2025-03-08
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5831003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127402726 | Approved | 27000 | 0 | 2025-03-10
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5831009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129139770 | Physically Completed | 27000 | 0 | 2025-03-02 | 2026-08-30
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5831014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106043610 | Approved | 27000 | 0 | 2024-11-04
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5831053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128294305 | Physically Completed | 27000 | 0 | 2025-09-30 | 2026-09-11
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5831107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128303205 | Approved | 27000 | 0 | 2025-04-04
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5831112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125125389 | Approved | 27000 | 0 | 2025-04-21
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5874354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122756737 | Physically Completed | 27000 | 24660 | 2026-07-09 | 2026-09-06
BARWANI / SENDHAWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/5997617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128566233 | Approved | 27000 | 0 | 2024-09-26
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6203226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113921632 | Approved | 27000 | 0 | 2026-02-08
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6206911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127350991 | Approved | 27000 | 0 | 2026-02-23
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6252540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116582221 | Approved | 27000 | 0 | 2026-04-01
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6259221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121979999 | Approved | 27000 | 0 | 2026-05-11
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6267069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127166343 | Approved | 27000 | 0 | 2026-04-01
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6267610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127163492 | Approved | 27000 | 0 | 2026-04-01
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6268660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128662271 | Approved | 27000 | 0 | 2026-04-01
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6283017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125245647 | Approved | 27000 | 0 | 2026-04-01
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6287683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118819371 | Approved | 27000 | 0 | 2026-04-01
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6300647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118320528 | Approved | 27000 | 0 | 2026-04-01
BARWANI / SENDHAWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6302788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128239841 | Approved | 27000 | 0 | 2026-04-01
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6350105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113921706 | Approved | 27000 | 0 | 2026-02-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6350156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127398768 | Approved | 27000 | 0 | 2026-02-16
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6350615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121979239 | Approved | 27000 | 0 | 2026-02-16
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6350820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127357872 | Approved | 27000 | 0 | 2026-02-16
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6350907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128767705 | Approved | 27000 | 0 | 2026-02-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6351123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118645143 | Approved | 27000 | 0 | 2026-02-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6351124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127849303 | Approved | 27000 | 0 | 2026-02-08
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6351246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126904422 | Approved | 27000 | 0 | 2026-02-23
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6351321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125244306 | Approved | 27000 | 0 | 2026-02-02
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6351336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125246224 | Approved | 27000 | 0 | 2026-02-08
BARWANI / SENDHAWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1742007023/IF/IAY/6391367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121977608 | Approved | 27000 | 0 | 2026-02-16
BARWANI / SENDHAWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1742007023/WC/22012035172284 — Bolder Check Dem Nirman Dhanora | New | 0 | 0 | 2024-04-01
BARWANI / SENDHAWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1742/DP/22012034558189 — Bas Ropan Karya CN No 707 Dhanora | Ongoing | 1962000 | 0 | 2022-07-17