## Work List
Exported on: 2026-10-12 11:15:18
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JARWAHI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KATNI / KATNI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soakage Channel for Community / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1744002005/AV/22012034595293 — SLWM-SEGGRIGATION SHED NIRMAN KARYA JARWAHI | Ongoing | 597932.74 | 0 | 2021-11-01
KATNI / KATNI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Block Plantation of Forestry Trees in fields for Individual | Plantation | 1744002005/IF/22012034342295 — naveen talab ke pass vraksha ropan | Ongoing | 0 | 0 | 2017-05-30
KATNI / KATNI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1744002005/IF/22012035331928 — satiya Kol koop nirman karya jarwahi | Approved | 327631.47 | 0 | 2025-04-08
KATNI / KATNI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1744002005/IF/22012035359770 — Rajkumar / amrit lal koop nirman karya jarwahi | Approved | 0 | 0 | 2025-04-14
KATNI / KATNI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1744002005/IF/22012035540828 — Dugwell nirman karya mamta bai | Approved | 25899.46 | 0 | 2025-04-14
KATNI / KATNI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1744002005/LD/22012034949623 — कंटूर निर्माण कार्य खसरा नंबर 947 ग्राम पंचायत जरवाही | New | 0 | 0 | 2025-01-30
KATNI / KATNI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1744002005/WC/22012035220883 — CPT JARWAHI | Approved | 252359.77 | 0 | 2024-08-16
KATNI / KATNI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1744002005/WC/22012035223759 — CHEK BOULDER NIRMAN KARYA KAKARHA GHAT NALA 01 | Approved | 0 | 0 | 2024-10-02
KATNI / KATNI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1744002005/WC/22012035223779 — CHEK BOULDER NIRMAN KARYA kakarha ghat nala NO.2 | Approved | 0 | 0 | 2024-10-02
KATNI / KATNI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1744002005/WC/VB/22012035329516 — CONSTRUCTION OF STAGGERED TRENCH FOR COMMUNITY JARWAHI | Ongoing | 403276.53 | 73098.05 | 2026-08-02
KATNI / KATNI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1744002005/WC/VB/22012035329520 — Construction of Roof top rain water harvesting samudayik bhawan jarwahi | Approved | 0 | 0 | 2026-06-15