## Work List
Exported on: 2026-10-10 17:25:32
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: PDUA
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KATNI / KATNI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1744002006/DP/22012034584580 — plantation work Vasudha vandan muktidham jayantinagar | Physically Completed | 54564.94 | 34049.56 | 2023-08-07 | 2026-01-20
KATNI / KATNI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1744002006/RC/22012034648294 — सुदूर सड़क निर्माण जयंती नगर टोला से रामकुमार आदिवासी के खेत तक | Physically Completed | 1313264 | 1190337.81 | 2023-08-25 | 2026-04-02
KATNI / KATNI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1744002006/WC/22012035213559 — Dharam Sagar Talab Jibuddin Avn Sundarikaran Karya | Physically Completed | 810000 | 802490.32 | 2024-06-30 | 2026-04-08