## Work List
Exported on: 2026-10-12 03:04:52
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KHITOLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KATNI / BADWARA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1744003046/AV/22012034510887 — खेल प्रोत्‍साहन हेतु स्‍टेडियम निर्माण कार्य | Ongoing | 1794000 | 0 | 2020-07-26
KATNI / BADWARA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Line Plantation of Horticulture Trees for Community | Plantation | 1744003046/DP/22012034563824 — कन्या हाई स्कूल खितौली मे व्रक्षारोपण कार्य | Ongoing | 240870.31 | 3000 | 2022-08-18
KATNI / BADWARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1744003046/IF/22012035477625 — richarge pit nirman kary dhanaiya rajak | New | 0 | 0 | 2025-04-13
KATNI / BADWARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1744003046/IF/22012035479184 — DRUGWEL RECHARGE PIT SHIVPRASAD / RURU | Physically Completed | 25899.46 | 0 | 2025-05-08 | 2026-07-21
KATNI / BADWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744003046/IF/22012035511163 — KHET TALAB NIRMAN KARY KHITAULI DHANAI / DHEENA RAJAK | Ongoing | 147621.16 | 0 | 2025-05-14
KATNI / BADWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744003046/IF/22012035511208 — KHET TALAB NIRMAN KARY KHITAULI SHEETAL PRASAD / PUNNA CHAUDAHRI | Ongoing | 147621.16 | 0 | 2025-05-14
KATNI / BADWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744003046/IF/22012035511246 — KHET TALAB NIRMAN KARY MIDRA SAMPAT / PUSAU | Ongoing | 147621.16 | 0 | 2025-05-14
KATNI / BADWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744003046/IF/22012035511312 — KHET TALAB NIRMAN KARY MIDRA GUDDI BAI / PADAM SINGH | Ongoing | 147621.16 | 0 | 2025-05-14
KATNI / BADWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744003046/IF/22012035516601 — KHET TALAB NIRMAN KARY KHITAULI NEETRAJ SINGH / DHANRAJ SINGH | Approved | 147621.16 | 0 | 2025-04-14
KATNI / BADWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744003046/IF/22012035516617 — KHET TALAB NIRMAN KARY KHITAULI YADVENDRA DUBEY / SANTOSH DUBEY | Approved | 147621.16 | 0 | 2025-04-14
KATNI / BADWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744003046/IF/22012035516645 — KHET TALAB NIRMAN KARY MIDRA SONAI CHARKU | Approved | 147621.16 | 0 | 2025-04-14
KATNI / BADWARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1744003046/IF/22012035559533 — हितग्राही मूलक सोक पिट निर्माण कार्य अमरनाथ / रामकुमार चतुर्वेदी | Approved | 0 | 0 | 2025-04-14
KATNI / BADWARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1744003046/IF/22012035559543 — हितग्राही मूलक सोक पिट निर्माण कार्य धनिराम / अंगद उरमलिया ग्राम खितौली | Approved | 0 | 0 | 2025-04-14
KATNI / BADWARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1744003046/IF/22012035559549 — हितग्राही मूलक सोक पिट निर्माण कार्य संतोष सिंह / अजब सिंह ग्राम खितौली | Approved | 0 | 0 | 2025-04-14
KATNI / BADWARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1744003046/IF/22012035559557 — हितग्राही मूलक सोक पिट निर्माण कार्य मनोज तिवारी / ओमप्रकास तिवारी ग्राम खितौली | Approved | 0 | 0 | 2025-04-14
KATNI / BADWARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1744003046/IF/22012035559569 — हितग्राही मूलक सोक पिट निर्माण कार्य संतोष सोनी / सुंदर लाल ग्राम खितौली | Approved | 0 | 0 | 2025-04-14
KATNI / BADWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744003046/IF/22012035559663 — हितग्राही मूलक नाड़ेप निर्माण कार्य संतोष सोनी / सुंदर लाल ग्राम खितौली | Approved | 0 | 0 | 2025-04-14
KATNI / BADWARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744003046/IF/IAY/3315087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3996522 | Approved | 27000 | 0 | 2021-11-02
KATNI / BADWARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744003046/IF/IAY/3490472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4613118 | Approved | 27000 | 0 | 2021-12-30
KATNI / BADWARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744003046/IF/IAY/3559973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4992981 | Approved | 27000 | 0 | 2022-01-06
KATNI / BADWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744003046/IF/IAY/4659359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147992421 | Ongoing | 27000 | 0 | 2024-10-07
KATNI / BADWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744003046/IF/IAY/5101232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147991992 | Ongoing | 27000 | 0 | 2025-07-21
KATNI / BADWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744003046/IF/IAY/5853860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146911885 | Ongoing | 27000 | 0 | 2026-02-01
KATNI / BADWARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744003046/IF/IAY/5853992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150967800 | Ongoing | 27000 | 0 | 2025-11-14
KATNI / BADWARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744003046/IF/IAY/6307725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147991483 | Approved | 27000 | 0 | 2025-03-27
KATNI / BADWARA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1744003046/RC/22012034655206 — सुदूर सड़क खितौली रेस्ट हाऊस के बगल से स्टेडियम होते हुये शा. कन्या हा स्कूल तक पहुच मार्ग निर्माण | Ongoing | 1012366.59 | 0 | 2023-10-08
KATNI / BADWARA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1744003046/RC/22012034677959 — सी0 सी0 रोड निर्माण कार्य | New | 0 | 0 | 2023-10-02
KATNI / BADWARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1744003046/RC/22012034830493 — सीमेंट कंकरीट सड़क मार्ग आगनवाड़ी से महिला घाट एव पुरुष घाट तक | Approved | 102000 | 0 | 2024-10-02
KATNI / BADWARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1744003046/RC/22012034830498 — सीमेंट कंकरीट सड़क मार्ग वार्ड क्रमांक 09 pwd रोड से गणेश शुक्ला के घर तक | Approved | 92000 | 0 | 2024-10-02
KATNI / BADWARA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1744003046/RC/22012034854034 — हदरहटा से करचुलहा पहुँच मार्ग निर्माण कार्य ग्राम- खितौली | Approved | 1025794.28 | 0 | 2026-04-14
KATNI / BADWARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1744003046/WC/22012035222023 — construction of community water harvesting ponds | Approved | 0 | 0 | 2024-10-02