## Work List
Exported on: 2026-10-23 15:02:31
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PADWAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KATNI / VIJAYRAGHAVGADH | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1744004005/AV/22012034375093 — anganwadi bhawan nirman krya chhata | Ongoing | 500000 | 0 | 2018-10-02
KATNI / VIJAYRAGHAVGADH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1744004005/DP/22012034493294 — pahalwan ke khet ke pas plantation karya | Ongoing | 677985.75 | 0 | 2020-08-07
KATNI / VIJAYRAGHAVGADH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1744004005/DP/22012034618894 — plantation muktidham ke pas chhata gram | Ongoing | 453563.17 | 0 | 2024-07-11
KATNI / VIJAYRAGHAVGADH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1744004005/IF/22012035283229 — Dug Well for individual kapildhara koop for irrigation rambhan ramdash rathore | Ongoing | 262882.73 | 0 | 2025-03-21
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744004005/IF/22012035340348 — Form pond pramod jaybhan singh | Ongoing | 219662.28 | 0 | 2025-04-20
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744004005/IF/22012035340364 — Form Pond ramlal hanuman singh | Ongoing | 219662.28 | 0 | 2025-04-20
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1744004005/IF/22012035523541 — construction of cattle shelter heeralal barelala rathore | Ongoing | 72920.12 | 0 | 2025-05-23
KATNI / VIJAYRAGHAVGADH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1744004005/IF/22012035525592 — Form pond for individual awadh raj maniram | Approved | 199516.62 | 0 | 2025-04-02
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744004005/IF/22012035525601 — Form pond for individual maniram bihari lal | Approved | 219662.28 | 0 | 2025-04-02
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1744004005/IF/22012035525615 — Form pond for individual govind ramvishal | Approved | 219662.28 | 0 | 2025-04-02
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1744004005/IF/22012035618620 — construction of cattle sumityra kanchhedi lal | Approved | 72059.92 | 0 | 2025-04-02
KATNI / VIJAYRAGHAVGADH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744004005/IF/IAY/1994219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2741763 | Ongoing | 27000 | 0 | 2019-08-25
KATNI / VIJAYRAGHAVGADH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744004005/IF/IAY/3440868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5539341 | Ongoing | 27000 | 0 | 2022-07-26
KATNI / VIJAYRAGHAVGADH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744004005/IF/IAY/3911133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150691158 | Ongoing | 27000 | 0 | 2022-08-09
KATNI / VIJAYRAGHAVGADH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744004005/IF/IAY/4357252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150602338 | Ongoing | 27000 | 0 | 2022-11-03
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744004005/IF/IAY/4681593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147687908 | Physically Completed | 23490 | 3402 | 2025-05-24 | 2026-08-02
KATNI / VIJAYRAGHAVGADH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744004005/IF/IAY/4683358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148674925 | Ongoing | 27000 | 6804 | 2024-10-25
KATNI / VIJAYRAGHAVGADH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744004005/IF/IAY/4683359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148675143 | Ongoing | 27000 | 7056 | 2024-10-05
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744004005/IF/IAY/4834489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148675193 | Ongoing | 27000 | 0 | 2025-05-24
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744004005/IF/IAY/5101526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148140542 | Ongoing | 27000 | 0 | 2025-04-21
KATNI / VIJAYRAGHAVGADH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744004005/IF/IAY/5106855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150557509 | Approved | 27000 | 0 | 2025-02-27
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1744004005/IF/IAY/5669808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145129649 | Ongoing | 27000 | 3132 | 2026-01-02
KATNI / VIJAYRAGHAVGADH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1744004005/LD/22012034951349 — Earthetn CPT talab ke pas padwai | Ongoing | 1070085 | 61504 | 2025-04-12
KATNI / VIJAYRAGHAVGADH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1744004005/RS/22012034682073 — Nali Nirman Kary Prathamik Shala school Ke pass Chhta | Ongoing | 9000 | 0 | 2023-12-06