## Work List
Exported on: 2026-09-30 23:14:13
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BARHATA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KATNI / VIJAYRAGHAVGADH | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1744004029/AV/22012034375094 — aganwadi bhawan nirman barhati | Ongoing | 500000 | 0 | 2018-09-28
KATNI / VIJAYRAGHAVGADH | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1744004029/AV/22012034537976 — वाण्ड्रीवाल निर्माण प्राथमिक शाला गोइन्द्रा | Ongoing | 135000 | 0 | 2020-10-08
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1744004029/IF/22012035329906 — Form pond ramesh prasad pita lalu lal baheli | Ongoing | 219662.28 | 0 | 2025-04-20
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744004029/IF/22012035349965 — dugwell kapil dhara koop phoolchand /dhanpad gadari | Approved | 0 | 0 | 2025-04-02
KATNI / VIJAYRAGHAVGADH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1744004029/IF/22012035531395 — open well reacharge lalwa nandi | Ongoing | 25899.46 | 0 | 2025-05-22
KATNI / VIJAYRAGHAVGADH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1744004029/IF/22012035548109 — open well reacharge phoolchand dhanpad gadarhi | Approved | 25899.46 | 0 | 2025-04-02
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1744004029/IF/22012035548290 — Form pond for individual ramgopal ganesh | Approved | 199516.62 | 0 | 2025-04-02
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744004029/IF/22012035585801 — ek bagiya ma ke nam sunita lvkush baheliya | Ongoing | 184025.5 | 0 | 2025-09-04
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744004029/IF/22012035585803 — ek bagiya ma ke nam putti ramswaroop choudhery | Ongoing | 183634.14 | 0 | 2025-09-11
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744004029/IF/22012035585804 — ek bagiya ma ke nam munni bai ramlakhan baheliya | Ongoing | 183139.61 | 0 | 2025-08-28
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744004029/IF/22012035585806 — ek bagiya ma ke nam arita singfh dharmendra singh baheliya | Ongoing | 184606.18 | 0 | 2025-08-28
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744004029/IF/22012035585809 — ek bagiya ma ke nam pooja bai ramai choudhery | Ongoing | 184409.03 | 0 | 2025-08-28
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744004029/IF/22012035585811 — ek bagiya ma ke nam rajkumari iswardeen pal | Ongoing | 184649.64 | 0 | 2025-08-22
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744004029/IF/22012035585813 — ek bagiya ma ke nam salni gopal singh gond | Ongoing | 184530.26 | 0 | 2025-08-28
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1744004029/IF/22012035585816 — ek bagiya ma ke nam archna hanumat baheliya | Ongoing | 183233.48 | 0 | 2025-08-28
KATNI / VIJAYRAGHAVGADH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1744004029/IF/22012035648612 — kapildhara koop rajendra jagannth jaiswal goindra | Ongoing | 193157.69 | 0 | 2026-03-20
KATNI / VIJAYRAGHAVGADH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1744004029/IF/IAY/4834070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149994559 | Ongoing | 27000 | 0 | 2024-12-12
KATNI / VIJAYRAGHAVGADH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1744004029/IF/IAY/943657 — Construction of IAY House -IAY REG. NO. MP2885070 | Ongoing | 27000 | 0 | 2022-12-13
KATNI / VIJAYRAGHAVGADH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1744004029/RC/22012034821910 — GFFSDFSFSFs | Approved | 430960 | 0 | 2024-04-01