## Work List
Exported on: 2026-10-02 00:06:05
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KACHHARI MAL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DINDORI / SHAHPURA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1745001059/AV/22012034550010 — Boundry Wal Nirman Gram Panchayat Bhawan Kachhari Mal | Physically Completed | 813995.67 | 0 | 2021-02-26 | 2026-09-28
DINDORI / SHAHPURA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1745001059/AV/22012034550012 — Boundry Wall Nirman Aganwadi Bawan Kachhari Mal | Ongoing | 923672.29 | 0 | 2021-02-19
DINDORI / SHAHPURA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1745001059/DP/22012034594331 — Plantation Work Meri Mati Mera Desh Bandh Ke Kinare GP Kachhari Mal | Ongoing | 120481.69 | 0 | 2023-08-09
DINDORI / SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1745001059/IC/22012034886648 — Gali Plug Nirman Karya Patpar Nala Ghusiya Ryt GP Kachhari Mal | New | 0 | 0 | 2024-08-16
DINDORI / SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1745001059/IC/22012034886649 — Gali Plug Nirman Karya Tadhiya Nala Ghusiya Ryt GP Kachhari Mal | New | 0 | 0 | 2024-08-16
DINDORI / SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1745001059/IC/22012034886650 — Gali Plug Nirman Karya Saraiha Nala Ghusiya Ryt GP Kachhari Mal | New | 0 | 0 | 2024-08-16
DINDORI / SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1745001059/IC/22012034886651 — Gali Plug Nirman Karya Garhani Nala Ghusiya Ryt GP Kachhari mal | New | 0 | 0 | 2024-08-16
DINDORI / SHAHPURA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1745001059/IF/22012034639437 — Med Bandhan Fulsingh/Lalsaiya GP Kachhari Mal | Ongoing | 70756.99 | 0 | 2021-04-01
DINDORI / SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1745001059/IF/22012035202510 — Pashu Shed Parvati/Balram GP Kachhari Mal | Ongoing | 132607.74 | 0 | 2025-03-04
DINDORI / SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1745001059/IF/22012035322073 — Koop Nirman Karya Vishram/ Churaman GP Kachhari Mal | Approved | 0 | 0 | 2025-04-01
DINDORI / SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1745001059/IF/22012035541098 — JGSA Contruction Of Farm Pond For Amrit/Saddhu GP Kachhari Mal | Ongoing | 183470.21 | 0 | 2025-05-25
DINDORI / SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1745001059/IF/22012035545269 — JGSA Contruction Of Farm Pond For Puniya/Gangaram GP Kachhari Mal | Ongoing | 183470.21 | 0 | 2025-05-25
DINDORI / SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1745001059/IF/22012035553247 — JGSA Contraction Of Farm Pond Radhe Singh Dasole GP Kachhari Mal | Approved | 0 | 0 | 2025-04-14
DINDORI / SHAHPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745001059/IF/IAY/3880904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147160742 | Approved | 28500 | 0 | 2022-05-01
DINDORI / SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745001059/IF/IAY/5848840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142209369 | Approved | 28500 | 0 | 2025-04-13
DINDORI / SHAHPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1745001059/WC/22012035209808 — Talab Gahrikaran Ghusiya Ryt GP Kachhari Mal | Approved | 0 | 0 | 2024-04-14
DINDORI / SHAHPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1745001059/WC/22012035232802 — Gali Plug Tadhiya Nala Ghusiya GP Kachhari Mal | Approved | 0 | 0 | 2024-08-16
DINDORI / SHAHPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1745001059/WC/22012035232803 — Gali Plug Patpar nala Ghusiya GP Kachhari Mal | Approved | 0 | 0 | 2024-08-16
DINDORI / SHAHPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1745001059/WC/22012035249410 — Talab Nirman Karya Bda Kholkha Kachhari Mal | Approved | 0 | 0 | 2025-01-26
DINDORI / SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1745001059/WC/22012035267761 — jgsa 2025 Sarvajanik Koop Bhurka Tola GP Kachhari Mal | Physically Completed | 594852.25 | 0 | 2025-05-08 | 2026-09-28
DINDORI / SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1745001059/WC/22012035267870 — jgsa 2025 Talab Nirman Karya Bda Khokha Kachhari Mal | Ongoing | 2440987.43 | 1616.24 | 2025-05-08
DINDORI / SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1745001059/WC/22012035296689 — JGSA Contruction Of Roof Top Rain Water Hervesting Panchayat Bhawan Kachhari Mal | Ongoing | 36697.7 | 0 | 2025-05-08
DINDORI / SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1745001059/WC/22012035325652 — BOULDER CHECK NIRMAN KARUNA NALA GHUSIYA RAYAT G P KACHHARI MAL | Approved | 1241843.58 | 0 | 2025-12-25
DINDORI / SHAHPURA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1745001059/WC/22012035325658 — BOULDER CHECK NIRMAN KARUNA NALA part 2 GHUSIYA RAYAT G P KACHHARI MAL | Approved | 0 | 0 | 2025-12-25
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745001059/WC/VB/22012035329819 — Counter Trench Nirman Karya Khoriya Path Kachhari Mal GP Kachhari Mal | Ongoing | 201335.8 | 41205 | 2026-08-05
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745001059/WC/VB/22012035329822 — Contoor Trench Nirman Karya Nan Kholkha Kachhari Mal | Ongoing | 201335.8 | 16195 | 2026-08-13
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745001059/WC/VB/22012035329913 — Conteer Trench Nirman Nan Kholkha 2 Kachhari Mal GP Kachhari Mal | Ongoing | 201335.8 | 18245.89 | 2026-08-13
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745001059/WC/VB/22012035329916 — Contoor Trench Nirman Khoriya Path 2 Kachhari Mal GP Kachhari Mal | Ongoing | 201335.8 | 13939.32 | 2026-08-13
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745001059/WC/VB/22012035329920 — Cantoor Trench Nirman Thuti Ber Dungariya Pahad Ghusiya Ryt GP Kachhari Mal | Ongoing | 201335.8 | 26651.3 | 2026-08-13
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745001059/WC/VB/22012035329924 — Contoor Trench Nirman Tuthi Ber Dungariya Pahad 2 Ghusiya Ryt Mal GP Kachhari Mal | Ongoing | 201335.8 | 24598.8 | 2026-08-13
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745001059/WC/VB/22012035329926 — Contoor Trench Nirman Pakarha Pahad Ghusiya Ryt GP Kachhari Mal | Ongoing | 314222.8 | 0 | 2026-08-18
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1745001059/WC/VB/22012035329931 — Contoor Trench Nirman Pakarha Nala 2 Ghusiya Ryt GP Kachhari Mal | Approved | 0 | 0 | 2026-04-14
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1745001059/WC/VB/22012035330243 — Bolder Check Nirman Barsaja Nala Kachhari GP Kachhari Mal | Approved | 0 | 0 | 2026-04-14
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1745001059/WC/VB/22012035330245 — Bolder Check Nirman Barapani Nala Kachhari Mal | Approved | 0 | 0 | 2026-04-14
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1745001059/WC/VB/22012035330247 — Bolder Check Nirman Bandariya Naswa Ghusiya GP Kachhari Mal | Approved | 0 | 0 | 2026-04-14
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1745001059/WC/VB/22012035330249 — Bolder Check Nirman Kolbahra Nala Ghusiya GP Kachhari Mal | Approved | 0 | 0 | 2026-04-14
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1745001059/WC/VB/22012035330252 — Bolder Check Nirman Kosam Nala Kachhari Mal | Approved | 0 | 0 | 2026-04-14
DINDORI / SHAHPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1745/WC/22012035005684 — WRD Repairing and Maintenance work of Canal of kachhari tank (Gram panchyat-Kachhari mal) | Ongoing | 971000 | 0 | 2022-11-18
DINDORI / SHAHPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1745/WC/22012035006535 — WRD Repairing and Maintenance work of V.R.B. Main canal of KACHHARI TANK (G.P.- KACHHARI MAL) | Ongoing | 984000 | 0 | 2022-11-18
DINDORI / SHAHPURA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1745/WC/22012035008160 — WRD Repairing & Maintenance work Construction of C.D. and canal of kachhari tank (G.P.-Kachhari Mal) | Ongoing | 994000 | 0 | 2022-11-18