## Work List
Exported on: 2026-10-10 11:02:05
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: RAIPURA MAL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DINDORI / SHAHPURA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1745001068/IF/22012035312721 — KHET TALAB NIRMAN MANNU/RAMSUROOP LALPUR G P RAIPURA | Approved | 0 | 0 | 2025-01-20
DINDORI / SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1745001068/IF/22012035645765 — peripheral stone bund hitgrahi ramphal/kalua gram raipura g p raipura | Ongoing | 94003.16 | 0 | 2026-03-15
DINDORI / SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1745001068/IF/22012035645795 — peripheral stone bund bhupendra/bhansingh gram raipura g p raipura | Ongoing | 67020.76 | 0 | 2026-03-15
DINDORI / SHAHPURA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745001068/IF/IAY/3262920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4368971 | Approved | 28500 | 0 | 2021-10-22
DINDORI / SHAHPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745001068/IF/IAY/3826037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121511418 | Approved | 28500 | 0 | 2022-05-02
DINDORI / SHAHPURA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745001068/IF/IAY/4215846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128160572 | Approved | 28500 | 0 | 2022-06-12
DINDORI / SHAHPURA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745001068/IF/IAY/5326448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128160046 | Ongoing | 28500 | 1500 | 2025-04-18
DINDORI / SHAHPURA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1745001068/RS/22012034530316 — SLWM Yojna ke taha Segrigetion Nirman karya G.P. Raipura | Ongoing | 612769.18 | 0 | 2021-08-17
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001068/WC/VB/22012035329750 — Countoor trench Lalpur sarhad gram Raipura gp Raipura | Ongoing | 201335.8 | 55802.79 | 2026-08-17
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001068/WC/VB/22012035329755 — Countoor trench majhgaon sarhad gram Raipura gp Raipura | Ongoing | 201335.8 | 101549.15 | 2026-08-03
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001068/WC/VB/22012035329757 — Countoor trench saraiyha pahad gram Raipura gp Raipura | Ongoing | 102602 | 54453.96 | 2026-08-03
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001068/WC/VB/22012035329759 — Countoor trench khulki pahadh gram Lalpur gp Raipura | Ongoing | 201335.8 | 0 | 2026-09-03
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001068/WC/VB/22012035329762 — Countoor trench dadri pahadh gram Lalpur gp Raipura | Ongoing | 201335.8 | 109382.83 | 2026-08-03
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001068/WC/VB/22012035329765 — Countoor trench chamar kundi pahadh gram Raipura gp Raipura | Ongoing | 201335.8 | 36599.84 | 2026-08-17
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001068/WC/VB/22012035329820 — Countoor trench milodi sarhad gram Lalpur gp Raipura | Ongoing | 201335.8 | 105312.41 | 2026-08-03
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745001068/WC/VB/22012035329827 — Boulder check 1 gram Lalpur gp Raipura | Physically Completed | 29065.74 | 14708.4 | 2026-08-18 | 2026-09-16
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1745001068/WC/VB/22012035329831 — Boulder check 2 gram Lalpur gp Raipura | Physically Completed | 29065.74 | 14470.56 | 2026-08-18 | 2026-09-16
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001068/WC/VB/22012035329836 — Countoor trench khulki pahadh 2 gram Lalpur gp Raipura | Ongoing | 201335.8 | 128987.48 | 2026-08-03
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001068/WC/VB/22012035329843 — Countoor trench majhgaon sarhad 2 gram Raipura gp Raipura | Ongoing | 201335.8 | 98423.39 | 2026-08-03
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1745001068/WC/VB/22012035330377 — Countoor trench khudari pahadh gram Lalpur gp Raipura | Ongoing | 201335.8 | 0 | 2026-09-03
DINDORI / SHAHPURA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1745001068/WC/VB/22012035330380 — Countoor trench mandogri pahadh gram Lalpur gp Raipura | Ongoing | 201335.8 | 0 | 2026-09-03
DINDORI / SHAHPURA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1745001068/WH/22012034940898 — GABION NIRMAN KARYA AJIVIKA BHAVAN KE PAS GRAM RAIPURA GP RAIPURA | Approved | 0 | 0 | 2024-06-08