## Work List
Exported on: 2026-10-01 04:12:43
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KHAIRDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DINDORI / AMARPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1745003041/AV/22012034586704 — boundriwal nirman karya p.s m.s. school khairda | Ongoing | 1209198.07 | 0 | 2021-08-27
DINDORI / AMARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1745003041/AV/22012034657395 — Puliya nirman karya baigan tola | New | 0 | 0 | 2024-05-10
DINDORI / AMARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1745003041/AV/22012034657397 — Puliya nirman karya baigan tola | New | 0 | 0 | 2024-05-10
DINDORI / AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745003041/DP/22012034629348 — GJSA PLANTAION WORK MAIN ROAD SAKRAHI NALA TO BARGA BECH TOLA | Approved | 0 | 0 | 2025-04-16
DINDORI / AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745003041/DP/22012034629349 — GJSA PLANTAION WORK MAIN ROAD SAKRAHI NALA SE NAYA TOLA KHAIRDA TK PARAT 01 | Approved | 0 | 0 | 2025-04-15
DINDORI / AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745003041/DP/22012034629350 — GJSA PLANTAION WORK MAIN NAYA TOLA TIRAHA SE KHAIRDA SARAHAD TK PART 2 | Approved | 0 | 0 | 2025-04-15
DINDORI / AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745003041/DP/22012034629355 — JGSA Road side Plantation Sakrahi Nalla to NAye tola Tiraha Part 1 | Ongoing | 480330.71 | 20160 | 2025-05-06
DINDORI / AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745003041/DP/22012034629358 — JGSA Road side Plantation Naya tola tiraha to Khairda Sarhad Part 2 | Ongoing | 480330.71 | 13650 | 2025-05-06
DINDORI / AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1745003041/DP/22012034629360 — JGSA Road side Plantation Sakrahi Nalla to Beech tola Barga | Ongoing | 480330.71 | 21257 | 2025-05-06
DINDORI / AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1745003041/DP/VB/22012034630863 — contor tranch nirman kary sarehan jangal sarhad ke pass bhag2 | Approved | 0 | 0 | 2026-07-10
DINDORI / AMARPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1745003041/IF/22012034311577 — KHET TALAB SAH KUP NIRMAN PRAHLAD SINGH/ SUKALI | Ongoing | 230000 | 0 | 2017-01-20
DINDORI / AMARPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1745003041/IF/22012034470182 — khet talab sah koop nirman kary moti singh / hari singh | Ongoing | 230000 | 0 | 2019-03-09
DINDORI / AMARPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1745003041/IF/22012034470200 — KHET TALAB SAH KOOP NIRMAN KARE LAXMIKANT | Ongoing | 230000 | 0 | 2019-03-11
DINDORI / AMARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1745003041/IF/22012035446973 — JGSA Construction Of Farm Pond Koushalya bai/Roop singh Khairda | Approved | 0 | 0 | 2025-04-10
DINDORI / AMARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1745003041/IF/22012035447059 — JGSA Construction Of Farm Pond Pushpraj tekam/Jagdish | New | 0 | 0 | 2025-04-10
DINDORI / AMARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1745003041/IF/22012035629365 — Ek Bagiya Ma Ke Name Ishvar Bai / Mangal MP45003041001/134 Khairda | New | 0 | 0 | 2025-10-02
DINDORI / AMARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1745003041/IF/22012035630497 — Ek Bagiya Ma Ke Name Durgavati / Brajkumar MP45003041001/5 Khairda | New | 0 | 0 | 2025-10-03
DINDORI / AMARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003041/IF/IAY/2704127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5638219 | Ongoing | 28500 | 0 | 2021-05-25
DINDORI / AMARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003041/IF/IAY/2710036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5553158 | Ongoing | 28500 | 0 | 2021-07-06
DINDORI / AMARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003041/IF/IAY/3278935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5574339 | Approved | 28500 | 0 | 2021-10-13
DINDORI / AMARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003041/IF/IAY/3759861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127215544 | Ongoing | 28500 | 1566 | 2022-06-23
DINDORI / AMARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003041/IF/IAY/3900243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149529855 | Approved | 28500 | 0 | 2022-05-02
DINDORI / AMARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003041/IF/IAY/4243854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116240833 | Approved | 28500 | 0 | 2022-06-21
DINDORI / AMARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003041/IF/IAY/5517750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151951421 | Completed | 24795 | 0 | 2025-05-09 | 2026-08-20
DINDORI / AMARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003041/IF/IAY/5523009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152091894 | Ongoing | 28500 | 0 | 2025-05-22
DINDORI / AMARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003041/IF/IAY/5848683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141841375 | Approved | 28500 | 0 | 2025-02-20
DINDORI / AMARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1745003041/IF/IAY/5876640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126246404 | Ongoing | 28500 | 0 | 2026-04-20
DINDORI / AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1745003041/WC/22012035266019 — JGSA Construction Of Naveen Talab Sajpani Khairda | Physically Completed | 1737016.57 | 0 | 2025-06-14 | 2026-08-22
DINDORI / AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1745003041/WC/22012035296694 — JGSA Dug well Recharge Pit Bhainswahi 2 | Approved | 0 | 0 | 2025-04-10
DINDORI / AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1745003041/WC/VB/22012035333673 — gabian structure palla kachhar nala | Approved | 0 | 0 | 2026-07-10
DINDORI / AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1745003041/WC/VB/22012035333675 — gabian structure bhangta nala barga | Approved | 0 | 0 | 2026-07-10
DINDORI / AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1745003041/WC/VB/22012035333676 — gabian structure dhulbaja nala khairda | Approved | 0 | 0 | 2026-07-10
DINDORI / AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1745003041/WC/VB/22012035333677 — bolder chek wall dhan singh ke khet ke pass nala me | Approved | 0 | 0 | 2026-07-10
DINDORI / AMARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1745003041/WC/VB/22012035333678 — bolder chek wall son singh ke khet ke pass nala me barga | Approved | 0 | 0 | 2026-07-10
DINDORI / AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1745003041/WH/22012034944374 — JGSA Renovation Of Dhulbaja Talab Khairda | New | 0 | 0 | 2025-04-10
DINDORI / AMARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1745003041/WH/22012034944375 — JGSA Renovation Of Dhulbaja Talab Khairda | Approved | 0 | 0 | 2025-04-10
DINDORI / AMARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1745/WC/22012034998479 — WRD Repairing and Manintenance work of Canal BARGATOLA TANK (G.P.- KHAIRDA) PART-09 | Ongoing | 989000 | 0 | 2024-06-09