## Work List
Exported on: 2026-10-08 13:17:23
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: CHANDANA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Agro Forestry Block Plantation in Waste Lands for Community | Plantation | 1745006032/DP/22012034629606 — JGSA Vrachharopan Chandna Ryt Se Badi Mohla Ki Or Gp Chandna Jp Karanjiya | Approved | 0 | 0 | 2025-04-14
DINDORI / KARANJIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1745006032/IF/22012034939920 — Kapildhara Koop - Narbad / Budhu Gp Chandna Jp Karanjiya | Ongoing | 275727.6 | 0 | 2022-05-27
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1745006032/IF/22012035272544 — खेत तालाब कामता सिंह / बैसाखू ग्राम पंचायत चंदना ज.प. करंजिया | New | 0 | 0 | 2024-11-18
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1745006032/IF/22012035276296 — Khet Talab Ramesh / Sukhram Gp Chandna Ryt Jp Kranjiya | Approved | 0 | 0 | 2024-10-21
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1745006032/IF/22012035276643 — Kapidhara Koop Dinesh / Dukh Singh Gp Chandna Jp Kraanjiya | New | 0 | 0 | 2024-10-21
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1745006032/IF/22012035276652 — Kapildhara Koop Vinod / Dukh Singh Gp Chandna Jp Kranjiya | New | 0 | 0 | 2024-10-21
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1745006032/IF/22012035277316 — Kapildhara Koop Vinod / Dukh Singh Gp Chandna Jp Kranjiya | New | 0 | 0 | 2024-10-21
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1745006032/IF/22012035301176 — Khet Talab - Chamrin / Ramsingh Gp Chandna Jp Karanjiya | Approved | 0 | 0 | 2024-12-18
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1745006032/IF/22012035307195 — Khet Talab Chamrin /Ramvati / kKumbhprasad Gp Chandna | Approved | 0 | 0 | 2024-11-19
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1745006032/IF/22012035307198 — Khet Talab Lalman/Bramha Gp Chandna Jp Karanjiya | Approved | 0 | 0 | 2024-11-19
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1745006032/IF/22012035307199 — Khet Talab Sankarlal/Babulal Gp Chandna Jp Karanjiya | New | 0 | 0 | 2024-11-19
DINDORI / KARANJIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1745006032/IF/22012035326796 — Khet Talab - Kalawati / Chattar Gp Chandna Jp Karanjiya | Approved | 0 | 0 | 2025-04-07
DINDORI / KARANJIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1745006032/IF/22012035326871 — Kapildhara Koop - Kuvar Singh / Ramprasad Gp Chandna Jp Karanjiya | New | 0 | 0 | 2025-04-07
DINDORI / KARANJIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1745006032/IF/22012035427882 — JGSA Khet Talab Kunti / Narbadprasad Gp CChandna Jp Karanjiya | Approved | 0 | 0 | 2025-04-08
DINDORI / KARANJIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1745006032/IF/22012035541064 — Kapildhara Koop Kunwar Singh / Ramprasad Gp Chandna Jp Kranjiya | New | 0 | 0 | 2025-04-14
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745006032/IF/IAY/4868602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152043910 | Approved | 28500 | 0 | 2024-12-02
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745006032/IF/IAY/4868616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152044163 | Approved | 28500 | 0 | 2024-12-02
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745006032/IF/IAY/4868617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152044165 | Approved | 28500 | 0 | 2024-12-02
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745006032/IF/IAY/4868936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152063976 | Approved | 28500 | 0 | 2024-12-02
DINDORI / KARANJIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745006032/IF/IAY/4886381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152056936 | Ongoing | 28500 | 0 | 2026-05-15
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745006032/IF/IAY/5172194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117757709 | Approved | 28500 | 0 | 2025-03-01
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745006032/IF/IAY/5181234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117437935 | Approved | 28500 | 0 | 2024-09-20
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745006032/IF/IAY/5206741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148546757 | Approved | 28500 | 0 | 2025-03-12
DINDORI / KARANJIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1745006032/IF/IAY/5732143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812443 | Approved | 28500 | 0 | 2024-09-20
DINDORI / KARANJIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1745006032/RC/22012034545768 — KARY KA NAM - C.C. ROD ASHOK KE GHAR SE SHIVKUMAR KE GHAR KI OR GRAM CHANDNA RYT TIKRA TOLA GP CHAND | Ongoing | 67500 | 0 | 2020-11-19
DINDORI / KARANJIYA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair & Maintenance of Cement Concrete Road for Community | Repair & maint of Road | 1745006032/RC/22012034597768 — c.c rod - nagin bai ke ghar se tendha ke ghar ki or jampani gp chandna | Ongoing | 104000 | 0 | 2021-11-27
DINDORI / KARANJIYA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1745006032/RC/22012034842705 — Greval Road Ms School Se Badi Mohla Ki Or Gp Chandna | Approved | 0 | 0 | 2025-04-08
DINDORI / KARANJIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035229423 — परकोलेशन टैंक जामपानी ग्राम पंचायत चंदना जनपद पंचायत करंजिया | Approved | 0 | 0 | 2024-11-16
DINDORI / KARANJIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035229828 — Parkoleson Taink Chandna Tikratola Gp Chandna Jp Kranjiya | Approved | 0 | 0 | 2024-11-18
DINDORI / KARANJIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035245616 — parkuleshan talab nirman karye kapoti nala tikara tola | Approved | 0 | 0 | 2024-08-18
DINDORI / KARANJIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035245618 — parkuleshan tenk nirman karye giti nala chandana ryt | Approved | 0 | 0 | 2024-08-18
DINDORI / KARANJIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035247973 — NAVEEN TALAB NIRMAN KARYAE KAPOTI NALI | Approved | 0 | 0 | 2024-05-04
DINDORI / KARANJIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035248116 — Parkoleson Taik JHiriya Nala Chandna Ryt Gp Chandna Jp Karnjiya | Approved | 0 | 0 | 2024-11-17
DINDORI / KARANJIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035248120 — Naveen Talab Parsha Nala Chandna Tikratola Gp Chandna Jp Karanjiya | Approved | 0 | 0 | 2024-11-17
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035278750 — JGSA Naveen Talab Gitti Nala Chandna Ryt Gp Chandna | Approved | 0 | 0 | 2025-04-08
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035278787 — JGSA Naveen Talab Gitti Nala Chandna Ryt Gp Chandna | New | 0 | 0 | 2025-04-08
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035278790 — JGSA Naveen Talab Gitti Nala Chandna Ryt Gp Chandna | New | 0 | 0 | 2025-04-08
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035278793 — JGSA Naveen Talab Junvani Nala Madhopur GpChandna | Approved | 1799927.47 | 0 | 2025-04-08
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035278811 — JGSA Naveen Talab Kapoti Nala GpChandna | Approved | 0 | 0 | 2025-04-08
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035282640 — JGSA Talab Gahrikaran Madhopur Gp Chandna Jp Karanjioya | Approved | 0 | 0 | 2025-04-08
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035282663 — JGSA Talab Gahrikaran Dhanrash Ryt Gp Chandna Jp Karanjioya | Approved | 0 | 0 | 2025-04-08
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035297435 — JGSA Naveen Talab Dhanrash Karnai Nala Ke Pas Gp Chandna Jp Karanjiya | Approved | 0 | 0 | 2025-04-14
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035310051 — Talab Gahrikaran Chandna Tikratola Gp Chandna | Approved | 0 | 0 | 2025-04-14
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/22012035310082 — JGSA Recarge Pit Nirman Kapidhara Koop Subhan Ke Ghar Pas Dhanrash Gp Chandna | New | 0 | 0 | 2025-04-14
DINDORI / KARANJIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1745006032/WC/22012035327075 — Nveen Talab Nistari Bade Chhapar Jampani Gp Chandna Jp Karanjiya | Approved | 0 | 0 | 2025-12-28
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035330114 — Bolder chek dem Sarai Nala Chandna Ryt | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035330117 — Gully Plug Nirman Kary Saja Nala Chandna Ryt | Ongoing | 81670.28 | 48760 | 2026-08-24
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035330119 — Gully Plug Nirman Kary Jhandi Nala Chandna Ryt | Ongoing | 75698.43 | 41710 | 2026-08-24
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035330120 — Gully Plug Nirman Kary Kaner Nala Chandna Ryt | Ongoing | 70125.97 | 43870 | 2026-08-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035330121 — Gully Plug Nirman Kary Sagvan Nala Chandna Ryt | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035330416 — Gully Plug Nirman Kary Hara Nala Dhanrash Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035330418 — Gully Plug Nirman Kary Parsa Nala Dhanrash Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035330419 — Gully Plug Nirman Kary Sarhad Nala Dhanrash Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035330421 — Gully Plug Nirman Kary Bar Nala Chandna Ryt | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035331364 — Gully Plug Nirman Kary Kosum Nala Dhanras Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035331366 — Gully Plug Nirman Kary Barmasiya Nala Dhanras Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035331368 — Gully Plug Nirman Kary Jam Nala Dhanras Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035331370 — Gully Plug Nirman Kary Pipal Nala Dhanras Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035331371 — Gully Plug Nirman Kary Kagdi Nala Dhanras Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035331373 — Gully Plug Nirman Kary Neem Nala Dhanras Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1745006032/WC/VB/22012035331374 — Gully Plug Nirman Kary Haindpaump Nala Dhanras Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332327 — Bolder chek dem Thakurdev Nala Dhanrash Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332329 — Bolder chek dem Parsa Nala Dhanrash Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332330 — Bolder chek dem Hara Nala Dhanrash Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332331 — Bolder chek dem Patparha Nala Dhanrash Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332332 — Bolder chek dem Jamun Nala Dhanrash Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332333 — Bolder chek dem Gitti Nala Dhanrash Gp Chandna | New | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332335 — Bolder chek dem Gitti Nala Dhanrash Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332336 — Bolder chek dem Pipal Nala Dhanrash GpChandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332766 — Bolder chek dem Kanhar Nala Chandna Ryt Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332768 — Bolder chek dem Bela Nala Chandna Ryt Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332769 — Bolder chek dem Ghori Nala Chandna Ryt Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332771 — Bolder chek dem Tulshi Nala Chandna Ryt Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332772 — Bolder chek dem Sheetal Nala Chandna Ryt Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332775 — Bolder chek dem Dev Nala Chandna Ryt Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332801 — Bolder chek dem Dhanva Nala Chandna Ryt Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332804 — Bolder chek dem Mahuva Nala Chandna Ryt Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035332805 — Bolder chek dem Chakoda Nala Chandna Ryt Gp Chandna | Approved | 0 | 0 | 2026-06-05
DINDORI / KARANJIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1745006032/WC/VB/22012035333873 — Bolder chek dem Hara Nala Dhanrash Gp Chandna | Approved | 0 | 0 | 2026-06-05